## 본공사입.출고현황
|  | ■ 본공사 자재 입.출고 현황 (Status of main construction materials) | [5 empty] | Current status of Doosan | [5 empty] | ※ Update every Sunday!!
|  | 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [16 empty] | 2026-06-01
| Code | No | Sortation | Material No. | Items / Services | Size | Unit | DOOSAN | [5 empty] | DAESUN |  |  |  |  | Remarks |  | Description | Size | Unit |  |  |  | installed |  | 실재고와 차이 | Checking of Balance
[8 empty] | Purchase | Incoming | Not come | Other company | Handover | Balance | Incoming | Install | Fabrication | Scrap/ Faulty | Balance | time axis 2025-04-12 to 2026-03-04
1 |  | A |  | Grounding | [24 empty] | 0
9 | GR001 | 1 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 17500 | 17200 | 300 | 300 | 17200 | 0 | 17200 | 14194.1 |  | 872.4 | 2133.5 |  |  | Ground Cable | 78SQ | M | O |  |  | 13643.384 |  | -1281 | 1318 | 1258 | 1258 | 1258 | 1223 | 1223 | 1223 | 1223 | 1223 | 1223 | 1223 | 1110.5 | 1110.5 | 1110.5 | 1110.5 | 1065.5 | 977.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 852.5 | 838.5 | 807 | 807 | 807 | 807 | 2252 | 2246 | 6
3 | GR002 | 2 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 3120 | 3120 | 0 |  | 3120 | 0 | 3120 | 258 |  | 0 | 2862 |  |  | Ground Cable | 70SQ | M | O |  |  | 22.1 |  | 80 | 3120 |  | 3120 | 3120 | 3120 | 3120 | 3120 | 3068 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2942 | 2906 | 2906 | 2906 | 2906 | 2906 | 2906 | 2906 | 2862 | 2862
4 | GR003 | 3 | Ground Fitting | Ground TERMINAL LUG 70mm2 | Terminal Lug | 70mm2 | EA | 200 | 200 | 0 |  | 200 | 0 | 200 |  |  |  | 200 |  |  | Ground TERMINAL LUG | 70mm2 | EA | O |  |  |  |  | -9 | 191 |  | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 191 | 200 | 200
5 | GR004 | 4 | Ground | Cadweld Powder #90 | Cadweld Powder | #90 | EA | 100 | 100 | 0 |  | 100 | 0 | 100 | 5 |  | 2 | 93 |  | 100 | Cadweld Powder | #90 | EA | O |  |  | 4 |  | 0 | 97 |  | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 97 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93 | 93
6 | GR005 | 5 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 540 | 540 | 0 |  | 540 | 0 | 540 | 207 |  | 16 | 317 |  | 419 | Cadweld Powder | #115 | EA | O |  |  | 151 | 389 | 47 | 414 |  | 414 | 414 | 414 | 414 | 414 | 404 | 394 | 394 | 394 | 384 | 384 | 384 | 384 | 374 | 374 | 374 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 364 | 359 | 359 | 357 | 347 | 347 | 347 | 347 | 337 | 333 | 4
7 | GR006 | 6 | Ground | Cadweld Powder #150 | Cadweld Powder | #150 | EA | 100 | 100 | 0 |  | 100 | 0 | 100 |  |  |  | 100 |  | 98 | Cadweld Powder | #150 | EA | O |  |  |  |  | -2 | 98 |  | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 100 | 100
8 | GR007 | 7 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 1332 | 1332 | 0 |  | 1332 | 0 | 1332 | 742 |  | 223 | 367 |  | 430 | Cadweld Powder | #200 | EA | O |  |  | 740 |  | 2 | 410 | 400 | 400 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 369 | 367 | 367 | 367 | 367 | 367 | 367
9 | GR008 | 8 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | 30 | 30 | 0 |  | 30 | 0 | 30 | 13 |  |  | 17 |  | 19 | Cadweld Mold | Cross (+) | EA | O |  |  |  |  | 1 | 18 |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 17 | 17
10 | GR009 | 9 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | 12 | 12 | 0 |  | 12 | 0 | 12 | 3 |  | 0 | 9 |  | 7 | Cadweld Mold | Parallel (=) | EA | O |  |  |  |  | 2 | 12 |  | 12 | 12 | 12 | 12 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
11 | GR010 | 10 | Ground | Cadweld TAC-Y4Y4 | Welding Mold | Cross (T) | EA | 5 | 5 | 0 |  | 5 | 0 | 5 | 1 |  | 0 | 4 |  | 9 | Cadweld Mold | Cross (T) | EA | O |  |  |  |  | 0 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
12 | GR011 | 11 | Ground | Zinc Spray | Zinc Spray |  | EA | 196 | 196 | 0 |  | 196 | 0 | 196 | 99 |  |  | 97 |  | 128 | Zinc Spray |  | EA |  |  |  | 91 |  | 8 | 130 |  | 130 | 130 | 130 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 129 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
13 | GR012 | 12 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 770 | 20 | 750 |  | 20 | 0 | 20 | 11 |  | 0 | 9 |  |  | Nicoband | 10m x 15cm | EA |  |  |  | 24 | m | 7 | 20 |  | 20 | 20 | 20 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 17 | 17 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
14 | GR013 | 13 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 2200 | 2200 | 0 |  | 2200 | 0 | 2200 | 859 |  | 121 | 1220 |  |  | Flexible Conduit | 2", 50mm | M |  |  |  | 632.46 |  | 58 | 1500 |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1450 | 1320 | 1320 | 1320 | 1320 | 1320 | 1320 | 1320 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1278 | 1276 | 1276 | 1276 | 1247.5 | 1247.5 | 1247.5 | 1247.5 | 1220 | 1220
15 | GR014 | 14 | PVC PIPE | PVC Flexible Pipe ф 20 | PVC PIPE | ф20 | M | 140 | 140 | 0 |  | 140 | 0 | 140 | 0 |  | 0 | 140 |  |  | PVC Flexible Pipe ф 20 | ф20 | M | [5 empty] | -140 | 2025-04-12: 60; 2025-04-25: 60; 2025-04-30: 60; 2025-05-10: 60; 2025-05-15: 60; 2025-05-24: 60; 2025-05-29: 60; 2025-06-12: 60; 2025-06-21: 60; 2025-06-29: 60; 2025-07-05: 60; 2025-07-13: 60; 2025-07-19: 60; 2025-07-27: 60; 2025-08-02: 60; 2025-08-07: 60; 2025-08-16: 60; 2025-08-21: 60; 2025-08-27: 60; 2025-09-04: 60; 2026-02-25: 140; 2026-03-04: 140
16 | GR015 | 15 | Ground | nVent Exothemic Welding Control Unit | CAD WELD GUN |  | EA | 3 | 3 | 0 |  | 3 | 0 | 3 | 2 |  | 0 | 1 |  | 1 | Welding Control Unit |  | EA | [5 empty] | 0 | bar: 2025-04-12; 2025-04-25 to 2026-03-04
17 |  | B |  | Conduit |  |  |  |  | 0 |  |  | 0 | 0 |  |  |  |  | 0 | [10 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
18 | CO001 | 1 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M | 2551 | 2437 | 114 |  | 2437 | 0 | 2437 | 1438 | 597 | 270 | 132 |  |  | Conduit (Galvanized) | 4.5" | M | O |  | 3" | 1331.121 | -120.879 | 600.6 | 68 |  | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 |  | 0 | 0 | 0 | 0 | 830 | 830 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 732.6 | 840 | 840
19 | CO002 | 2 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 5390 | 5390 | 0 |  | 5390 | 0 | 5390 | 1452 | 460 | 238 | 3240 | ULD 및 UGD 필요수량 포함 |  | Conduit (Galvanized) | 3" | M | O |  | 4" | 5156.088 | -0.4 | 84 | 612 |  | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 3618 | 3564 | 3564 | 3564 | 3564 | 3564 | 3564 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324 | 3324
20 | XX-CO003 | 3 | Conduit | Conduit 159x4.5 | Conduit | 159x6.0 | M | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 설계 변경 → 6.5"(168mm) | holding | Conduit | 6" | M | 삭제 요망 |  | 4.5" | 933.165 | -504.835 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | CO003 | 4 | Conduit | Conduit (Galvanized) 168x6 | Conduit (Galvanized) | 168x6 | M | 172 | 0 | 172 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 설계 추가 |  | Conduit (Galvanized) | 6.5" | M | O |  | 5.5" | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 172
21 | CO004 | 5 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 1400.32 | 1400.32 | 0 |  | 1400.32 | 0 | 1400.32 | 1176 |  | 116.32 | 108 |  |  | Conduit | 6" | M | O |  | 6" | 1175.36 | -0.64 | 0 | 190 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 162 | 156 | 156 | 156 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108 | 108
22 | CO005 | 6 | Conduit | Conduit (Galvanized) 140x5 | Conduit (Galvanized) | 140x5 | M | 530 | 530 | 0 |  | 530 | 0 | 530 | 0 | 189 | 0 | 341 |  | holding | Conduit (Galvanized) | 5.5" | M |  |  | 6.5" | 0 | 0 | 0.16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 451 | 530 | 530 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341.16 | 341 | 341
23 | XX-CO006 | 7 | Conduit | Conduit 108x5 | Conduit | 108x5 | M | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 설계 삭제(토건 역무) | holding | Conduit | 4" | M | 삭제 요망 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | CO007 | 8 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 6040 | 5956 | 84 | 66 | 5956 | 0 | 5956 | 5156.488 | 113 | 555.512 | 131 | (Scrap 555.5)-(발전기 굴뚝 : 86M) |  | Conduit | 4" | M | O |  |  |  |  | -66 | 937.5 | 841 | 640 | 640 | 640 | 640 | 467 | 467 | 467 | 447 | 314 | 314 | 307.5 | 305.5 | 295.5 | 295.5 | 235.17 | 235.17 | 122.9 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 131 | 131
25 | CO008.1 | 9 | Conduit | Conduit (Galvanized) 60.3x3.91 | Conduit (Galvanized) | 60.3x3.91 | M | 18 | 18 | 0 |  | 18 | 0 | 18 | 18 | 0 | 0 | 0 | 추가 |  | Conduit (Galvanized) | 2" | M | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | CO009 | 10 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M | 44 | 44 | 0 |  | 44 | 0 | 44 | 1.3 |  | 0 | 42.7 | 284.6667 | 0.14573 | Coupling | 6" | EA | O |  |  |  |  | 0 |  |  | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 43 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7 | 42.7
27 | CO010 | 11 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 200 | 200 | 0 |  | 200 | 0 | 200 | 188 | 0 | 0 | 12 |  |  | Coupling | 6" | EA | O |  |  |  |  | 0 |  |  | 26 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
28 | CO011 | 12 | Conduit Fitting | Conduit Coupling 125-Ts | Conduit Coupling | Ts-125x5 | EA | 120 | 60 | 60 |  | 60 | 0 | 60 | 0 | 14 | 0 | 46 |  | holding | Coupling (Galvanized) | 5.5" | EA | [5 empty] | 14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
29 | CO012 | 13 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M | 104 | 104 | 0 |  | 104 | 0 | 104 | 48 | 1.5 | 0 | 54.5 | 363.3333 | 0.088907 | Coupling | 4" | EA | O |  |  |  |  | 0 | 72.5 | 72.5 | 72.5 | 71.5 | 70 | 71.5 | 71.5 | 71.5 | 71.5 | 68.5 | 68.5 | 68.5 | 56.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5 | 54.5
30 | CO013 | 14 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 456 | 456 | 0 |  | 456 | 0 | 456 | 423 | 33 | 0 | 0 |  |  | Coupling | 4" | EA | O |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | CO014 | 15 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA | 280 | 280 | 0 |  | 280 | 0 | 280 | 175 |  | 0 | 105 |  |  | Coupling (Galvanized) | 4.5" | EA | O |  |  |  |  | 20 | 7 | 7 | 7 | 7 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
32 | CO015 | 16 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 440 | 440 | 0 |  | 440 | 0 | 440 | 368 |  | 0 | 72 |  |  | Coupling (Galvanized) | 3" | EA | O |  |  |  |  | -11 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 60 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 55 | 53 | 30 | 30 | 30 | 30 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 299 | 299
| CO015.1 | 17 | Conduit Fitting | Conduit Coupling | Conduit Coupling | 50-11 NPT | EA | 9 | 9 | 0 |  | 9 | 0 | 9 | 9 | 0 |  | 0 | 추가 |  | Coupling (Galvanized) | 2" | EA
33 | CO016 | 18 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 3584 | 3584 | 0 |  | 3584 | 0 | 3584 | 2726 | 459.1 | 326.9 | 72 | ULD 및 UGD 필요수량 포함 |  | Angle | 50*50*5 | M | O |  |  |  |  | 0 | 858 | 858 | 840 | 780 | 660 | 636 | 624 | 540 | 516 | 396 | 396 | 348 | 264 | 252 | 204 | 204 | 204 | 204 | 204 | 204 | 168 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 72 | 872 | 872
34 | CO017 | 19 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 732 | 732 | 0 |  | 732 | 0 | 732 | 414.4 |  | 29.6 | 288 |  |  | Angle | 70*70*7 | M | O |  |  |  |  | 0 | 432 | 432 | 336 | 336 | 336 | 336 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 318 | 318 | 318 | 318 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288
35 | CO018 | 20 | Sup't | Angle 75x75x5 | Angle | 75x75x5 | M | 40 | 40 | 0 |  | 40 | 0 | 40 | 35 |  | 5 | 0 |  |  | Angle | 75x75x5 | M | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | CO019a | 21 | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 23 | 6 | 17 | 1 | 6 | 0 | 6 | 5 |  |  | 1 |  |  | Paint | 16L | CAN | [5 empty] | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
36 | CO019b | 22 | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 23 | 6 | 17 | 1 | 6 | 0 | 6 | 5 |  |  | 1 |  |  | Paint | 4L | CAN | [5 empty] | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
37 | CO020 | 23 | Paint | JOTUN Pipe Top-coated Paint | Paint | 20L | CAN | 21 | 0 | 21 | 1 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | Paint | 20L | CAN | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | CO021 | 24 | Paint | JOTUN Thinner | Paint | 20L | CAN | 21 | 2 | 19 | 1 | 2 | 0 | 2 | 1 |  |  | 1 |  |  | Thinner | 20L | CAN | [5 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
39 |  | C |  | CCGG |  |  |  |  | 0 |  |  | 0 | 0 | [15 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
40 | CG001 | 1 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 156805.25 | 111445.25 | 45360 |  | 111445.25 | 0 | 111445.25 | 100172.6 | 800 | 1816.833 | 8655.817 | 1 ton=1620.7 | 1Roll=3130m | Steel round bar(rebar) | ф10 | M | O |  |  |  |  | -2473.817 | 4390 | 3239 | 3241.4 | 2608 | 1180 | 4062 | 2852 | 2002 | 1362 | 6952.8 | 5322.8 | 4962.8 | 3612.8 | 2742.8 | 1322.8 | 6580.6 | 5680.6 | 4980.6 | 3430.6 | 2730.6 | 6553.4 | 5210.4 | 5010.4 | 2090 | 1905 | 7500 | 5525 | 4450 | 2879 | 7924 | 6182 | 4971 | 6981 | 5821 | 2966 | 6748 | 3180 | 6280 | 4093 | 878 | 15010.217 | 12620.217 | 2390
41 | CG002 | 2 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 3132 | 1200 | 1932 |  | 1200 | 0 | 1200 | 927 | 3.5 | 19.5 | 250 |  | 1EA=12m | Angle | 100x100x10 (12m) | M | O | 1/8, 14*6=84m |  |  |  | 315 | 408 | 408 | 378 | 378 | 378 | 354 | 342 | 330 | 312 | 240 | 240 | 228 | 216 | 198 | 156 | 126 | 126 | 126 | 114 | 90 | 78 | 618 | 612 | 576 | 576 | 576 | 572 | 572 | 571 | 571 | 565 | 564 | 558 | 549.5 | 549.5 | 549.5 | 549.5 | 450 | 450 | 420 | 267.02 | 267.02
42 | CG003 | 3 | Plate | Carbon Plate 1000x6000x8 | CCGG | 1000x6000x8 | PCS | 10 | 1 | 9 |  | 1 | 0 | 1 | 0.8 | 0 | 0 | 0.2 |  |  | Plate | 1000x6000x8 | PCS | O | 1/8, 14*6=84m |  |  |  | -0.2 | 2025-04-12: 408; 2025-04-17: 408; 2025-04-25: 378; 2025-04-30: 378; 2025-05-10: 378; 2025-05-15: 354; 2025-05-24: 342; 2025-05-29: 330; 2025-06-12: 312; 2025-06-21: 240; 2025-06-29: 240; 2025-07-05: 228; 2025-07-13: 216; 2025-07-19: 198; 2025-07-27: 156; 2025-08-02: 126; 2025-08-07: 126; 2025-08-16: 126; 2025-08-21: 114; 2025-08-27: 90; 2025-09-04: 78; 2026-02-25: 1; 2026-03-04: 1
42 | CG004 | 4 | Plate | Carbon Plate 1500x6000x10 | CCGG | 1500x6000x10 | PCS | 1 | 1 | 0 |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  |  | Plate | 1500x6000x10 | PCS | O | 1/8, 14*6=84m |  |  |  | -1 | 2025-04-12: 408; 2025-04-17: 408; 2025-04-25: 378; 2025-04-30: 378; 2025-05-10: 378; 2025-05-15: 354; 2025-05-24: 342; 2025-05-29: 330; 2025-06-12: 312; 2025-06-21: 240; 2025-06-29: 240; 2025-07-05: 228; 2025-07-13: 216; 2025-07-19: 198; 2025-07-27: 156; 2025-08-02: 126; 2025-08-07: 126; 2025-08-16: 126; 2025-08-21: 114; 2025-08-27: 90; 2025-09-04: 78; 2026-02-25: 1; 2026-03-04: 1
0
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
9100
Note on K22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: POR-1038
Note on K25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: POR-1038
Note on M37: 128ea return

## POR Control Log-income
POR CONTROL LOG - Income
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [7 empty] | from Doosan to Daesun
| No | RSI No | POR | Date | Material No. | Sortation | Items / Services | Applicable Code & Standards | Size | Unit | Q'TY | Remarks
[5 empty] | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 6200 | 이전RSI 화인후 수정
[5 empty] | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 0 | 이전RSI 화인후 수정
[5 empty] | GR003 | Ground Fitting | Ground TERMINAL LUG 70mm2 | Terminal Lug | 70mm2 | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR004 | Ground | Cadweld Powder #90 | Cadweld Powder | #90 | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR006 | Ground | Cadweld Powder #150 | Cadweld Powder | #150 | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 232 | 이전RSI 화인후 수정
[5 empty] | GR008 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR010 | Ground | Cadweld TAC-Y4Y4 | Welding Mold | Cross (T) | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA | -30 | 이전RSI 화인후 수정
[5 empty] | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 0 | 이전RSI 화인후 수정
[5 empty] | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 2100 | 이전RSI 화인후 수정
[5 empty] | GR015 | Ground | nVent Exothemic Welding Control Unit | CAD WELD GUN | 0 | EA | 0 | 이전RSI 화인후 수정
[5 empty] | CO001 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M | 107 | 이전RSI 화인후 수정
[5 empty] | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | -1732 | 이전RSI 화인후 수정
[5 empty] | XX-CO003 | Conduit | Conduit 159x4.5 | Conduit | 159x6.0 | M | 0 | 이전RSI 화인후 수정
[5 empty] | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 80.32 | 이전RSI 화인후 수정
[5 empty] | CO005 | Conduit | Conduit (Galvanized) 140x5 | Conduit (Galvanized) | 140x5 | M | 0 | 이전RSI 화인후 수정
[5 empty] | XX-CO006 | Conduit | Conduit 108x5 | Conduit | 108x5 | M | 0 | 이전RSI 화인후 수정
[5 empty] | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | -2469 | 이전RSI 화인후 수정
[5 empty] | XX-CO008 | 0 | 0 | 0 | 0 | 0 | 0 | 이전RSI 화인후 수정
[5 empty] | CO009 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M | 0 | 이전RSI 화인후 수정
[5 empty] | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 10 | 이전RSI 화인후 수정
[5 empty] | CO011 | Conduit Fitting | Conduit Coupling 125-Ts | Conduit Coupling | Ts-125x5 | EA | 0 | 이전RSI 화인후 수정
[5 empty] | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M | 0 | 이전RSI 화인후 수정
[5 empty] | CO013 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 64 | 이전RSI 화인후 수정
[5 empty] | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA | 0 | 이전RSI 화인후 수정
[5 empty] | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | -18 | 이전RSI 화인후 수정
[5 empty] | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | -40 | 이전RSI 화인후 수정
[5 empty] | CO018 | Sup't | Angle 75x75x5 | Angle | 75x75x5 | M | -104 | 이전RSI 화인후 수정
[5 empty] | CO020 | Paint | JOTUN Pipe Top-coated Paint | Paint | 20L | CAN | 0 | 이전RSI 화인후 수정
[5 empty] | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 4755.6 | 이전RSI 화인후 수정 |  | 12893.6 | -8138
[5 empty] | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  | 이전RSI 화인후 수정
1 | 1 | 수기 |  | 2024-02-18 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 2635.22
2 | 2 | 수기 |  | 2024-02-18 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 596.31
3 | 3 | 수기 |  | 2024-02-18 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M | 17.12
4 | 4 | 수기 |  | 2024-02-18 | CO009 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M | 20
5 | 5 | 수기 |  | 2024-02-18 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 200
6 | 6 | 수기 |  | 2024-02-18 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 40
7 | 7 | 수기 |  | 2024-02-26 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 384
8 | 8 | 수기 |  | 2024-02-22 | CO013 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 20
9 | 9 | 수기 |  | 2024-02-22 | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 20
10 | 10 | 수기 |  | 2024-03-13 | CO013 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 30
11 | 11 | 수기 |  | 2024-03-13 | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 20
12 | 12 | 수기 |  | 2024-03-20 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 21
13 | 13 | 수기 |  | 2024-03-20 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 200
14 | 14 | 수기 |  | 2024-03-20 | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA | 126
15 | 15 | 수기 |  | 2024-03-20 | CO013 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 228
16 | 16 | 수기 |  | 2024-03-20 | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 100
17 | 17 | 수기 |  | 2024-03-27 | Co007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 4.78
18 | 18 | 수기 |  | 2024-03-27 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 3.69
19 | 19 | 수기 |  | 2024-03-27 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M | 2.88
20 | 20 | 수기 |  | 2024-03-27 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 384
21 | 21 | 수기 |  | 2024-03-27 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 156
22 | 22 | 수기 |  | 2024-04-04 | CO013 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 114
23 | 23 | 수기 |  | 2024-04-04 | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 50
24 | 24 | 수기 |  | 2024-04-04 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 300
25 | 25 | 수기 |  | 2024-04-04 | CO018 | Sup't | Angle 75x75x5 | Angle | 75x75x5 | M | 144
26 | 26 | 수기 |  | 2024-05-13 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 1200
27 | 27 | 수기 |  | 2024-05-13 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 276
28 | 28 | 수기 |  | 2024-05-15 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 6500
29 | 29 | 수기 |  | 2024-05-15 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 20
30 | 30 | 수기 |  | 2024-05-15 | CO001 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M | 1500
31 | 31 | 수기 |  | 2024-05-15 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 408
32 | 32 | 수기 |  | 2024-06-06 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 2469
33 | 33 | 수기 |  | 2024-06-06 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 720
34 | 34 | 수기 |  | 2024-06-06 | CO009 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M | 24
35 | 35 | 수기 |  | 2024-06-06 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 252
36 | 36 | 수기 | 9-072-D-450-1020-E /9-072-D-450-1018-E | 2024-06-24 | GR014 | PVC PIPE | PVC Flexible Pipe ф 20 | PVC PIPE | ф20 | M | 140
37 | 37 | 수기 |  | 2024-06-06 | GR003 | Ground Fitting | Ground TERMINAL LUG 70mm2 | Terminal Lug | 70mm2 | EA | 200
38 | 38 | 수기 |  | 2024-06-06 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 10
39 | 39 | 수기 |  | 2024-06-26 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 847
40 | 40 | 수기 |  | 2024-06-26 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M | 84
41 | 41 | 수기 |  | 2024-06-26 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 3120
42 | 42 | 수기 |  | 2024-06-26 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 864
43 | 43 | 수기 |  | 2024-07-22 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 600
44 | 44 | 수기 |  | 2024-07-22 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 150
45 | 45 | 수기 |  | 2024-07-22 | GR008 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | 20
46 | 46 | 수기 |  | 2024-07-22 | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | 5
47 | 47 | 수기 |  | 2024-07-22 | GR010 | Ground | Cadweld TAC-Y4Y4 | Welding Mold | Cross (T) | EA | 5
48 | 48 | 수기 |  | 2024-07-22 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 120
49 | 49 | 수기 |  | 2024-07-22 | GR004 | Ground | Cadweld Powder #90 | Cadweld Powder | #90 | EA | 100
50 | 50 | 수기 |  | 2024-07-22 | GR015 | Ground | nVent Exothemic Welding Control Unit | CAD WELD GUN | 0 | EA | 2
51 | 51 | 수기 |  | 2024-08-19 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 1008
52 | 52 | 수기 |  | 2024-08-19 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 300
53 | 53 | 수기 |  | 2024-08-19 | CO019 | 0 | 0 | 0 | 0 | 0 | 20
54 | 54 | 수기 |  | 2024-08-19 | CO020 | Paint | JOTUN Pipe Top-coated Paint | Paint | 20L | CAN | 0 | 미입고(창고X)
55 | 55 | 수기 |  | 2024-09-11 | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA | 120
56 | 56 | 수기 |  | 2024-09-22 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 1732
57 | 57 | 수기 |  | 2024-09-22 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 128
58 | 58 | 수기 |  | 2024-12-04 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 4500
59 | 59 | 수기 |  | 2024-12-04 | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA | 70
60 | 60 | 수기 |  | 2024-12-04 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 100
61 | 61 | 수기 |  | 2024-12-04 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 150
62 | 62 | 수기 |  | 2024-12-04 | GR006 | Ground | Cadweld Powder #150 | Cadweld Powder | #150 | EA | 100
63 | 63 | 수기 |  | 2024-12-04 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 300
64 | 64 | 수기 |  | 2024-12-04 | GR015 | Ground | nVent Exothemic Welding Control Unit | CAD WELD GUN | 0 | EA | 1
65 | 65 | 수기 |  | 2024-12-04 | GR008 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | 4
66 | 66 | 수기 |  | 2024-03-25 | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA | 30
67 | 67 | 수기 |  | 2024-03-25 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 219
68 | 68 | 수기 |  | 2024-04-02 | GR008 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | 6
69 | 69 | 수기 |  | 2024-05-28 | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | 7
70 | 70 | 수기 |  | 2024-06-05 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 2223
71 | 71 | 수기 |  | 2024-05-06 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 108
72 | 72 | 수기 |  | 2024-03-30 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 866
73 | 73 | 수기 |  | 2024-03-30 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 20
74 | 74 | 수기 |  | 2024-06-05 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 246
75 | 75 | 수기 |  | 2024-12-22 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 12
76 | 76 | 수기 |  | 2024-09-25 | CO008 | 0 | 0 | 0 | 0 | 0 | 53 | 반납
77 | 77 | 수기 |  | 2024-10-19 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 1620
78 | 78 | 수기 |  | 2024-10-30 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 108
79 | 79 | 수기 |  | 2024-11-26 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 3000
80 | 80 | 수기 |  | 2024-11-26 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 128
81 | 81 | 수기 | 9-072-D-450-1039-E | 2024-12-22 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 12 | 1pcs x 12m | 1 pcs
82 | 82 | 수기 |  | 2025-01-01 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 3241.4 | 2ton | 1 roll
83 | 83 | 수기 | 9-072-D-450-1039-E | 2025-01-14 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 360 | 30pcs x 12m | 30 pcs
84 | 84 | 수기 | 9-072-D-450-1040-E | 2025-02-10 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 3241.4 | 2ton | 1 roll
85 | 85 | 수기 | 9-072-D-450-1040-E | 2025-02-16 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton | 2 roll
86 | 86 | 수기 | 9-072-D-450-1040-E | 2025-02-16 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 168 | 28pcs x 6m | 28 pcs
87 | 87 | RSI2025003220 |  | 2025-04-29 | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA
88 | 88 | RSI2025003283 |  | 2025-05-04 | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA | 35 | 1pcs = 1.8 KG
89 | 89 | RSI2025003405 | 9-072-D-450-1040-E | 2025-05-13 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 3241.4 | 2ton | 1 roll
90 | 90 | RSI2025003760 |  | 2025-06-03 | CO019a | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 1
91 | 91 | RSI2025003760 |  | 2025-06-03 | CO019b | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 1
92 | 92 | RSI2025003760 |  | 2025-06-03 | CO021 | Paint | JOTUN Thinner | Paint | 20L | CAN | 1
93 | 93 | RSI2025003833 |  | 2025-06-15 | CO005 | Conduit | Conduit (Galvanized) 140x5 | Conduit (Galvanized) | 140x5 | M | 451 | 1610 KG
94 | 94 | RSI2025003879 /RSI2025003882 | 9-072-D-450-1040-E | 2025-06-18 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton | 2 roll
95 | 95 | RSI X |  | 2025-07-22 | CO019a | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 1
96 | 96 | RSI X |  | 2025-07-22 | CO019b | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 1
97 | 97 | RSI2025004363 | 9-072-D-450-1040-E | 2025-07-28 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
98 | 98 | RSI2025004905 /RSI2025004909 | 9-072-D-450-1040-E | 2025-09-02 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton | 1620.7
99 | 99 | RSI2025005027 |  | 2025-09-08 | CO005 | Conduit | Conduit (Galvanized) 140x5 | Conduit (Galvanized) | 140x5 | M | 79 |  |  | 40690
100 | 100 | RSI2025005027 |  | 2025-09-08 | CO001 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M | 830 |  |  | 25931.2
101 | 101 | RSI2025005027 |  | 2025-09-08 | CO011 | Conduit Fitting | Conduit Coupling 125-Ts | Conduit Coupling | Ts-152x5 | EA | 60 | RSI ITEM 상이함 |  | 14758.8
102 | 102 | RSI2025005027 |  | 2025-09-08 | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA | 125
103 | 103 | RSI2025005027 | 9-072-D-450-1042-E | 2025-09-08 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 540
104 | 104 | RSI2025005106 |  | 2025-09-14 | CO019a | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 1
105 | 105 | RSI2025005106 |  | 2025-09-14 | CO019b | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 1
106 | 106 | RSI2025005319 | 9-072-D-450-1042-E | 2025-09-30 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
107 | 107 | RSI2025005320 |  | 2025-09-30 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 52
108 | 108 | RSI2025005596 |  | 2025-10-20 | CO019a | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 1
109 | 109 | RSI2025005596 |  | 2025-10-20 | CO019b | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 1
110 | 110 | RSI2025005596 |  | 2025-10-20 | CO021 | Paint | JOTUN Thinner | Paint | 20L | CAN | 1
111 | 111 | RSI2025005660 | 9-072-D-450-1042-E | 2025-10-26 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
112 | 112 | RSI2025005934 | 9-072-D-450-1042-E | 2025-11-18 | CG001 | Steel round bar | Round wire 10Ø | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
113 | 113 | RSI2025006016 | 9-072-D-450-1032-E | 2025-11-24 | CO019a | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 2
114 | 114 | RSI2025006016 | 9-072-D-450-1032-E | 2025-11-24 | CO019b | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 2
115 | 115 | RSI2025006220 | 9-072-D-450-1042-E | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
116 | 116 | RSI2025006531 | 9-072-D-450-1045-E | 2025-12-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
117 | 117 | RSI2026000208 | 9-072-D-450-1045-E | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3241.4 | 2ton
118 | 118 | RSI2026000240 | 9-072-D-450-1171-A-0316 | 2026-01-18 | CG004 | Plate | Carbon Plate 1500x6000x10 | CCGG | 1500x6000x10 | PCS | 1
119 | 119 | 수기 | 9-072-D-450-1039-E | 2024-12-22 | CG003 | Plate | Carbon Plate 1000x6000x8 | CCGG | 1000x6000x8 | PCS | 1 | 총10PCS입고후 9PCS확이요
120 | 120 | RSI2026000401 | 9-072-D-450-1045-E | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 6482.8 | 4ton
121 | 121 | 타업체 대여분 회수 |  | 2026-02-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 5672.45 | 3.5ton
122 | 122 | RSI2026000753 | 1152-A-001 /1161-A-001 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 8638 | 5.3ton
123 | 123 | RSI2026001823 | 9-072-D-450-1051-E | 2026-04-29 | CO008.1 | Conduit | Conduit (Galvanized) 60.3x3.91 | Conduit (Galvanized) | 60.3x3.91 | M | 18 | 1pcs 6m
124 | 124 | RSI2026001823 | 9-072-D-450-1051-E | 2026-04-29 | CO015.1 | Conduit Fitting | Conduit Coupling | Conduit Coupling | 50-11 NPT | EA | 9
125 | 125 | RSI2026001861 | 9-072-D-450-1045-E_0038 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 12965.6 | 8TON
126 | 126 |  |  |  |  | 0 | 0 | 0 | 0 | 0
127 | 127 |  |  |  |  | 0 | 0 | 0 | 0 | 0
128 | 128 |  |  |  |  | 0 | 0 | 0 | 0 | 0
129 | 129 |  |  |  |  | 0 | 0 | 0 | 0 | 0
130 | 130 |  |  |  |  | 0 | 0 | 0 | 0 | 0
131 | 131 |  |  |  |  | 0 | 0 | 0 | 0 | 0
132 | 132 |  |  |  |  | 0 | 0 | 0 | 0 | 0
133 | 133 |  |  |  |  | 0 | 0 | 0 | 0 | 0
134 | 134 |  |  |  |  | 0 | 0 | 0 | 0 | 0
135 | 135 |  |  |  |  | 0 | 0 | 0 | 0 | 0
136 | 136 |  |  |  |  | 0 | 0 | 0 | 0 | 0
137 | 137 |  |  |  |  | 0 | 0 | 0 | 0 | 0
138 | 138 |  |  |  |  | 0 | 0 | 0 | 0 | 0
139 | 139 |  |  |  |  | 0 | 0 | 0 | 0 | 0
140 | 140 |  |  |  |  | 0 | 0 | 0 | 0 | 0
141 | 141 |  |  |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 3 | 4 | 5 | 6 | 7

## POR Control Log-out
POR CONTROL LOG - Issue
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [5 empty] | from Warehouse & Workshop to Site
| No | Date | Material No. | Sortation | Items / Services | Applicable Code & Standards | Size | Unit | Unit # | BLDG | Q'TY | User | Remarks
| 1 | 2024이전사용분 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 12796.6
| 2 | 2024이전사용분 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M |  |  | 18
| 3 | 2024이전사용분 | GR003 | Ground Fitting | Ground TERMINAL LUG 70mm2 | Terminal Lug | 70mm2 | EA |  |  | 9
| 4 | 2024이전사용분 | GR004 | Ground | Cadweld Powder #90 | Cadweld Powder | #90 | EA |  |  | 5
| 5 | 2024이전사용분 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA |  |  | 94
| 6 | 2024이전사용분 | GR006 | Ground | Cadweld Powder #150 | Cadweld Powder | #150 | EA |  |  | 2
| 7 | 2024이전사용분 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA |  |  | 678
| 8 | 2024이전사용분 | GR008 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA |  |  | 12
| 9 | 2024이전사용분 | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA |  |  | 0
| 10 | 2024이전사용분 | GR010 | Ground | Cadweld TAC-Y4Y4 | Welding Mold | Cross (T) | EA |  |  | 1
| 11 | 2024이전사용분 | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA |  |  | 87
| 12 | 2024이전사용분 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA |  |  | 0
| 13 | 2024이전사용분 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M |  |  | 563
| 15 | 2024이전사용분 | GR015 | Ground | nVent Exothemic Welding Control Unit | CAD WELD GUN | 0 | EA |  |  | 2
| 16 | 2024이전사용분 | CO001 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M |  |  | 934
| 17 | 2024이전사용분 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M |  |  | 1398
| 18 | 2024이전사용분 | XX-CO003 | Conduit | Conduit 159x4.5 | Conduit | 159x6.0 | M |  |  | 0
| 19 | 2024이전사용분 | CO003 | Conduit | Conduit (Galvanized) 168x6 | Conduit (Galvanized) | 168x6 | M |  |  | -24
| 20 | 2024이전사용분 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M |  |  | 1085.5
| 21 | 2024이전사용분 | CO005 | Conduit | Conduit (Galvanized) 140x5 | Conduit (Galvanized) | 140x5 | M |  |  | 0
| 22 | 2024이전사용분 | XX-CO006 | Conduit | Conduit 108x5 | Conduit | 108x5 | M |  |  | 0
| 23 | 2024이전사용분 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 4447.388
| 24 | 2024이전사용분 | XX-CO008 | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 25 | 2024이전사용분 | CO009 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M |  |  | 0
| 26 | 2024이전사용분 | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA |  |  | 180
| 27 | 2024이전사용분 | CO011 | Conduit Fitting | Conduit Coupling 125-Ts | Conduit Coupling | Ts-125x5 | EA |  |  | 0
| 28 | 2024이전사용분 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M |  |  | 30
| 29 | 2024이전사용분 | CO013 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA |  |  | 423
| 30 | 2024이전사용분 | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA |  |  | 78
| 31 | 2024이전사용분 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA |  |  | 24
| 32 | 2024이전사용분 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 1843
| 33 | 2024이전사용분 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M |  |  | 361.9
| 34 | 2024이전사용분 | CO018 | Sup't | Angle 75x75x5 | Angle | 75x75x5 | M |  |  | 34
| 35 | 2024이전사용분 | CO019a | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN |  |  | 5
| 36 | 2024이전사용분 | CO019b | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN |  |  | 5
| 37 | 2024이전사용분 | CO020 | Paint | JOTUN Pipe Top-coated Paint | Paint | 20L | CAN |  |  | 0
| 38 | 2024이전사용분 | CO021 | Paint | JOTUN Thinner | Paint | 20L | CAN |  |  | 1
| 39 | 2024이전사용분 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 4181.6
| 40 | 2024이전사용분 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 385 |  |  | 444 | 829
1 | 1 | 2025-01-01 | CO018 | Sup't | Angle 75x75x5 | Angle | 75x75x5 | M | 2 | 20USJ | 1 | Hussien Elsayed
2 | 2 | 2025-01-01 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 4 | 40 UMA | 4.5 | Hussien Elsayed
3 | 3 | 2025-01-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 78 | Ahmed Saeed | Fabrication |  | 130
4 | 4 | 2025-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 72 | Ahmed Saeed | Fabrication |  | 120
5 | 5 | 2025-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 78 | Ahmed Saeed | Fabrication |  | 130
6 | 6 | 2025-01-08 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 3 | 30UMA | 50
7 | 7 | 2025-01-11 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 3 | 30UMA | 25 |  | 50*0.5=25m
8 | 8 | 2025-01-11 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 3 | 30UMA | 6
9 | 9 | 2025-01-11 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 3 | 30UMA | 10
10 | 10 | 2025-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 30 |  | 50*0.6=30m
11 | 11 | 2025-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 97 | Ahmed Saeed | Fabrication
12 | 12 | 2025-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 105 | Ahmed Saeed | Fabrication
13 | 13 | 2025-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 100
14 | 14 | 2025-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 480 |  | Fabrication
15 | 15 | 2025-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 280 |  | Fabrication
16 | 16 | 2025-02-24 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 4 | 40UMA | 505 |  | bay4.3~4.5, 2/20~2-/24
17 | 17 | 2025-02-24 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 4 | 40UMA | 4 |  | bay4.3~4.5, 2/20~2-/24
18 | 18 | 2025-02-24 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 4 | 40UMA | 32 |  | bay4.3~4.5, 2/20~2-/24
19 | 19 | 2025-02-24 | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA | 4 | 40UMA | 4 |  | bay4.3~4.5, 2/20~2-/24
20 | 20 | 2025-02-24 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 4 | 40UMA | 14 |  | bay4.3~4.5, 2/20~2-/24
21 | 21 | 2025-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 0 |  | 150 | Ahmed Saeed
22 | 22 | 2025-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 300 | Ahmed Saeed
23 | 23 | 2025-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 0 |  | 200 | Ahmed Saeed
24 | 24 | 2025-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 360 | Ahmed Saeed
25 | 25 | 2025-03-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 410 | Ahmed Saeed
26 | 26 | 2025-03-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 60 | Ahmed Saeed
27 | 27 | 2025-03-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 0 | workshop | 400 | Ahmed Saeed | Fabrication
28 | 28 | 2025-03-19 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 0 | workshop |  | Hussien Elsayed | Fabrication
29 | 29 | 2025-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 300 | Hussien Elsayed
30 | 30 | 2025-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 400 | Hussien Elsayed
31 | 31 | 2025-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 140 | Hussien Elsayed | Fabrication
32 | 32 | 2025-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | workshop | 175 | Hussien Elsayed | Fabrication
33 | 33 | 2025-03-27 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 2 | 20USJ | 5 | Hussien Elsayed
34 | 34 | 2025-03-27 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 4 | 40UGB | 6 | Hussien Elsayed
35 | 35 | 2025-03-27 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 4 | 40UGB | 100
36 | 36 | 2025-03-27 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 4 | 40UGB | 20
37 | 37 | 2025-04-08 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 60
38 | 38 | 2025-04-09 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 60
39 | 39 | 2025-04-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 670 | Hussien Elsayed
40 | 40 | 2025-04-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 180 | Hussien Elsayed
41 | 41 | 2025-04-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 280 | Hussien Elsayed
42 | 42 | 2025-04-16 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA |  |  | 10 | salama
43 | 43 | 2025-04-14 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 4 |  | 40 | Hussien Elsayed
44 | 44 | 2025-04-14 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 4 |  | 80 | Hussien Elsayed
45 | 45 | 2025-04-15 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 3 |  | 84 | Hussien Elsayed
46 | 46 | 2025-04-15 | CO003 | Conduit | Conduit (Galvanized) 168x6 | Conduit (Galvanized) | 168x6 | M | 3 |  | 24 | Hussien Elsayed |  |  | CO003→CO004 바뀌어야함??
47 | 47 | 2025-04-16 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 3 |  | 60 | salama
48 | 48 | 2025-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 60 | Taleb
49 | 49 | 2025-04-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 375 | Taleb
50 | 50 | 2025-04-21 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 4 | 40UMA | 4 | Hussien Elsayed
51 | 51 | 2025-04-21 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UMA | 12 | Hussien Elsayed
52 | 52 | 2025-04-22 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 4 | 40UMA | 3 | Hussien Elsayed
53 | 53 | 2025-04-23 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UMA | 12 | Hussien Elsayed
54 | 54 | 2025-04-24 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 2 | 20UMA | 4 | Hussien Elsayed
55 | 55 | 2025-04-25 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 2 | 20USJ | 10 | Hussien Elsayed
56 | 56 | 2025-04-25 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 3 | 30USJ | 30 | Hussien Elsayed
57 | 57 | 2025-04-27 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 24 | Hussien Elsayed
58 | 58 | 2025-04-28 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 36 | Hussien Elsayed
59 | 59 | 2025-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Hussien Elsayed
60 | 60 | 2025-04-29 | CO010 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA |  |  | 8 | Hussien Elsayed
61 | 61 | 2025-04-29 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M |  |  | 1 | Hussien Elsayed
62 | 62 | 2025-04-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 33 | Ahmed Saeed
63 | 63 | 2025-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 120 | Ahmed Saeed
64 | 64 | 2025-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 160 | Ahmed Saeed
65 | 65 | 2025-05-05 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 60 | Ahmed Saeed
66 | 66 | 2025-05-06 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 60 | Ahmed Saeed
67 | 67 | 2025-05-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 260 | Ahmed Saeed
68 | 68 | 2025-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 120 | Ahmed Saeed
69 | 69 | 2025-05-08 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 4 | 40UMA | 35 | Ahmed Saeed
70 | 70 | 2025-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 168 | Ahmed Saeed
71 | 71 | 2025-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Taleb
72 | 72 | 2025-05-10 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | Ahmed Saeed
73 | 73 | 2025-05-10 | CO014 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA |  |  | 97 | Hussien Elsayed
74 | 74 | 2025-05-12 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | Ahmed Saeed
75 | 75 | 2025-05-12 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA |  |  | 1 | Mr. KIM
76 | 76 | 2025-05-13 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | Ahmed Saeed
77 | 77 | 2025-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 360 | Ahmed Saeed
78 | 78 | 2025-05-14 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | Ahmed Saeed
79 | 79 | 2025-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 200 | Ahmed Saeed
80 | 80 | 2025-05-18 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | Ahmed Saeed | Fabrication
81 | 81 | 2025-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 200 | Ahmed Saeed
82 | 82 | 2025-05-19 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 173 | Hussien Elsayed
83 | 83 | 2025-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 422 | Ahmed Saeed
84 | 84 | 2025-05-20 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | Ahmed Saeed | Fabrication
85 | 85 | 2025-05-21 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M |  |  | 13.5 | Ahmed Saeed | Fabrication
86 | 86 | 2025-05-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 388 | Ahmed Saeed | Fabrication
87 | 87 | 2025-05-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 250 | Ahmed Saeed
88 | 88 | 2025-05-26 | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA |  |  | 1 | salama
89 | 89 | 2025-05-26 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA |  |  | 10 | salama
90 | 90 | 2025-05-26 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M |  |  | 52 | salama
91 | 91 | 2025-05-26 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M |  |  | 50 | salama
92 | 92 | 2025-05-25 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 36 | Ahmed Saeed | Fabrication
93 | 93 | 2025-05-26 | CO016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | Ahmed Saeed | Fabrication
94 | 94 | 2025-05-27 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 36 | Ahmed Saeed | Fabrication
95 | 95 | 2025-05-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Ahmed Saeed
96 | 96 | 2025-05-28 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | Ahmed Saeed
97 | 97 | 2025-06-01 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | ahmed saaed
98 | 98 | 2025-06-01 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA |  |  | 10 | SALAMA
99 | 99 | 2025-06-01 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M |  |  | 126 | SALAMA
100 | 100 | 2025-06-01 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M |  |  | 100 | SALAMA
101 | 101 | 2025-06-02 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | ahmed saaed
102 | 102 | 2025-06-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 60 | ahmed saaed
103 | 103 | 2025-06-03 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M |  |  | 30 | SALAMA
104 | 104 | 2025-06-02 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
105 | 105 | 2025-06-03 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
106 | 106 | 2025-06-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 350 | ahmed saaed
107 | 107 | 2025-06-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 230 | ahmed saaed
108 | 108 | 2025-06-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 240 | ahmed saaed
109 | 109 | 2025-06-12 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
110 | 110 | 2025-06-13 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 60 | ahmed saaed
111 | 111 | 2025-06-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 412 | ahmed saaed
112 | 112 | 2025-06-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 80 | ahmed saaed
113 | 113 | 2025-06-15 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 48 | ahmed saaed
114 | 114 | 2025-06-15 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M |  |  | 1.5 | Hussien Elsayed
115 | 115 | 2025-06-17 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 20 | Hussien Elsayed
116 | 116 | 2025-06-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 160 | ahmed saaed
117 | 117 | 2025-06-18 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 24 | ahmed saaed
118 | 118 | 2025-06-19 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 24 | ahmed saaed
119 | 119 | 2025-06-19 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M |  |  | 1.5 | Hussien Elsayed
120 | 120 | 2025-06-20 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | abdelrasol
121 | 121 | 2025-06-21 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | ahmed saaed
122 | 122 | 2025-06-22 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 390 | ahmed saaed
123 | 123 | 2025-06-23 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 350 | ahmed saaed
124 | 124 | 2025-06-23 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 133 | Hussien Elsayed
125 | 125 | 2025-06-24 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 340 | ahmed saaed
126 | 126 | 2025-06-25 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 300 | ahmed saaed
127 | 127 | 2025-06-26 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 250 | ahmed saaed
128 | 128 | 2025-06-28 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 48 | ahmed saaed
129 | 129 | 2025-06-30 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 112.5 | salama
130 | 130 | 2025-06-30 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA |  |  | 10 | salama
|  | 2025-06-30 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA |  |  | 1 | salama
131 | 131 | 2025-06-30 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
132 | 132 | 2025-07-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 250 | ahmed saaed
133 | 133 | 2025-07-01 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 36 | ahmed saaed
134 | 134 | 2025-07-02 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
135 | 135 | 2025-07-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 110 | ahmed saaed
136 | 136 | 2025-07-03 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | ahmed saaed
137 | 137 | 2025-07-07 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 24 | ahmed saaed
138 | 138 | 2025-07-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 400 | ahmed saaed
139 | 139 | 2025-07-08 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M |  |  | 12 | ahmed saaed
140 | 140 | 2025-07-08 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 350 | ahmed saaed
141 | 141 | 2025-07-08 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | ahmed saaed
142 | 142 | 2025-07-09 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 6.5 | ahmed saaed
143 | 143 | 2025-07-12 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 48 | Mohamed abdelrahman
144 | 144 | 2025-07-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Mohamed abdelrahman
145 | 145 | 2025-07-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 250 | ahmed saaed
146 | 146 | 2025-07-13 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | ahmed saaed
147 | 147 | 2025-07-13 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
148 | 148 | 2025-07-14 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
149 | 149 | 2025-07-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 500 | ahmed saaed
150 | 150 | 2025-07-15 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 2 | Hussien Elsayed | Nikimt
151 | 151 | 2025-07-15 | CO004 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M |  |  | 6 | Hussien Elsayed | Nikimt
152 | 152 | 2025-07-15 | CO012 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M |  |  | 2 | Hussien Elsayed | Nikimt
153 | 153 | 2025-07-15 | CO009 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M |  |  | 1 | Hussien Elsayed | Nikimt
154 | 154 | 2025-07-15 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
155 | 155 | 2025-07-16 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 300 | ahmed saaed
156 | 156 | 2025-07-19 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 70 | Wael Ragab
157 | 157 | 2025-07-19 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | Wael Ragab
158 | 158 | 2025-07-19 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | Wael Ragab
159 | 159 | 2025-07-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 500 | ahmed saaed
160 | 160 | 2025-07-20 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 18 | ahmed saaed
161 | 161 | 2025-07-21 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 670 | ahmed saaed
162 | 162 | 2025-07-21 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
163 | 163 | 2025-07-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 150 | ahmed saaed
164 | 164 | 2025-07-22 | CO009 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M |  |  | 0.3 | ahmed saaed
165 | 165 | 2025-07-23 | Co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 48 | ahmed saaed
166 | 166 | 2025-07-24 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 10 | ahmed saaed
167 | 167 | 2025-07-26 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
168 | 168 | 2025-07-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 100 | ahmed saaed
169 | 169 | 2025-07-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 750 | ahmed saaed
170 | 170 | 2025-07-27 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 45 | SALAMA
171 | 171 | 2025-07-27 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA |  |  | 10 | SALAMA
172 | 172 | 2025-07-27 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M |  |  | 42 | SALAMA
173 | 173 | 2025-07-27 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
174 | 174 | 2025-07-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 500 | ahmed saaed
175 | 175 | 2025-07-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 450 | ahmed saaed
176 | 176 | 2025-07-29 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M |  |  | 6 | ahmed saaed
177 | 177 | 2025-07-30 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 18 | ahmed saaed
178 | 178 | 2025-07-31 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 200 | Taleb
179 | 179 | 2025-08-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 75 | Taleb
180 | 180 | 2025-08-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 100 | ahmed saaed
181 | 181 | 2025-08-03 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 88 | SALAMA
182 | 182 | 2025-08-03 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA |  |  | 2 | SALAMA
183 | 183 | 2025-08-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | ahmed saaed
184 | 184 | 2025-08-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 200 | ahmed saaed
185 | 185 | 2025-08-06 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 60.33 | Hussien Elsayed
186 | 186 | 2025-08-09 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA |  |  | 2 | SALAMA
187 | 187 | 2025-08-09 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 60 | SALAMA
188 | 188 | 2025-08-11 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Ahmed Saaed
189 | 189 | 2025-08-11 | CO002 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M |  |  | 54 | Ahmed Saaed
190 | 190 | 2025-08-12 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M |  |  | 65 | SALAMA
191 | 191 | 2025-08-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 100 | Ahmed Saaed
192 | 192 | 2025-08-13 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA |  |  | 74 | Ahmed Saaed
193 | 193 | 2025-08-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Ahmed saaed
194 | 194 | 2025-08-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 650 | Ahmed saaed
195 | 195 | 2025-08-18 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA |  |  | 10 | SALAMA
196 | 196 | 2025-08-18 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 112.27 | Ahmed saaed
197 | 197 | 2025-08-20 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 300 | Ahmed saaed
198 | 198 | 2025-08-21 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | Ahmed saaed
199 | 199 | 2025-08-21 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 80 | Ahmed saaed
200 | 200 | 2025-08-23 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 200 | Ahmed saaed
201 | 201 | 2025-08-24 | CO007 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M |  |  | 58 | NIKMET
202 | 202 | 2025-08-24 | CO017 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M |  |  | 30 | NIKMET
203 | 203 | 2025-08-24 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA |  |  | 1 | salama
204 | 204 | 2025-08-24 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 24 | ahmed saaed
205 | 205 | 2025-08-26 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 350 | Taleb
206 | 206 | 2025-08-27 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 150 | Taleb
207 | 207 | 2025-08-28 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 350 | ahmed saaed
208 | 208 | 2025-08-28 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 36 | Taleb
209 | 209 | 2025-08-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 600 | Taleb
210 | 210 | 2025-08-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 60 | ahmed saaed
211 | 211 | 2025-08-31 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 100 | ahmed saaed
212 | 212 | 2025-08-31 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
213 | 213 | 2025-09-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 550 | ahmed saaed
214 | 214 | 2025-09-01 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
215 | 215 | 2025-09-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 1000 | ahmed saaed
216 | 216 | 2025-09-04 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA |  |  | 69 | ahmed saaed
217 | 217 | 2025-09-06 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA |  |  | 64 | ahmed saaed
218 | 218 | 2025-09-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 550 | ahmed saaed
219 | 219 | 2025-09-07 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 36 | Wael Ragab
220 | 220 | 2025-09-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 200 | Wael Ragab
221 | 221 | 2025-09-08 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 24 | Wael Ragab
222 | 222 | 2025-09-09 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 24 | Wael Ragab
223 | 223 | 2025-09-10 | co016 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M |  |  | 12 | Wael Ragab
224 | 224 | 2025-09-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 90 | Wael Ragab
225 | 225 | 2025-09-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 400 | ahmed saaed
226 | 226 | 2025-09-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 500 | ahmed saaed
227 | 227 | 2025-09-14 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA |  |  | 62 | Hussien Elsayed
228 | 228 | 2025-09-15 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 250 | ahmed saaed
229 | 229 | 2025-09-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 300 | ahmed saaed
230 | 230 | 2025-09-17 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 6 | ahmed saaed
231 | 231 | 2025-09-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 150 | ahmed saaed
232 | 232 | 2025-09-19 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 250 | ahmed saaed
233 | 233 | 2025-09-19 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
234 | 234 | 2025-09-20 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 150 | ahmed saaed
235 | 235 | 2025-09-20 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
236 | 236 | 2025-09-21 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 300 | ahmed saaed
237 | 237 | 2025-09-22 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 400 | ahmed saaed
238 | 238 | 2025-09-23 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 500 | ahmed saaed
239 | 239 | 2025-09-24 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
240 | 240 | 2025-09-24 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 300 | ahmed saaed
241 | 241 | 2025-09-25 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 670 | Taleb
242 | 242 | 2025-09-26 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  |  | 750 | Taleb
243 | 243 | 2025-09-27 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M |  |  | 12 | ahmed saaed
244 | 244 | 2025-09-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 175 | ahmed saaed
245 | 245 | 2025-09-29 | CO015 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA |  |  | 75 | Hussien Elsayed
246 | 246 | 2025-09-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | ahmed saaed
247 | 247 | 2025-09-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 45 | ahmed saaed
248 | 248 | 2025-09-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 45 | ahmed saaed
249 | 249 | 2025-09-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
250 | 250 | 2025-09-29 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 45 | ahmed saaed
251 | 251 | 2025-09-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 32.5 | ahmed saaed
252 | 252 | 2025-09-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 62.5 | ahmed saaed
253 | 253 | 2025-09-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 210 | ahmed saaed
254 | 254 | 2025-09-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
255 | 255 | 2025-09-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 37.5 | ahmed saaed
256 | 256 | 2025-09-30 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | ahmed saaed
257 | 257 | 2025-10-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 50 | ahmed saaed
258 | 258 | 2025-10-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 175 | ahmed saaed
259 | 259 | 2025-10-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
260 | 260 | 2025-10-01 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 10 | ahmed saaed
261 | 261 | 2025-10-02 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 10 | Taleb
262 | 262 | 2025-10-02 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | Taleb
263 | 263 | 2025-10-02 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
264 | 264 | 2025-10-02 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 30 | Taleb
265 | 265 | 2025-10-02 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Taleb
266 | 266 | 2025-10-02 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 205 | Taleb
267 | 267 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 62.5 | Taleb
268 | 268 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | Taleb
269 | 269 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
270 | 270 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 37.5 | Taleb
271 | 271 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | Taleb
272 | 272 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 50 | Taleb
273 | 273 | 2025-10-03 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
274 | 274 | 2025-10-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | Taleb
275 | 275 | 2025-10-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 45 | Taleb
276 | 276 | 2025-10-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 45 | Taleb
277 | 277 | 2025-10-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
278 | 278 | 2025-10-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 45 | Taleb
279 | 279 | 2025-10-04 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 32.5 | Taleb
280 | 280 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
281 | 281 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 30 | Taleb
282 | 282 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Taleb
283 | 283 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 205 | Taleb
284 | 284 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 62.5 | Taleb
285 | 285 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | Taleb
286 | 286 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
287 | 287 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 37.5 | Taleb
288 | 288 | 2025-10-05 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | Taleb
289 | 289 | 2025-10-06 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 15 | Taleb
290 | 290 | 2025-10-06 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 10 | Taleb
291 | 291 | 2025-10-06 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 4 | 40UGB | 2 | Taleb
292 | 292 | 2025-10-06 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | Taleb
293 | 293 | 2025-10-06 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Taleb
294 | 294 | 2025-10-06 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | Taleb
295 | 295 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 55 | Taleb
296 | 296 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 15 | Taleb
297 | 297 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Taleb
298 | 298 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 5 | Taleb
299 | 299 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
300 | 300 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | Taleb
301 | 301 | 2025-10-07 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Taleb
302 | 302 | 2025-10-08 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Taleb
303 | 303 | 2025-10-08 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 50 | Taleb
304 | 304 | 2025-10-08 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 45 | Taleb
305 | 305 | 2025-10-08 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Taleb
306 | 306 | 2025-10-08 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Taleb
307 | 307 | 2025-10-08 | cg002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UMA | 2 | Taleb
308 | 308 | 2025-10-09 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 45 | Taleb
309 | 309 | 2025-10-09 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | Taleb
310 | 310 | 2025-10-09 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Taleb
311 | 311 | 2025-10-09 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 12 | Taleb
312 | 312 | 2025-10-10 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 10 | Taleb
313 | 313 | 2025-10-10 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 10 | Taleb
314 | 314 | 2025-10-10 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | Taleb
315 | 315 | 2025-10-10 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
316 | 316 | 2025-10-10 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 30 | Taleb
317 | 317 | 2025-10-10 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Taleb
318 | 318 | 2025-10-11 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 55 | ahmed saaed
319 | 319 | 2025-10-11 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 15 | ahmed saaed
320 | 320 | 2025-10-11 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
321 | 321 | 2025-10-11 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 5 | ahmed saaed
322 | 322 | 2025-10-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
323 | 323 | 2025-10-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
324 | 324 | 2025-10-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 40 | ahmed saaed
325 | 325 | 2025-10-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 40 | ahmed saaed
326 | 326 | 2025-10-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
327 | 327 | 2025-10-12 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 30 | ahmed saaed
328 | 328 | 2025-10-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 50 | ahmed saaed
329 | 329 | 2025-10-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 30 | ahmed saaed
330 | 330 | 2025-10-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
331 | 331 | 2025-10-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 20 | ahmed saaed
332 | 332 | 2025-10-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
333 | 333 | 2025-10-13 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M |  | 90UGG | 50 | ahmed saaed
334 | 334 | 2025-10-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
335 | 335 | 2025-10-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 40 | ahmed saaed
336 | 336 | 2025-10-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
337 | 337 | 2025-10-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
338 | 338 | 2025-10-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 10 | ahmed saaed
339 | 339 | 2025-10-14 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
340 | 340 | 2025-10-15 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 40 | ahmed saaed
341 | 341 | 2025-10-15 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | ahmed saaed
342 | 342 | 2025-10-15 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 210 | ahmed saaed
343 | 343 | 2025-10-15 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
344 | 344 | 2025-10-15 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 45 | ahmed saaed
345 | 345 | 2025-10-16 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 25 | ahmed saaed
346 | 346 | 2025-10-16 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 55 | ahmed saaed
347 | 347 | 2025-10-16 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 90 | ahmed saaed
348 | 348 | 2025-10-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
349 | 349 | 2025-10-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 5 | ahmed saaed
350 | 350 | 2025-10-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
351 | 351 | 2025-10-17 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
352 | 352 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
353 | 353 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | Taleb
354 | 354 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 30 | Taleb
355 | 355 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 35 | Taleb
356 | 356 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Taleb
357 | 357 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 40 | Taleb
358 | 358 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 100 | Taleb
359 | 359 | 2025-10-18 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Taleb
360 | 360 | 2025-10-19 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
361 | 361 | 2025-10-19 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
362 | 362 | 2025-10-19 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 40 | ahmed saaed
363 | 363 | 2025-10-19 | cg001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
364 | 364 | 2025-10-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 5 | ahmed saaed
365 | 365 | 2025-10-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 115 | ahmed saaed
366 | 366 | 2025-10-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 40 | ahmed saaed
367 | 367 | 2025-10-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 20 | ahmed saaed
368 | 368 | 2025-10-20 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 4 | 40UGB | 1 | ahmed saaed
369 | 369 | 2025-10-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | ahmed saaed
370 | 370 | 2025-10-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 195 | ahmed saaed
371 | 371 | 2025-10-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | ahmed saaed
372 | 372 | 2025-10-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
373 | 373 | 2025-10-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
374 | 374 | 2025-10-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
375 | 375 | 2025-10-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
376 | 376 | 2025-10-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 125 | ahmed saaed
377 | 377 | 2025-10-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
378 | 378 | 2025-10-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | ahmed saaed
379 | 379 | 2025-10-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 30 | ahmed saaed
380 | 380 | 2025-10-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
381 | 381 | 2025-10-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 60 | ahmed saaed
382 | 382 | 2025-10-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
383 | 383 | 2025-10-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 50 | ahmed saaed
384 | 384 | 2025-10-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 100 | ahmed saaed
385 | 385 | 2025-10-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 80 | ahmed saaed
386 | 386 | 2025-10-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 35 | ahmed saaed
387 | 387 | 2025-10-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
388 | 388 | 2025-10-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
389 | 389 | 2025-10-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
390 | 390 | 2025-10-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 210 | ahmed saaed
391 | 391 | 2025-10-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 10 | 10UGB | 35 | ahmed saaed
392 | 392 | 2025-10-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | ahmed saaed
393 | 393 | 2025-10-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 75 | ahmed saaed
394 | 394 | 2025-10-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
395 | 395 | 2025-10-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 45 | ahmed saaed
396 | 396 | 2025-10-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
397 | 397 | 2025-10-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
398 | 398 | 2025-10-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
399 | 399 | 2025-10-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
400 | 400 | 2025-10-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
401 | 401 | 2025-10-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
402 | 402 | 2025-10-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
403 | 403 | 2025-10-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
404 | 404 | 2025-10-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
405 | 405 | 2025-10-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
406 | 406 | 2025-10-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
407 | 407 | 2025-10-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
408 | 408 | 2025-10-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
409 | 409 | 2025-10-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
410 | 410 | 2025-10-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
411 | 411 | 2025-10-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
412 | 412 | 2025-10-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
413 | 413 | 2025-10-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
414 | 414 | 2025-11-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 40 | ahmed saaed
415 | 415 | 2025-11-01 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 3 | ahmed saaed
416 | 416 | 2025-11-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
417 | 417 | 2025-11-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 40 | ahmed saaed
418 | 418 | 2025-11-02 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 3 | ahmed saaed
419 | 419 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
420 | 420 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 40 | ahmed saaed
421 | 421 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | ahmed saaed
422 | 422 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | ahmed saaed
423 | 423 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
424 | 424 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
425 | 425 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
426 | 426 | 2025-11-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
427 | 427 | 2025-11-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
428 | 428 | 2025-11-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
429 | 429 | 2025-11-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
430 | 430 | 2025-11-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 5 | ahmed saaed
431 | 431 | 2025-11-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 2 | ahmed saaed
432 | 432 | 2025-11-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
433 | 433 | 2025-11-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
434 | 434 | 2025-11-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 80 | ahmed saaed
435 | 435 | 2025-11-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
436 | 436 | 2025-11-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
437 | 437 | 2025-11-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
438 | 438 | 2025-11-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 60 | ahmed saaed
439 | 439 | 2025-11-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | ahmed saaed
440 | 440 | 2025-11-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
441 | 441 | 2025-11-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
442 | 442 | 2025-11-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 70 | ahmed saaed
443 | 443 | 2025-11-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
444 | 444 | 2025-11-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
445 | 445 | 2025-11-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
446 | 446 | 2025-11-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
447 | 447 | 2025-11-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | Taleb
448 | 448 | 2025-11-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | Taleb
449 | 449 | 2025-11-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Taleb
450 | 450 | 2025-11-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Taleb
451 | 451 | 2025-11-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 75 | Taleb
452 | 452 | 2025-11-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Taleb
453 | 453 | 2025-11-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | Taleb
454 | 454 | 2025-11-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 20 | Taleb
455 | 455 | 2025-11-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 115 | ahmed saaed
456 | 456 | 2025-11-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 30 | ahmed saaed
457 | 457 | 2025-11-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
458 | 458 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
459 | 459 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 35 | ahmed saaed
460 | 460 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | ahmed saaed
461 | 461 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
462 | 462 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 91UGG | 20 | ahmed saaed
463 | 463 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
464 | 464 | 2025-11-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 40 | ahmed saaed
465 | 465 | 2025-11-10 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 91UGG | 1 | ahmed saaed
466 | 466 | 2025-11-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
467 | 467 | 2025-11-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
468 | 468 | 2025-11-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
469 | 469 | 2025-11-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
470 | 470 | 2025-11-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | ahmed saaed
471 | 471 | 2025-11-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 40 | ahmed saaed
472 | 472 | 2025-11-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
473 | 473 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
474 | 474 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
475 | 475 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
476 | 476 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
477 | 477 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | ahmed saaed
478 | 478 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
479 | 479 | 2025-11-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 91UGG | 15 | ahmed saaed
480 | 480 | 2025-11-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 100 | Taleb
481 | 481 | 2025-11-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 75 | Taleb
482 | 482 | 2025-11-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Taleb
483 | 483 | 2025-11-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 200 | Taleb
484 | 484 | 2025-11-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | Taleb
485 | 485 | 2025-11-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 150 | Taleb
486 | 486 | 2025-11-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 100 | Taleb
487 | 487 | 2025-11-17 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UGB | 2 | Taleb
488 | 488 | 2025-11-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | Taleb
489 | 489 | 2025-11-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
490 | 490 | 2025-11-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 85 | Taleb
491 | 491 | 2025-11-18 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 3 | 30USJ | 1 | ahmed saaed
492 | 492 | 2025-11-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 50 | ahmed saaed
493 | 493 | 2025-11-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
494 | 494 | 2025-11-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 125 | ahmed saaed
495 | 495 | 2025-11-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
496 | 496 | 2025-11-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 100 | ahmed saaed
497 | 497 | 2025-11-19 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UGB | 2.5 | ahmed saaed
498 | 498 | 2025-11-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 125 | ahmed saaed
499 | 499 | 2025-11-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
500 | 500 | 2025-11-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | ahmed saaed
501 | 501 | 2025-11-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 100 | ahmed saaed
502 | 502 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
503 | 503 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | ahmed saaed
504 | 504 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
505 | 505 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 50 | ahmed saaed
506 | 506 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | ahmed saaed
507 | 507 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | ahmed saaed
508 | 508 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
509 | 509 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 75 | ahmed saaed
510 | 510 | 2025-11-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
511 | 511 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
512 | 512 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
513 | 513 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
514 | 514 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
515 | 515 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
516 | 516 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
517 | 517 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
518 | 518 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
519 | 519 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
520 | 520 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
521 | 521 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
522 | 522 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
523 | 523 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
524 | 524 | 2025-11-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
525 | 525 | 2025-11-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | Taleb
526 | 526 | 2025-11-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | Taleb
527 | 527 | 2025-11-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 40 | Taleb
528 | 528 | 2025-11-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
529 | 529 | 2025-11-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
530 | 530 | 2025-11-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
531 | 531 | 2025-11-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
532 | 532 | 2025-11-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
533 | 533 | 2025-11-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
534 | 534 | 2025-11-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
535 | 535 | 2025-11-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
536 | 536 | 2025-11-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
537 | 537 | 2025-11-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 20 | Taleb
538 | 538 | 2025-11-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 5 | Taleb
539 | 539 | 2025-11-24 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 1 | Taleb
540 | 540 | 2025-11-25 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 1 | 10UGB | 18 | SALAMA
541 | 541 | 2025-11-25 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UGB | 5 | SALAMA
542 | 542 | 2025-11-25 | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | 1 | 10UGB | 1 | SALAMA
543 | 543 | 2025-11-25 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 1 | 10UGB | 6 | SALAMA
544 | 544 | 2025-11-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 60 | Taleb
545 | 545 | 2025-11-25 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 3.5 | Taleb
546 | 546 | 2025-11-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | Taleb
547 | 547 | 2025-11-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | Taleb
548 | 548 | 2025-11-25 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UMA | 1 | Taleb
549 | 549 | 2025-11-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 60 | Taleb
550 | 550 | 2025-11-26 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 3 | Taleb
551 | 551 | 2025-11-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 15 | Taleb
552 | 552 | 2025-11-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | Taleb
553 | 553 | 2025-11-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
554 | 554 | 2025-11-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
555 | 555 | 2025-11-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | Taleb
556 | 556 | 2025-11-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
557 | 557 | 2025-11-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
558 | 558 | 2025-11-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
559 | 559 | 2025-11-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
560 | 560 | 2025-11-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
561 | 561 | 2025-11-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
562 | 562 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 125 | ahmed saaed
563 | 563 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
564 | 564 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | ahmed saaed
565 | 565 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 100 | ahmed saaed
566 | 566 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
567 | 567 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | ahmed saaed
568 | 568 | 2025-11-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
569 | 569 | 2025-11-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 50 | ahmed saaed
570 | 570 | 2025-11-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | ahmed saaed
571 | 571 | 2025-11-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | ahmed saaed
572 | 572 | 2025-11-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
573 | 573 | 2025-11-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 75 | ahmed saaed
574 | 574 | 2025-11-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
575 | 575 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
576 | 576 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
577 | 577 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
578 | 578 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
579 | 579 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
580 | 580 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
581 | 581 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
582 | 582 | 2025-11-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
583 | 583 | 2025-12-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
584 | 584 | 2025-12-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
585 | 585 | 2025-12-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
586 | 586 | 2025-12-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
587 | 587 | 2025-12-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
588 | 588 | 2025-12-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
589 | 589 | 2025-12-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
590 | 590 | 2025-12-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
591 | 591 | 2025-12-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
592 | 592 | 2025-12-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
593 | 593 | 2025-12-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
594 | 594 | 2025-12-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
595 | 595 | 2025-12-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
596 | 596 | 2025-12-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
597 | 597 | 2025-12-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
598 | 598 | 2025-12-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
599 | 599 | 2025-12-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
600 | 600 | 2025-12-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
601 | 601 | 2025-12-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
602 | 602 | 2025-12-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
603 | 603 | 2025-12-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
604 | 604 | 2025-12-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
605 | 605 | 2025-12-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
606 | 606 | 2025-12-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
607 | 607 | 2025-12-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
608 | 608 | 2025-12-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
609 | 609 | 2025-12-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
610 | 610 | 2025-12-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
611 | 611 | 2025-12-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
612 | 612 | 2025-12-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 20 | Taleb
613 | 613 | 2025-12-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 5 | Taleb
614 | 614 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 15 | Taleb
615 | 615 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | Taleb
616 | 616 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
617 | 617 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
618 | 618 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | Taleb
619 | 619 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
620 | 620 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
621 | 621 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
622 | 622 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
623 | 623 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
624 | 624 | 2025-12-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
625 | 625 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 125 | Taleb
626 | 626 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
627 | 627 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | Taleb
628 | 628 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 100 | Taleb
629 | 629 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | Taleb
630 | 630 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | Taleb
631 | 631 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | Taleb
632 | 632 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 50 | Taleb
633 | 633 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | Taleb
634 | 634 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | Taleb
635 | 635 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
636 | 636 | 2025-12-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 75 | Taleb
637 | 637 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | Taleb
638 | 638 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
639 | 639 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
640 | 640 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
641 | 641 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
642 | 642 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
643 | 643 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
644 | 644 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
645 | 645 | 2025-12-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
646 | 646 | 2025-12-09 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 1 | 10UMA | 2 | SALAMA
647 | 647 | 2025-12-09 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UMA | 14 | SALAMA
648 | 648 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
649 | 649 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
650 | 650 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
651 | 651 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | Taleb
652 | 652 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Taleb
653 | 653 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Taleb
654 | 654 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | Taleb
655 | 655 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | Taleb
656 | 656 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | Taleb
657 | 657 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
658 | 658 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | Taleb
659 | 659 | 2025-12-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | Taleb
660 | 660 | 2025-12-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
661 | 661 | 2025-12-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
662 | 662 | 2025-12-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
663 | 663 | 2025-12-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
664 | 664 | 2025-12-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
665 | 665 | 2025-12-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
666 | 666 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 125 | ahmed saaed
667 | 667 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
668 | 668 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | ahmed saaed
669 | 669 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 100 | ahmed saaed
670 | 670 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
671 | 671 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | ahmed saaed
672 | 672 | 2025-12-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
673 | 673 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 50 | ahmed saaed
674 | 674 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | ahmed saaed
675 | 675 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | ahmed saaed
676 | 676 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
677 | 677 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 75 | ahmed saaed
678 | 678 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
679 | 679 | 2025-12-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
680 | 680 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
681 | 681 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
682 | 682 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
683 | 683 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
684 | 684 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
685 | 685 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
686 | 686 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
687 | 687 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
688 | 688 | 2025-12-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
689 | 689 | 2025-12-15 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 4 | 40UMA | 31.5 | Taleb
690 | 690 | 2025-12-15 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 4 | 40UMA | 10 | Taleb
691 | 691 | 2025-12-15 | GR007 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 4 | 40UMA | 2 | Taleb
692 | 692 | 2025-12-15 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 4 | 40UMA | 29 | ahmed saaed
693 | 693 | 2025-12-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
694 | 694 | 2025-12-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
695 | 695 | 2025-12-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
696 | 696 | 2025-12-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
697 | 697 | 2025-12-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
698 | 698 | 2025-12-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
699 | 699 | 2025-12-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
700 | 700 | 2025-12-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
701 | 701 | 2025-12-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
702 | 702 | 2025-12-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
703 | 703 | 2025-12-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
704 | 704 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
705 | 705 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
706 | 706 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
707 | 707 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
708 | 708 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
709 | 709 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
710 | 710 | 2025-12-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
711 | 711 | 2025-12-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
712 | 712 | 2025-12-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
713 | 713 | 2025-12-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
714 | 714 | 2025-12-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
715 | 715 | 2025-12-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
716 | 716 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
717 | 717 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
718 | 718 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
719 | 719 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
720 | 720 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
721 | 721 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
722 | 722 | 2025-12-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
723 | 723 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | ahmed saaed
724 | 724 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
725 | 725 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
726 | 726 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
727 | 727 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
728 | 728 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
729 | 729 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
730 | 730 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
731 | 731 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 5 | ahmed saaed
732 | 732 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 2 | ahmed saaed
733 | 733 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
734 | 734 | 2025-12-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
735 | 735 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 80 | ahmed saaed
736 | 736 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
737 | 737 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
738 | 738 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
739 | 739 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 60 | ahmed saaed
740 | 740 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | ahmed saaed
741 | 741 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
742 | 742 | 2025-12-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
743 | 743 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 70 | ahmed saaed
744 | 744 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
745 | 745 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
746 | 746 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
747 | 747 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
748 | 748 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | Taleb
749 | 749 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | Taleb
750 | 750 | 2025-12-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Taleb
751 | 751 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Taleb
752 | 752 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 75 | Taleb
753 | 753 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Taleb
754 | 754 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | Taleb
755 | 755 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 20 | Taleb
756 | 756 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 115 | ahmed saaed
757 | 757 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 30 | ahmed saaed
758 | 758 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
759 | 759 | 2025-12-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
760 | 760 | 2025-12-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 35 | ahmed saaed
761 | 761 | 2025-12-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | ahmed saaed
762 | 762 | 2025-12-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
763 | 763 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
764 | 764 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
765 | 765 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
766 | 766 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
767 | 767 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
768 | 768 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
769 | 769 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
770 | 770 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
771 | 771 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
772 | 772 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
773 | 773 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
774 | 774 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
775 | 775 | 2025-12-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
776 | 776 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
777 | 777 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
778 | 778 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
779 | 779 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
780 | 780 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
781 | 781 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
782 | 782 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
783 | 783 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
784 | 784 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
785 | 785 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
786 | 786 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
787 | 787 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
788 | 788 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
789 | 789 | 2025-12-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
790 | 790 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
791 | 791 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
792 | 792 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
793 | 793 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | ahmed saaed
794 | 794 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
795 | 795 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | Taleb
796 | 796 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
797 | 797 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
798 | 798 | 2025-12-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
799 | 799 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
800 | 800 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
801 | 801 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
802 | 802 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
803 | 803 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
804 | 804 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
805 | 805 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
806 | 806 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
807 | 807 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
808 | 808 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
809 | 809 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
810 | 810 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
811 | 811 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
812 | 812 | 2025-12-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
813 | 813 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
814 | 814 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
815 | 815 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
816 | 816 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
817 | 817 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
818 | 818 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
819 | 819 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
820 | 820 | 2025-12-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 20 | Taleb
821 | 821 | 2025-12-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 5 | Taleb
822 | 822 | 2025-12-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 15 | Taleb
823 | 823 | 2025-12-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | Taleb
824 | 824 | 2025-12-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
825 | 825 | 2025-12-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
826 | 826 | 2026-01-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | Taleb
827 | 827 | 2026-01-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
828 | 828 | 2026-01-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
829 | 829 | 2026-01-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
830 | 830 | 2026-01-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
831 | 831 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
832 | 832 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
833 | 833 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
834 | 834 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
835 | 835 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
836 | 836 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | Taleb
837 | 837 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
838 | 838 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Taleb
839 | 839 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
840 | 840 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
841 | 841 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Taleb
842 | 842 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
843 | 843 | 2026-01-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
844 | 844 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 5 | Taleb
845 | 845 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 2 | Taleb
846 | 846 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
847 | 847 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Taleb
848 | 848 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 80 | Taleb
849 | 849 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
850 | 850 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
851 | 851 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
852 | 852 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 60 | ahmed saaed
853 | 853 | 2026-01-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 55 | ahmed saaed
854 | 854 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
855 | 855 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
856 | 856 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
857 | 857 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | ahmed saaed
858 | 858 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
859 | 859 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
860 | 860 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
861 | 861 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
862 | 862 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
863 | 863 | 2026-01-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
864 | 864 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
865 | 865 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UFT | 30 | ahmed saaed
866 | 866 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
867 | 867 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
868 | 868 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
869 | 869 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
870 | 870 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
871 | 871 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
872 | 872 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
873 | 873 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
874 | 874 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
875 | 875 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
876 | 876 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
877 | 877 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
878 | 878 | 2026-01-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
879 | 879 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
880 | 880 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
881 | 881 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
882 | 882 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
883 | 883 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
884 | 884 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | ahmed saaed
885 | 885 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
886 | 886 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
887 | 887 | 2026-01-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
888 | 888 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 20 | ahmed saaed
889 | 889 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 115 | ahmed saaed
890 | 890 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 30 | ahmed saaed
891 | 891 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
892 | 892 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
893 | 893 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 35 | ahmed saaed
894 | 894 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | ahmed saaed
895 | 895 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
896 | 896 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 20 | ahmed saaed
897 | 897 | 2026-01-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
898 | 898 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 40 | ahmed saaed
899 | 899 | 2026-01-08 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 5 | ahmed saaed
900 | 900 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
901 | 901 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
902 | 902 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
903 | 903 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
904 | 904 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | ahmed saaed
905 | 905 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 40 | ahmed saaed
906 | 906 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
907 | 907 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
908 | 908 | 2026-01-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 125 | ahmed saaed
909 | 909 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 125 | ahmed saaed
910 | 910 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
911 | 911 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | ahmed saaed
912 | 912 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
913 | 913 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 15 | ahmed saaed
914 | 914 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 100 | ahmed saaed
915 | 915 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 75 | ahmed saaed
916 | 916 | 2026-01-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
917 | 917 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
918 | 918 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 75 | ahmed saaed
919 | 919 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 150 | ahmed saaed
920 | 920 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 100 | ahmed saaed
921 | 921 | 2026-01-10 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UGB | 5 | ahmed saaed
922 | 922 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
923 | 923 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | ahmed saaed
924 | 924 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 85 | ahmed saaed
925 | 925 | 2026-01-10 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 3 | 30USJ | 5 | ahmed saaed
926 | 926 | 2026-01-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 50 | ahmed saaed
927 | 927 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
928 | 928 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
929 | 929 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
930 | 930 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
931 | 931 | 2026-01-11 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 1 | 10UGB | 15 | ahmed saaed
932 | 932 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
933 | 933 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
934 | 934 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 15 | ahmed saaed
935 | 935 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
936 | 936 | 2026-01-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
937 | 937 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | ahmed saaed
938 | 938 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
939 | 939 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
940 | 940 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
941 | 941 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
942 | 942 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
943 | 943 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
944 | 944 | 2026-01-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
945 | 945 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
946 | 946 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
947 | 947 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
948 | 948 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
949 | 949 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
950 | 950 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
951 | 951 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
952 | 952 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
953 | 953 | 2026-01-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
954 | 954 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
955 | 955 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
956 | 956 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | ahmed saaed
957 | 957 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 25 | ahmed saaed
958 | 958 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
959 | 959 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
960 | 960 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
961 | 961 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
962 | 962 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
963 | 963 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
964 | 964 | 2026-01-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
965 | 965 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
966 | 966 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
967 | 967 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UFT | 30 | ahmed saaed
968 | 968 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
969 | 969 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
970 | 970 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
971 | 971 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
972 | 972 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | Taleb
973 | 973 | 2026-01-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | Taleb
974 | 974 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
975 | 975 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 100 | Taleb
976 | 976 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
977 | 977 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
978 | 978 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
979 | 979 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
980 | 980 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
981 | 981 | 2026-01-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
982 | 982 | 2026-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
983 | 983 | 2026-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
984 | 984 | 2026-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
985 | 985 | 2026-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
986 | 986 | 2026-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | ahmed saaed
987 | 987 | 2026-01-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
988 | 988 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
989 | 989 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
990 | 990 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 20 | ahmed saaed
991 | 991 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 115 | ahmed saaed
992 | 992 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 30 | ahmed saaed
993 | 993 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
994 | 994 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
995 | 995 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 35 | ahmed saaed
996 | 996 | 2026-01-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 115 | ahmed saaed
997 | 997 | 2026-01-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
998 | 998 | 2026-01-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UGG | 20 | ahmed saaed
999 | 999 | 2026-01-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1000 | 1000 | 2026-01-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30USJ | 40 | ahmed saaed
1001 | 1001 | 2026-01-19 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | C | 90UGG | 5 | ahmed saaed
1002 | 1002 | 2026-01-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 75 | ahmed saaed
1003 | 1003 | 2026-01-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1004 | 1004 | 2026-01-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1005 | 1005 | 2026-01-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1006 | 1006 | 2026-01-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 105 | ahmed saaed
1007 | 1007 | 2026-01-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 40 | ahmed saaed
1008 | 1008 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | ahmed saaed
1009 | 1009 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1010 | 1010 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1011 | 1011 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1012 | 1012 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1013 | 1013 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1014 | 1014 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1015 | 1015 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1016 | 1016 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
1017 | 1017 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1018 | 1018 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1019 | 1019 | 2026-01-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1020 | 1020 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1021 | 1021 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1022 | 1022 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1023 | 1023 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1024 | 1024 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1025 | 1025 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1026 | 1026 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1027 | 1027 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1028 | 1028 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1029 | 1029 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1030 | 1030 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1031 | 1031 | 2026-01-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1032 | 1032 | 2026-01-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1033 | 1033 | 2026-01-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1034 | 1034 | 2026-01-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1035 | 1035 | 2026-01-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1036 | 1036 | 2026-01-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1037 | 1037 | 2026-01-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1038 | 1038 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1039 | 1039 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
1040 | 1040 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1041 | 1041 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1042 | 1042 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1043 | 1043 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1044 | 1044 | 2026-01-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1045 | 1045 | 2026-01-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1046 | 1046 | 2026-01-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1047 | 1047 | 2026-01-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1048 | 1048 | 2026-01-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1049 | 1049 | 2026-01-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1050 | 1050 | 2026-01-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1051 | 1051 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1052 | 1052 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1053 | 1053 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1054 | 1054 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1055 | 1055 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1056 | 1056 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1057 | 1057 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1058 | 1058 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1059 | 1059 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1060 | 1060 | 2026-01-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1061 | 1061 | 2026-01-26 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 1 | 10UGB | 55 | Salama
1062 | 1062 | 2026-01-26 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 4 | 40UMA | 30 | Salama
1063 | 1063 | 2026-01-26 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 4 | 40UMA | 10 | Salama
1064 | 1064 | 2026-01-26 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 4 | 40UMA | 12 | Salama
1065 | 1065 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1066 | 1066 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1067 | 1067 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1068 | 1068 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1069 | 1069 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1070 | 1070 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1071 | 1071 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1072 | 1072 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1073 | 1073 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1074 | 1074 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1075 | 1075 | 2026-01-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1076 | 1076 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1077 | 1077 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1078 | 1078 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1079 | 1079 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1080 | 1080 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1081 | 1081 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1082 | 1082 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1083 | 1083 | 2026-01-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | W |  | 500 | ahmed saaed | Fabrication
1084 | 1084 | 2026-01-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | NASR
1085 | 1085 | 2026-01-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 30 | NASR
1086 | 1086 | 2026-01-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1087 | 1087 | 2026-01-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | NASR
1088 | 1088 | 2026-01-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | NASR
1089 | 1089 | 2026-01-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | NASR
1090 | 1090 | 2026-01-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | NASR
1091 | 1091 | 2026-01-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | NASR
1092 | 1092 | 2026-01-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | NASR
1093 | 1093 | 2026-01-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1094 | 1094 | 2026-01-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1095 | 1095 | 2026-01-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | NASR
1096 | 1096 | 2026-01-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | NASR
1097 | 1097 | 2026-01-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | NASR
1098 | 1098 | 2026-02-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | NASR
1099 | 1099 | 2026-02-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | NASR
1100 | 1100 | 2026-02-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | NASR
1101 | 1101 | 2026-02-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | NASR
1102 | 1102 | 2026-02-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | NASR
1103 | 1103 | 2026-02-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | NASR
1104 | 1104 | 2026-02-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | NASR
1105 | 1105 | 2026-02-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | NASR
1106 | 1106 | 2026-02-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | NASR
1107 | 1107 | 2026-02-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | NASR
1108 | 1108 | 2026-02-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1109 | 1109 | 2026-02-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | NASR
1110 | 1110 | 2026-02-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | NASR
1111 | 1111 | 2026-02-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | NASR
1112 | 1112 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1113 | 1113 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1114 | 1114 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1115 | 1115 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1116 | 1116 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1117 | 1117 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1118 | 1118 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 65 | ahmed saaed
1119 | 1119 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1120 | 1120 | 2026-02-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1121 | 1121 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1122 | 1122 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1123 | 1123 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1124 | 1124 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1125 | 1125 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1126 | 1126 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1127 | 1127 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1128 | 1128 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1129 | 1129 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1130 | 1130 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1131 | 1131 | 2026-02-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1132 | 1132 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1133 | 1133 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1134 | 1134 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1135 | 1135 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1136 | 1136 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1137 | 1137 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1138 | 1138 | 2026-02-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1139 | 1139 | 2026-02-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1140 | 1140 | 2026-02-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1141 | 1141 | 2026-02-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1142 | 1142 | 2026-02-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1143 | 1143 | 2026-02-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1144 | 1144 | 2026-02-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1145 | 1145 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1146 | 1146 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1147 | 1147 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1148 | 1148 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1149 | 1149 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1150 | 1150 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1151 | 1151 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1152 | 1152 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1153 | 1153 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1154 | 1154 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1155 | 1155 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1156 | 1156 | 2026-02-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1157 | 1157 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1158 | 1158 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | W |  | 500 | ahmed saaed
1159 | 1159 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 30 | NASR
1160 | 1160 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 30 | NASR
1161 | 1161 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1162 | 1162 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | NASR
1163 | 1163 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | NASR
1164 | 1164 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | NASR
1165 | 1165 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | NASR
1166 | 1166 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | NASR
1167 | 1167 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | NASR
1168 | 1168 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1169 | 1169 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1170 | 1170 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | NASR
1171 | 1171 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | NASR
1172 | 1172 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | NASR
1173 | 1173 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | NASR
1174 | 1174 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | NASR
1175 | 1175 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | NASR
1176 | 1176 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | NASR
1177 | 1177 | 2026-02-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | NASR
1178 | 1178 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | NASR
1179 | 1179 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | NASR
1180 | 1180 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | NASR
1181 | 1181 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | NASR
1182 | 1182 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | NASR
1183 | 1183 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | NASR
1184 | 1184 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | NASR
1185 | 1185 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | NASR
1186 | 1186 | 2026-02-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | NASR
1187 | 1187 | 2026-02-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1188 | 1188 | 2026-02-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 30 | ahmed saaed
1189 | 1189 | 2026-02-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 75 | ahmed saaed
1190 | 1190 | 2026-02-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 25 | ahmed saaed
1191 | 1191 | 2026-02-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1192 | 1192 | 2026-02-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1193 | 1193 | 2026-02-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 75 | ahmed saaed
1194 | 1194 | 2026-02-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1195 | 1195 | 2026-02-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
1196 | 1196 | 2026-02-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1197 | 1197 | 2026-02-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1198 | 1198 | 2026-02-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1199 | 1199 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1200 | 1200 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1201 | 1201 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1202 | 1202 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1203 | 1203 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1204 | 1204 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1205 | 1205 | 2026-02-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1206 | 1206 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1207 | 1207 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1208 | 1208 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | ahmed saaed
1209 | 1209 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1210 | 1210 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1211 | 1211 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1212 | 1212 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1213 | 1213 | 2026-02-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1214 | 1214 | 2026-02-16 | GR002 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 1 | 10UGB | 14 | Salama
1215 | 1215 | 2026-02-16 | GR013 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 1 | 10UGB | 13 | Salama
1216 | 1216 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
1217 | 1217 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 65 | ahmed saaed
1218 | 1218 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1219 | 1219 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1220 | 1220 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | ahmed saaed
1221 | 1221 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 40 | ahmed saaed
1222 | 1222 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1223 | 1223 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1224 | 1224 | 2026-02-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 20 | ahmed saaed
1225 | 1225 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 25 | ahmed saaed
1226 | 1226 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1227 | 1227 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1228 | 1228 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1229 | 1229 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1230 | 1230 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1231 | 1231 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1232 | 1232 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1233 | 1233 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1234 | 1234 | 2026-02-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1235 | 1235 | 2026-02-19 | GR008 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | C |  | 1 | Salama
1236 | 1236 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1237 | 1237 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 75 | ahmed saaed
1238 | 1238 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1239 | 1239 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
1240 | 1240 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1241 | 1241 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1242 | 1242 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1243 | 1243 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1244 | 1244 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1245 | 1245 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1246 | 1246 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1247 | 1247 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1248 | 1248 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1249 | 1249 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1250 | 1250 | 2026-02-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1251 | 1251 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1252 | 1252 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1253 | 1253 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | ahmed saaed
1254 | 1254 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1255 | 1255 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1256 | 1256 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1257 | 1257 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1258 | 1258 | 2026-02-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1259 | 1259 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1260 | 1260 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1261 | 1261 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1262 | 1262 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1263 | 1263 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1264 | 1264 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1265 | 1265 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1266 | 1266 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1267 | 1267 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1268 | 1268 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1269 | 1269 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1270 | 1270 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1271 | 1271 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1272 | 1272 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1273 | 1273 | 2026-02-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1274 | 1274 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1275 | 1275 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | ahmed saaed
1276 | 1276 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1277 | 1277 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1278 | 1278 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1279 | 1279 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1280 | 1280 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
1281 | 1281 | 2026-02-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1282 | 1282 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1283 | 1283 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1284 | 1284 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1285 | 1285 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1286 | 1286 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | ahmed saaed
1287 | 1287 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1288 | 1288 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1289 | 1289 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1290 | 1290 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1291 | 1291 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
1292 | 1292 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1293 | 1293 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1294 | 1294 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1295 | 1295 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1296 | 1296 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | ahmed saaed
1297 | 1297 | 2026-02-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1298 | 1298 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1299 | 1299 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1300 | 1300 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1301 | 1301 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1302 | 1302 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1303 | 1303 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1304 | 1304 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1305 | 1305 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1306 | 1306 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1307 | 1307 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1308 | 1308 | 2026-02-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1309 | 1309 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1310 | 1310 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1311 | 1311 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1312 | 1312 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1313 | 1313 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1314 | 1314 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1315 | 1315 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1316 | 1316 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1317 | 1317 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1318 | 1318 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1319 | 1319 | 2026-02-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1320 | 1320 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | ahmed saaed
1321 | 1321 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | ahmed saaed
1322 | 1322 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1323 | 1323 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1324 | 1324 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1325 | 1325 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1326 | 1326 | 2026-02-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1327 | 1327 | 2026-02-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | Taleb
1328 | 1328 | 2026-02-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | Taleb
1329 | 1329 | 2026-02-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
1330 | 1330 | 2026-02-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Taleb
1331 | 1331 | 2026-02-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
1332 | 1332 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 50 | Taleb
1333 | 1333 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
1334 | 1334 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | Taleb
1335 | 1335 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
1336 | 1336 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
1337 | 1337 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
1338 | 1338 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
1339 | 1339 | 2026-02-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Taleb
1340 | 1340 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1341 | 1341 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1342 | 1342 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1343 | 1343 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1344 | 1344 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1345 | 1345 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1346 | 1346 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1347 | 1347 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1348 | 1348 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1349 | 1349 | 2026-03-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1350 | 1350 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1351 | 1351 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1352 | 1352 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1353 | 1353 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1354 | 1354 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1355 | 1355 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1356 | 1356 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1357 | 1357 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1358 | 1358 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1359 | 1359 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1360 | 1360 | 2026-03-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1361 | 1361 | 2026-03-03 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 4 | 40UMa | 6 | Salama
1362 | 1362 | 2026-03-03 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 4 | 40UMa | 4 | Salama
1363 | 1363 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1364 | 1364 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1365 | 1365 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1366 | 1366 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1367 | 1367 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1368 | 1368 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1369 | 1369 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1370 | 1370 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1371 | 1371 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | ahmed saaed
1372 | 1372 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1373 | 1373 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1374 | 1374 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1375 | 1375 | 2026-03-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1376 | 1376 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1377 | 1377 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1378 | 1378 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1379 | 1379 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1380 | 1380 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1381 | 1381 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1382 | 1382 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1383 | 1383 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1384 | 1384 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1385 | 1385 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1386 | 1386 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1387 | 1387 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1388 | 1388 | 2026-03-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1389 | 1389 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Taleb
1390 | 1390 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 50 | Taleb
1391 | 1391 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
1392 | 1392 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 30 | Taleb
1393 | 1393 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | Taleb
1394 | 1394 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Taleb
1395 | 1395 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | Taleb
1396 | 1396 | 2026-03-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Taleb
1397 | 1397 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Taleb
1398 | 1398 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 40 | Taleb
1399 | 1399 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Taleb
1400 | 1400 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Taleb
1401 | 1401 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | Taleb
1402 | 1402 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
1403 | 1403 | 2026-03-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
1404 | 1404 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1405 | 1405 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1406 | 1406 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1407 | 1407 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1408 | 1408 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1409 | 1409 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1410 | 1410 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1411 | 1411 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1412 | 1412 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1413 | 1413 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1414 | 1414 | 2026-03-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1415 | 1415 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 75 | ahmed saaed
1416 | 1416 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMa | 50 | ahmed saaed
1417 | 1417 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMa | 20 | ahmed saaed
1418 | 1418 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1419 | 1419 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | ahmed saaed
1420 | 1420 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1421 | 1421 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1422 | 1422 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1423 | 1423 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1424 | 1424 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1425 | 1425 | 2026-03-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 15 | ahmed saaed
1426 | 1426 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
1427 | 1427 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1428 | 1428 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1429 | 1429 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1430 | 1430 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1431 | 1431 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1432 | 1432 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | ahmed saaed
1433 | 1433 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | ahmed saaed
1434 | 1434 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 50 | ahmed saaed
1435 | 1435 | 2026-03-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1436 | 1436 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | ahmed saaed
1437 | 1437 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1438 | 1438 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1439 | 1439 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 40 | ahmed saaed
1440 | 1440 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1441 | 1441 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1442 | 1442 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1443 | 1443 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1444 | 1444 | 2026-03-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | W | workshop | 1140 | ahmed saaed | fabrication
1445 | 1445 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1446 | 1446 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1447 | 1447 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1448 | 1448 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1449 | 1449 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1450 | 1450 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1451 | 1451 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1452 | 1452 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1453 | 1453 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | ahmed saaed
1454 | 1454 | 2026-03-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1455 | 1455 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1456 | 1456 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1457 | 1457 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1458 | 1458 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1459 | 1459 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1460 | 1460 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1461 | 1461 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1462 | 1462 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1463 | 1463 | 2026-03-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1464 | 1464 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1465 | 1465 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1466 | 1466 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1467 | 1467 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1468 | 1468 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1469 | 1469 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1470 | 1470 | 2026-03-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1471 | 1471 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1472 | 1472 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 70 | ahmed saaed
1473 | 1473 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1474 | 1474 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1475 | 1475 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 40 | ahmed saaed
1476 | 1476 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1477 | 1477 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1478 | 1478 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1479 | 1479 | 2026-03-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1480 | 1480 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
1481 | 1481 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
1482 | 1482 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1483 | 1483 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1484 | 1484 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1485 | 1485 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1486 | 1486 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1487 | 1487 | 2026-03-15 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 2 | 20UMA | 6 | ahmed saaed
1488 | 1488 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 25 | ahmed saaed
1489 | 1489 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1490 | 1490 | 2026-03-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1491 | 1491 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMa | 50 | ahmed saaed
1492 | 1492 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMa | 20 | ahmed saaed
1493 | 1493 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1494 | 1494 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 50 | ahmed saaed
1495 | 1495 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1496 | 1496 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1497 | 1497 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1498 | 1498 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1499 | 1499 | 2026-03-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1500 | 1500 | 2026-03-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 15 | ahmed saaed
1501 | 1501 | 2026-03-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
1502 | 1502 | 2026-03-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1503 | 1503 | 2026-03-17 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 3 | 30UMA | 4 | Salama
1504 | 1504 | 2026-03-17 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UMA | 2 | Salama
1505 | 1505 | 2026-03-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1506 | 1506 | 2026-03-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1507 | 1507 | 2026-03-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1508 | 1508 | 2026-03-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1509 | 1509 | 2026-03-18 | CG002 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 2 | 20UMA | 6 | ahmed saaed
1510 | 1510 | 2026-03-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1511 | 1511 | 2026-03-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1512 | 1512 | 2026-03-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1513 | 1513 | 2026-03-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1514 | 1514 | 2026-03-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1515 | 1515 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1516 | 1516 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1517 | 1517 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1518 | 1518 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1519 | 1519 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1520 | 1520 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1521 | 1521 | 2026-03-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1522 | 1522 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1523 | 1523 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1524 | 1524 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1525 | 1525 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 25 | ahmed saaed
1526 | 1526 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1527 | 1527 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1528 | 1528 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1529 | 1529 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1530 | 1530 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1531 | 1531 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1532 | 1532 | 2026-03-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1533 | 1533 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1534 | 1534 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1535 | 1535 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1536 | 1536 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
1537 | 1537 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
1538 | 1538 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Taleb
1539 | 1539 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 30 | Taleb
1540 | 1540 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Taleb
1541 | 1541 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Taleb
1542 | 1542 | 2026-03-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Taleb
1543 | 1543 | 2026-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Taleb
1544 | 1544 | 2026-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Taleb
1545 | 1545 | 2026-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Taleb
1546 | 1546 | 2026-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | Taleb
1547 | 1547 | 2026-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Taleb
1548 | 1548 | 2026-03-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Taleb
1549 | 1549 | 2026-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1550 | 1550 | 2026-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1551 | 1551 | 2026-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1552 | 1552 | 2026-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1553 | 1553 | 2026-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1554 | 1554 | 2026-03-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1555 | 1555 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMa | 20 | ahmed saaed
1556 | 1556 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1557 | 1557 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1558 | 1558 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1559 | 1559 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1560 | 1560 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1561 | 1561 | 2026-03-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1562 | 1562 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1563 | 1563 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 15 | ahmed saaed
1564 | 1564 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
1565 | 1565 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1566 | 1566 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1567 | 1567 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1568 | 1568 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1569 | 1569 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1570 | 1570 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | ahmed saaed
1571 | 1571 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | ahmed saaed
1572 | 1572 | 2026-03-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1573 | 1573 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1574 | 1574 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1575 | 1575 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1576 | 1576 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1577 | 1577 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1578 | 1578 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1579 | 1579 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1580 | 1580 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1581 | 1581 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1582 | 1582 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | W | workshop | 500 | ahmed saaed
1583 | 1583 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1584 | 1584 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1585 | 1585 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1586 | 1586 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1587 | 1587 | 2026-03-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1588 | 1588 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1589 | 1589 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1590 | 1590 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1591 | 1591 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1592 | 1592 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1593 | 1593 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1594 | 1594 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1595 | 1595 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1596 | 1596 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1597 | 1597 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1598 | 1598 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1599 | 1599 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1600 | 1600 | 2026-03-31 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1601 | 1601 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1602 | 1602 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1603 | 1603 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1604 | 1604 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1605 | 1605 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1606 | 1606 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1607 | 1607 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMa | 20 | ahmed saaed
1608 | 1608 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1609 | 1609 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1610 | 1610 | 2026-04-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1611 | 1611 | 2026-04-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1612 | 1612 | 2026-04-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1613 | 1613 | 2026-04-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | ahmed saaed
1614 | 1614 | 2026-04-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1615 | 1615 | 2026-04-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 15 | ahmed saaed
1616 | 1616 | 2026-04-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | ahmed saaed
1617 | 1617 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | ahmed saaed
1618 | 1618 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1619 | 1619 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1620 | 1620 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1621 | 1621 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1622 | 1622 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | ahmed saaed
1623 | 1623 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | ahmed saaed
1624 | 1624 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1625 | 1625 | 2026-04-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1626 | 1626 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1627 | 1627 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1628 | 1628 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1629 | 1629 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1630 | 1630 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1631 | 1631 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1632 | 1632 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | ahmed saaed
1633 | 1633 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1634 | 1634 | 2026-04-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1635 | 1635 | 2026-04-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | ahmed saaed
1636 | 1636 | 2026-04-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1637 | 1637 | 2026-04-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1638 | 1638 | 2026-04-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1639 | 1639 | 2026-04-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1640 | 1640 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1641 | 1641 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1642 | 1642 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1643 | 1643 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1644 | 1644 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 15 | ahmed saaed
1645 | 1645 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1646 | 1646 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1647 | 1647 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1648 | 1648 | 2026-04-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1649 | 1649 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1650 | 1650 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1651 | 1651 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 15 | ahmed saaed
1652 | 1652 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1653 | 1653 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1654 | 1654 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1655 | 1655 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1656 | 1656 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1657 | 1657 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1658 | 1658 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1659 | 1659 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1660 | 1660 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1661 | 1661 | 2026-04-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1662 | 1662 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1663 | 1663 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 15 | ahmed saaed
1664 | 1664 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1665 | 1665 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1666 | 1666 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | ahmed saaed
1667 | 1667 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | ahmed saaed
1668 | 1668 | 2026-04-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1669 | 1669 | 2026-04-08 | CG003 | Plate | Carbon Plate 1000x6000x8 | CCGG | 1000x6000x8 | PCS |  |  | 0.8
1670 | 1670 | 2026-04-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | ahmed saaed
1671 | 1671 | 2026-04-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1672 | 1672 | 2026-04-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | ahmed saaed
1673 | 1673 | 2026-04-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1674 | 1674 | 2026-04-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | ahmed saaed
1675 | 1675 | 2026-04-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1676 | 1676 | 2026-04-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | ahmed saaed
1677 | 1677 | 2026-04-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | ahmed saaed
1678 | 1678 | 2026-04-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | ahmed saaed
1679 | 1679 | 2026-04-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | ahmed saaed
1680 | 1680 | 2026-04-11 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 1 | 10UMA | 66 | SALAMA
1681 | 1681 | 2026-04-11 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UMA | 6 | SALAMA
1682 | 1682 | 2026-04-11 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 1 | 10UMA | 1 | SALAMA
1683 | 1683 | 2026-04-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | ahmed saaed
1684 | 1684 | 2026-04-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1685 | 1685 | 2026-04-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | ahmed saaed
1686 | 1686 | 2026-04-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1687 | 1687 | 2026-04-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | ahmed saaed
1688 | 1688 | 2026-04-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | ahmed saaed
1689 | 1689 | 2026-04-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1690 | 1690 | 2026-04-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1691 | 1691 | 2026-04-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1692 | 1692 | 2026-04-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1693 | 1693 | 2026-04-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1694 | 1694 | 2026-04-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1695 | 1695 | 2026-04-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1696 | 1696 | 2026-04-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1697 | 1697 | 2026-04-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | ahmed saaed
1698 | 1698 | 2026-04-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | ahmed saaed
1699 | 1699 | 2026-04-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | ahmed saaed
1700 | 1700 | 2026-04-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | ahmed saaed
1701 | 1701 | 2026-04-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | ahmed saaed
1702 | 1702 | 2026-04-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | ahmed saaed
1703 | 1703 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | ahmed saaed
1704 | 1704 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | ahmed saaed
1705 | 1705 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | ahmed saaed
1706 | 1706 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1707 | 1707 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | ahmed saaed
1708 | 1708 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | ahmed saaed
1709 | 1709 | 2026-04-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | ahmed saaed
1710 | 1710 | 2026-04-15 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 1 | 10UMA | 20 | SALAMA
1711 | 1711 | 2026-04-15 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UMA | 4 | SALAMA
1712 | 1712 | 2026-04-16 | CO001 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M |  |  | 504 |  | fabrication
1713 | 1713 | 2026-04-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1714 | 1714 | 2026-04-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1715 | 1715 | 2026-04-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | Nasr
1716 | 1716 | 2026-04-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1717 | 1717 | 2026-04-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1718 | 1718 | 2026-04-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1719 | 1719 | 2026-04-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1720 | 1720 | 2026-04-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | Nasr
1721 | 1721 | 2026-04-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Nasr
1722 | 1722 | 2026-04-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | Nasr
1723 | 1723 | 2026-04-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Nasr
1724 | 1724 | 2026-04-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1725 | 1725 | 2026-04-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Nasr
1726 | 1726 | 2026-04-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1727 | 1727 | 2026-04-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1728 | 1728 | 2026-04-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Nasr
1729 | 1729 | 2026-04-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1730 | 1730 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1731 | 1731 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1732 | 1732 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1733 | 1733 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1734 | 1734 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1735 | 1735 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1736 | 1736 | 2026-04-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1737 | 1737 | 2026-04-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1738 | 1738 | 2026-04-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1739 | 1739 | 2026-04-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1740 | 1740 | 2026-04-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1741 | 1741 | 2026-04-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1742 | 1742 | 2026-04-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1743 | 1743 | 2026-04-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1744 | 1744 | 2026-04-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1745 | 1745 | 2026-04-21 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1746 | 1746 | 2026-04-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1747 | 1747 | 2026-04-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1748 | 1748 | 2026-04-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1749 | 1749 | 2026-04-22 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1750 | 1750 | 2026-04-22 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 1 | 10UMA | 10 | SALAMA
1751 | 1751 | 2026-04-22 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UMA | 2 | SALAMA
1752 | 1752 | 2026-04-22 | GR009 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | C |  | 1 | SALAMA
1753 | 1753 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1754 | 1754 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1755 | 1755 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | Nasr
1756 | 1756 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1757 | 1757 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1758 | 1758 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1759 | 1759 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1760 | 1760 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | Nasr
1761 | 1761 | 2026-04-23 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Nasr
1762 | 1762 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | Nasr
1763 | 1763 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Nasr
1764 | 1764 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1765 | 1765 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Nasr
1766 | 1766 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1767 | 1767 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1768 | 1768 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Nasr
1769 | 1769 | 2026-04-24 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1770 | 1770 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1771 | 1771 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1772 | 1772 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1773 | 1773 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1774 | 1774 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1775 | 1775 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1776 | 1776 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1777 | 1777 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1778 | 1778 | 2026-04-25 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1779 | 1779 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1780 | 1780 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1781 | 1781 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1782 | 1782 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1783 | 1783 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1784 | 1784 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1785 | 1785 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1786 | 1786 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1787 | 1787 | 2026-04-26 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1788 | 1788 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1789 | 1789 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1790 | 1790 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1791 | 1791 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1792 | 1792 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | Nasr
1793 | 1793 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1794 | 1794 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1795 | 1795 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1796 | 1796 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1797 | 1797 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | Nasr
1798 | 1798 | 2026-04-27 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Nasr
1799 | 1799 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | Nasr
1800 | 1800 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Nasr
1801 | 1801 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1802 | 1802 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Nasr
1803 | 1803 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1804 | 1804 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1805 | 1805 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Nasr
1806 | 1806 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1807 | 1807 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1808 | 1808 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1809 | 1809 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1810 | 1810 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1811 | 1811 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1812 | 1812 | 2026-04-28 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1813 | 1813 | 2026-04-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1814 | 1814 | 2026-04-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1815 | 1815 | 2026-04-29 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1816 | 1816 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1817 | 1817 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1818 | 1818 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1819 | 1819 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1820 | 1820 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | Nasr
1821 | 1821 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Nasr
1822 | 1822 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | Nasr
1823 | 1823 | 2026-04-30 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Nasr
1824 | 1824 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1825 | 1825 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 40 | Nasr
1826 | 1826 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1827 | 1827 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1828 | 1828 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Nasr
1829 | 1829 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1830 | 1830 | 2026-05-01 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1831 | 1831 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1832 | 1832 | 2026-05-02 | GR011 | Ground | Zinc Spray | Zinc Spray | 0 | EA | C |  | 8 | Nasr
1833 | 1833 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1834 | 1834 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1835 | 1835 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1836 | 1836 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1837 | 1837 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1838 | 1838 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1839 | 1839 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1840 | 1840 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1841 | 1841 | 2026-05-02 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1842 | 1842 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1843 | 1843 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1844 | 1844 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1845 | 1845 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1846 | 1846 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1847 | 1847 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1848 | 1848 | 2026-05-03 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1849 | 1849 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1850 | 1850 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1851 | 1851 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1852 | 1852 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1853 | 1853 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1854 | 1854 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1855 | 1855 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1856 | 1856 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1857 | 1857 | 2026-05-04 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1858 | 1858 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1859 | 1859 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1860 | 1860 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1861 | 1861 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1862 | 1862 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1863 | 1863 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | Nasr
1864 | 1864 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1865 | 1865 | 2026-05-05 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1866 | 1866 | 2026-05-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1867 | 1867 | 2026-05-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1868 | 1868 | 2026-05-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 50 | Nasr
1869 | 1869 | 2026-05-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Nasr
1870 | 1870 | 2026-05-06 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 50 | Nasr
1871 | 1871 | 2026-05-07 | CO008.1 | Conduit | Conduit (Galvanized) 60.3x3.91 | Conduit (Galvanized) | 60.3x3.91 | M | C | 90UTF | 18 | ahmed saaed | Fabrication
1872 | 1872 | 2026-05-07 | CO015.1 | Conduit Fitting | Conduit Coupling | Conduit Coupling | 50-11 NPT | EA | C | 90UTF | 9 | ahmed saaed | Fabrication
1873 | 1873 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UTF | 25 | Nasr
1874 | 1874 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1875 | 1875 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1876 | 1876 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1877 | 1877 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1878 | 1878 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | Nasr
1879 | 1879 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1880 | 1880 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 15 | Nasr
1881 | 1881 | 2026-05-07 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | Nasr
1882 | 1882 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | Nasr
1883 | 1883 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1884 | 1884 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1885 | 1885 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1886 | 1886 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1887 | 1887 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | Nasr
1888 | 1888 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UTF | 30 | Nasr
1889 | 1889 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1890 | 1890 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1891 | 1891 | 2026-05-08 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1892 | 1892 | 2026-05-09 | GR001 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 1 | 10UMA | 12.5 | SALAMA
1893 | 1893 | 2026-05-09 | GR005 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 1 | 10UMA | 2 | SALAMA
1894 | 1894 | 2026-05-09 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 1 | 10UMA | 2 | SALAMA
1895 | 1895 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1896 | 1896 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1897 | 1897 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1898 | 1898 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1899 | 1899 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1900 | 1900 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | Nasr
1901 | 1901 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1902 | 1902 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1903 | 1903 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | Nasr
1904 | 1904 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1905 | 1905 | 2026-05-09 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1906 | 1906 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UTF | 25 | Nasr
1907 | 1907 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1908 | 1908 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1909 | 1909 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1910 | 1910 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1911 | 1911 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1912 | 1912 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 15 | Nasr
1913 | 1913 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1914 | 1914 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1915 | 1915 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UTF | 25 | Nasr
1916 | 1916 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1917 | 1917 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1918 | 1918 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 15 | Nasr
1919 | 1919 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 15 | Nasr
1920 | 1920 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 30 | Nasr
1921 | 1921 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1922 | 1922 | 2026-05-10 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1923 | 1923 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1924 | 1924 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1925 | 1925 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 20 | Nasr
1926 | 1926 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1927 | 1927 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1928 | 1928 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | C | 90UTF | 25 | Nasr
1929 | 1929 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1930 | 1930 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1931 | 1931 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 15 | Nasr
1932 | 1932 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1933 | 1933 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1934 | 1934 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 15 | Nasr
1935 | 1935 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1936 | 1936 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1937 | 1937 | 2026-05-11 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1938 | 1938 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1939 | 1939 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1940 | 1940 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1941 | 1941 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1942 | 1942 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1943 | 1943 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1944 | 1944 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1945 | 1945 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1946 | 1946 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1947 | 1947 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1948 | 1948 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1949 | 1949 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 75 | Nasr
1950 | 1950 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1951 | 1951 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1952 | 1952 | 2026-05-12 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1953 | 1953 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1954 | 1954 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1955 | 1955 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1956 | 1956 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1957 | 1957 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1958 | 1958 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1959 | 1959 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1960 | 1960 | 2026-05-13 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 30 | Nasr
1961 | 1961 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1962 | 1962 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 15 | Nasr
1963 | 1963 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 30 | Nasr
1964 | 1964 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 30 | Nasr
1965 | 1965 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
1966 | 1966 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1967 | 1967 | 2026-05-14 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
1968 | 1968 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
1969 | 1969 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USG | 25 | Nasr
1970 | 1970 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20USJ | 30 | Nasr
1971 | 1971 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1972 | 1972 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1973 | 1973 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1974 | 1974 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 20 | Nasr
1975 | 1975 | 2026-05-15 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 15 | Nasr
1976 | 1976 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
1977 | 1977 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 20 | Nasr
1978 | 1978 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 20 | Nasr
1979 | 1979 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 20 | Nasr
1980 | 1980 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1981 | 1981 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
1982 | 1982 | 2026-05-16 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 30 | Nasr
1983 | 1983 | 2026-05-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1984 | 1984 | 2026-05-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 25 | Nasr
1985 | 1985 | 2026-05-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 25 | Nasr
1986 | 1986 | 2026-05-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1987 | 1987 | 2026-05-17 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1988 | 1988 | 2026-05-18 | GR012 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 1 | 10UMA | 1 | SALAMA
1989 | 1989 | 2026-05-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1990 | 1990 | 2026-05-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
1991 | 1991 | 2026-05-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1992 | 1992 | 2026-05-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
1993 | 1993 | 2026-05-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1994 | 1994 | 2026-05-18 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 20 | Nasr
1995 | 1995 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
1996 | 1996 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1997 | 1997 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
1998 | 1998 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 50 | Nasr
1999 | 1999 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 15 | Nasr
2000 | 2000 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
2001 | 2001 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 15 | Nasr
2002 | 2002 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
2003 | 2003 | 2026-05-19 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 20 | Nasr
2004 | 2004 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UMA | 25 | Nasr
2005 | 2005 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10UGB | 20 | Nasr
2006 | 2006 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 1 | 10USJ | 25 | Nasr
2007 | 2007 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UMA | 25 | Nasr
2008 | 2008 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 2 | 20UGB | 25 | Nasr
2009 | 2009 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UMA | 50 | Nasr
2010 | 2010 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 3 | 30UGB | 15 | Nasr
2011 | 2011 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UMA | 25 | Nasr
2012 | 2012 | 2026-05-20 | CG001 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 4 | 40UGB | 50 | Nasr
2013 | 2013 |  |  | 0 | 0 | 0 | 0 | 0
2014 | 2014 |  |  | 0 | 0 | 0 | 0 | 0
2015 | 2015 |  |  | 0 | 0 | 0 | 0 | 0
2016 | 2016 |  |  | 0 | 0 | 0 | 0 | 0
2017 | 2017 |  |  | 0 | 0 | 0 | 0 | 0
2018 | 2018 |  |  | 0 | 0 | 0 | 0 | 0
2019 | 2019 |  |  | 0 | 0 | 0 | 0 | 0
2020 | 2020 |  |  | 0 | 0 | 0 | 0 | 0
2021 | 2021 |  |  | 0 | 0 | 0 | 0 | 0
2022 | 2022 |  |  | 0 | 0 | 0 | 0 | 0
2023 | 2023 |  |  | 0 | 0 | 0 | 0 | 0
2024 | 2024 |  |  | 0 | 0 | 0 | 0 | 0
2025 | 2025 |  |  | 0 | 0 | 0 | 0 | 0
2026 | 2026 |  |  | 0 | 0 | 0 | 0 | 0
2027 | 2027 |  |  | 0 | 0 | 0 | 0 | 0
2028 | 2028 |  |  | 0 | 0 | 0 | 0 | 0
2029 | 2029 |  |  | 0 | 0 | 0 | 0 | 0
2030 | 2030 |  |  | 0 | 0 | 0 | 0 | 0
2031 | 2031 |  |  | 0 | 0 | 0 | 0 | 0
2032 | 2032 |  |  | 0 | 0 | 0 | 0 | 0
2033 | 2033 |  |  | 0 | 0 | 0 | 0 | 0
2034 | 2034 |  |  | 0 | 0 | 0 | 0 | 0
1957 | 1957 |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 3 | 4 | 5 | 6 | 7

## 케이블트레이입.출고현황
|  |  | Cable Tray 자재 집계현황(Material Summary) | [14 empty] | 2026-06-01
|  | 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [15 empty] | 2026-06-01 |  | DAESUN CODE | Sortation | Description | type | Size | Unit | 1항차
|  | Sortation | Sortation | Items / Services | Size | Unit | DOOSAN | [5 empty] | DAESUN |  |  |  |  | Remarks
[7 empty] | Purchase | Incoming | Not come | Other company | Handover | Balance | Incoming | Install | Fabrication | Scrap/ Faulty | Balance
TRY001 | 1 | Tray | Straight tray LP-50 | 3-LP-50/200/3-M-TA4 | 3000x200x50; T=1.5 | pcs | 8 | 8 | 0 | 0 | 0 | 8 |  | 0 | [5 empty] | TRY001 | Tray | Straight tray LP-50 | 3-LP-50/200/3-M-TA4 | 3000x200x50; T=1.5 | pcs | pcs
TRY002 | 2 | Tray | Straight tray LP-50 | 3-LP-50/300/3-M-TA4 | 3000x300x50; T=1.5 | pcs | 24 | 24 | 0 | 0 | 0 | 24 | 0 | 0 |  |  | 0 |  |  | TRY002 | Tray | Straight tray LP-50 | 3-LP-50/300/3-M-TA4 | 3000x300x50; T=1.5 | pcs | pcs
TRY002.1 | 3 | Tray | Straight tray LP-50 | 3-LP-50/400/3-M-TA4 | 692x396x48.5; T=1.5 | pcs | 81 | 81 | 0 | 0 | 0 | 81 | 0 | 0 |  |  | 0 |  |  | TRY002.1 | Tray | Straight tray LP-50 | 3-LP-50/400/3-M-TA4 | 692x396x48.5; T=1.5 | pcs | pcs
TRY003 | 4 | Tray | Straight tray LP-50 | 3-LP-50/500/3-M-TA4 | 3000x500x50; T=1.5 | pcs | 1180 | 1180 | 0 | 0 | 0 | 1180 | 0 | 0 |  |  | 0 |  |  | TRY003 | Tray | Straight tray LP-50 | 3-LP-50/500/3-M-TA4 | 3000x500x50; T=1.5 | pcs | pcs
TRY004 | 5 | Tray | Straight tray LP-50 | 3-LP-50/600/3-M-TA4 | 3000x600x50; T=1.5 | pcs | 556 | 556 | 0 | 0 | 0 | 556 | 0 | 0 |  |  | 0 |  |  | TRY004 | Tray | Straight tray LP-50 | 3-LP-50/600/3-M-TA4 | 3000x600x50; T=1.5 | pcs | pcs
TRY005 | 6 | Tray | Straight tray LP-100 | 3-LP-100/200/3-M-TA4 | 3000x200x100; T=1.5 | pcs | 10 | 10 | 0 | 0 | 0 | 10 | 0 | 0 |  |  | 0 |  |  | TRY005 | Tray | Straight tray LP-100 | 3-LP-100/200/3-M-TA4 | 3000x200x100; T=1.5 | pcs | pcs
TRY006 | 7 | Tray | Straight tray LP-100 | 3-LP-100/300/3-M-TA4 | 3000x300x100; T=1.5 | pcs | 22 | 22 | 0 | 0 | 0 | 22 | 0 | 0 |  |  | 0 |  |  | TRY006 | Tray | Straight tray LP-100 | 3-LP-100/300/3-M-TA4 | 3000x300x100; T=1.5 | pcs | pcs
TRY007 | 8 | Tray | Straight tray LP-100 | 3-LP-100/500/3-M-TA4 | 3000x500x100; T=1.5 | pcs | 250 | 250 | 0 | 0 | 0 | 250 | 0 | 0 |  |  | 0 |  |  | TRY007 | Tray | Straight tray LP-100 | 3-LP-100/500/3-M-TA4 | 3000x500x100; T=1.5 | pcs | pcs
TRY007.1 | 9 | Tray | Horizontal section SG-50/400-90 for turning the cable route from straight trays | 3-SG-50/400-90-M-TA4 | 692x396x48.5; T=1.5 | pcs | 11 | 11 | 0 | 0 | 0 | 11 | 0 | 0 |  |  | 0 |  |  | TRY007.1 | Tray | Horizontal section SG-50/400-90 for turning the cable route from straight trays | 3-SG-50/400-90-M-TA4 | 692x396x48.5; T=1.5 | pcs | pcs
TRY008 | 10 | Tray | Horizontal section SG-50/500-90 for turning the cable route from straight trays LP-50 and LP-100 at 90° | 3-SG-50/500-90-M-TA4 | 792x496x48.5; T=1.5 | pcs | 22 | 22 | 0 | 0 | 0 | 22 | 0 | 0 |  |  | 0 |  |  | TRY008 | Tray | Horizontal section SG-50/500-90 for turning the cable route from straight trays LP-50 and LP-100 at 90° | 3-SG-50/500-90-M-TA4 | 792x496x48.5; T=1.5 | pcs | pcs
TRY009 | 11 | Tray | Horizontal section SG-100/500-90 for turning the cable route from straight trays LP-50 and LP-100 at 90° | 3-SG-100/500-90-M-TA4 | 792x496x98.5; T=1.5 | pcs | 6 | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  |  | 0 |  |  | TRY009 | Tray | Horizontal section SG-100/500-90 for turning the cable route from straight trays LP-50 and LP-100 at 90° | 3-SG-100/500-90-M-TA4 | 792x496x98.5; T=1.5 | pcs | pcs
TRY009.1 | 12 | Tray | Horizontal section SG-50/600-90 for turning the cable route from straight trays | 3-SG-50/600-90-M-TA5 | 892x596x48.5; T=1.5 | pcs | 40 | 40 | 0 | 0 | 0 | 40 | 0 | 0 |  |  | 0 |  |  | TRY009.1 | Tray | Horizontal section SG-50/600-90 for turning the cable route from straight trays | 3-SG-50/600-90-M-TA5 | 892x596x48.5; T=1.5 | pcs | pcs
TRY010 | 13 | Tray | Branch section SO-50/500 for branching the cable route from straight trays LP-50 and LP-100 for three directions | 3-SO-50/500-M-TA4 | #N/A | pcs | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 |  |  | 0 |  |  | TRY010 | Tray | Branch section SO-50/500 for branching the cable route from straight trays LP-50 and LP-100 for three directions | 3-SO-50/500-M-TA4 | #N/A | pcs | pcs
TRY010.1 | 14 | Tray | Vertical section SV-50/400 for vertical bending of cable route from straight trays | 3-SV-50/400-M-TA4 | 331x396x50; T=1.5 | pcs | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  |  | 0 |  |  | TRY010.1 | Tray | Vertical section SV-50/400 for vertical bending of cable route from straight trays | 3-SV-50/400-M-TA4 | 331x396x50; T=1.5 | pcs | pcs
TRY011 | 15 | Tray | Vertical section SV-50/500 for vertical bending of cable route from straight trays LP-50 and LP-100 up or down at any angle | 3-SV-50/500-M-TA4 | 331x170x496x50; T=1.5 | pcs | 80 | 80 | 0 | 0 | 0 | 80 | 0 | 0 |  |  | 0 |  |  | TRY011 | Tray | Vertical section SV-50/500 for vertical bending of cable route from straight trays LP-50 and LP-100 up or down at any angle | 3-SV-50/500-M-TA4 | 331x170x496x50; T=1.5 | pcs | pcs
TRY012 | 16 | Tray | Vertical section SV-100/500 for vertical bending of cable route from straight trays LP-50 and LP-100 up or down at any angle | 3-SV-100/500-M-TA4 | 395x205x496x100; T=1.5 | pcs | 20 | 20 | 0 | 0 | 0 | 20 | 0 | 0 |  |  | 0 |  |  | TRY012 | Tray | Vertical section SV-100/500 for vertical bending of cable route from straight trays LP-50 and LP-100 up or down at any angle | 3-SV-100/500-M-TA4 | 395x205x496x100; T=1.5 | pcs | pcs
TRY013 | 17 | Tray | Straight duct KP | 3-KP-0.1/0.2-3-M-TA4 | 3000x200x100; T=1.5 | pcs | 56 | 56 | 0 | 0 | 0 | 56 | 0 | 0 |  |  | 0 |  |  | TRY013 | Tray | Straight duct KP | 3-KP-0.1/0.2-3-M-TA4 | 3000x200x100; T=1.5 | pcs | pcs
TRY014 | 18 | Tray | Straight duct KP | 3-KP-0.1/0.3-3-M-TA4 | 3000x300x 100; T=1.5 | pcs | 84 | 84 | 0 | 0 | 0 | 84 | 0 | 0 |  |  | 0 |  |  | TRY014 | Tray | Straight duct KP | 3-KP-0.1/0.3-3-M-TA4 | 3000x300x 100; T=1.5 | pcs | pcs
TRY015 | 19 | Tray | Siraight duct KP | 3-KP-0.1/0.5-3-M-TA4 | 3000x500x 100; T=1.5 | pcs | 40 | 40 | 0 | 0 | 0 | 40 | 0 | 0 |  |  | 0 |  |  | TRY015 | Tray | Siraight duct KP | 3-KP-0.1/0.5-3-M-TA4 | 3000x500x 100; T=1.5 | pcs | pcs
TRY016 | 20 | Tray | Angle duct KUG for horizontal bend of cable route at 90° | 3-KUG-0.1/0.2-M-TA4 | 455x196x103; T=1.5 | pcs | 10 | 10 | 0 | 0 | 0 | 10 | 0 | 0 |  |  | 0 |  |  | TRY016 | Tray | Angle duct KUG for horizontal bend of cable route at 90° | 3-KUG-0.1/0.2-M-TA4 | 455x196x103; T=1.5 | pcs | pcs
TRY017 | 21 | Tray | Angle duct KUG for horizontal bend of cable route et 90° | 3-KUG-0.1/0.3-M-TA4 | 555x296x103; T=1.5 | pcs | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 |  |  | 0 |  |  | TRY017 | Tray | Angle duct KUG for horizontal bend of cable route et 90° | 3-KUG-0.1/0.3-M-TA4 | 555x296x103; T=1.5 | pcs | pcs
TRY018 | 22 | Tray | Angle duct KUG for horizontal bend of cable route at 90° | 3-KUG-0.1/0.5-M-TA4 | 755x496x103; T=1.5 | pcs | 6 | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  |  | 0 |  |  | TRY018 | Tray | Angle duct KUG for horizontal bend of cable route at 90° | 3-KUG-0.1/0.5-M-TA4 | 755x496x103; T=1.5 | pcs | pcs
TRY019 | 23 | Tray | Angle duct KUG for horizontal bend of cable route at 45° | 3-KUG-0.1/0.2-45-M-TA4 | #N/A | pcs | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  |  | 0 |  |  | TRY019 | Tray | Angle duct KUG for horizontal bend of cable route at 45° | 3-KUG-0.1/0.2-45-M-TA4 | #N/A | pcs | pcs
TRY020 | 24 | Tray | Angle duct KUG for horizontal bend of cable route at 45° | 3-KUG-0.1/0.3-45-M-TA4 | #N/A | pcs | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  |  | 0 |  |  | TRY020 | Tray | Angle duct KUG for horizontal bend of cable route at 45° | 3-KUG-0.1/0.3-45-M-TA4 | #N/A | pcs | pcs
TRY021 | 25 | Tray | Angle duct KUV for turning horizontal cable route upward at an anale of 90° | 3-KUV-0.1/0.5-M-TA4 | 290x496x103; T=1.5 | pcs | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  |  | 0 |  |  | TRY021 | Tray | Angle duct KUV for turning horizontal cable route upward at an anale of 90° | 3-KUV-0.1/0.5-M-TA4 | 290x496x103; T=1.5 | pcs | pcs
TRY022 | 26 | Tray | Angle duct KUN for turning horizontal cable route downwards at an anqle of 90° | 3-KUN-0.1/0.5-M-TA4 | 352x496x103; T=1.5 | pcs | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  |  | 0 |  |  | TRY022 | Tray | Angle duct KUN for turning horizontal cable route downwards at an anqle of 90° | 3-KUN-0.1/0.5-M-TA4 | 352x496x103; T=1.5 | pcs | pcs
TRY022.1 | 27 | Tray | Branch section SO | 3-SO-50/400-M-TA4 | 780x396x48.5; I T=1.5 | pcs | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 |  |  | 0 |  |  | TRY022.1 | Tray | Branch section SO | 3-SO-50/400-M-TA4 | 780x396x48.5; I T=1.5 | pcs | pcs
TRY022.2 | 28 | Tray | Branch section SO | 3-SO-50/600-M-TA4 | 980x596x48.5; I T=1-5 | pcs | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  |  | 0 |  |  | TRY022.2 | Tray | Branch section SO | 3-SO-50/600-M-TA4 | 980x596x48.5; I T=1-5 | pcs | pcs
TRY022.3 | 29 | Tray | Vertical section SV-.. ./... | 3-SV-50/600-M-TA4 | 331x596x50; T=1.5 | pcs | 35 | 35 | 0 | 0 | 0 | 35 | 0 | 0 |  |  | 0 |  |  | TRY022.3 | Tray | Vertical section SV-.. ./... | 3-SV-50/600-M-TA4 | 331x596x50; T=1.5 | pcs | pcs
TRY023 | 30 | Console | Console KS3-340 | 3-KS3-340-M-TA4 | 344x45x146; T=2.0 | pcs | 54 | 54 | 0 | 0 | 0 | 54 | 0 | 0 |  |  | 0 |  |  | TRY023 | Console | Console KS3-340 | 3-KS3-340-M-TA4 | 344x45x146; T=2.0 | pcs | pcs
TRY024 | 31 | Console | Console KS3-440 | 3-KS3-440-M-TA4 | 444x45x146; T=2.0 | pcs | 176 | 176 | 0 | 0 | 0 | 176 | 0 | 0 |  |  | 0 |  |  | TRY024 | Console | Console KS3-440 | 3-KS3-440-M-TA4 | 444x45x146; T=2.0 | pcs | pcs
TRY025 | 32 | Console | Console KS3-540 | 3-KS3-540-M-TA4 | 544x45x146; T=2.0 | pcs | 348 | 348 | 0 | 0 | 0 | 348 | 0 | 0 |  |  | 0 |  |  | TRY025 | Console | Console KS3-540 | 3-KS3-540-M-TA4 | 544x45x146; T=2.0 | pcs | pcs
TRY026 | 33 | Console | Console KS3-640 | 3-KS3-640-M-TA4 | 644x45x146; T=3.0 | pcs | 4094 | 4094 | 0 | 0 | 0 | 4094 | 0 | 0 |  |  | 0 |  |  | TRY026 | Console | Console KS3-640 | 3-KS3-640-M-TA4 | 644x45x146; T=3.0 | pcs | pcs
TRY027 | 34 | Console | Console KS3-750 | 3-KS3-750-M-TA4 | 754x45x146; T=3.0 | pcs | 1865 | 1865 | 0 | 0 | 423 | 1442 | 423 | 144 |  |  | 279 |  |  | TRY027 | Console | Console KS3-750 | 3-KS3-750-M-TA4 | 754x45x146; T=3.0 | pcs | pcs
TRY028 | 35 | Console | Console KS3-850 | 3-KS3-850-M-TA4 | 850x50x180; T=4.0 | pcs | 82 | 82 | 0 | 0 | 0 | 82 | 0 | 0 |  |  | 0 |  |  | TRY028 | Console | Console KS3-850 | 3-KS3-850-M-TA4 | 850x50x180; T=4.0 | pcs | pcs
TRY029 | 36 | Console | Console KS3-1050 | 3-KS3-1050-M-TA4 | 1050x50x180; T=4.0 | pcs | 80 | 80 | 0 | 0 | 0 | 80 | 0 | 0 |  |  | 0 |  |  | TRY029 | Console | Console KS3-1050 | 3-KS3-1050-M-TA4 | 1050x50x180; T=4.0 | pcs | pcs
TRY030 | 37 |  | Perforated Z-section | 3-PZ-N-83x40x80x8-TA4 | 83x40x80x8; T=3.0 | pcs | 10 | 10 | 0 | 0 | 0 | 10 | 0 | 0 |  |  | 0 |  |  | TRY030 |  | Perforated Z-section | 3-PZ-N-83x40x80x8-TA4 | 83x40x80x8; T=3.0 | pcs | pcs
TRY030.1 | 38 | Rack | Rack ST | 3-ST-60-4-M-TA4 | 600x63x37; T=4.0 | pcs | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 |  |  | TRY030.1 | Rack | Rack ST | 3-ST-60-4-M-TA4 | 600x63x37; T=4.0 | pcs | pcs
TRY030.2 | 39 | Rack | Rack ST | 3-ST-80-4-M-TA4 | 800x63x37; T=4.0 | pcs | 15 | 15 | 0 | 0 | 0 | 15 | 0 | 0 |  |  | 0 |  |  | TRY030.2 | Rack | Rack ST | 3-ST-80-4-M-TA4 | 800x63x37; T=4.0 | pcs | pcs
TRY031 | 40 | Rack | Rack ST | 3-ST-90-4-M-TA4 | 900x63x37x20; T=4.0 | pcs | 286 | 286 | 0 | 0 | 0 | 286 | 0 | 0 |  |  | 0 |  |  | TRY031 | Rack | Rack ST | 3-ST-90-4-M-TA4 | 900x63x37x20; T=4.0 | pcs | pcs
TRY031.1 | 41 | Rack | Rack ST | 3-ST-100-4-M-TA4 | 1000x 63x37; T=4.0 | pcs | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  |  | 0 |  |  | TRY031.1 | Rack | Rack ST | 3-ST-100-4-M-TA4 | 1000x 63x37; T=4.0 | pcs | pcs
TRY032 | 42 | Rack | Rack ST | 3-ST-120-4-M-TA4 | 1200x63x37x20; T=4.0 | pcs | 24 | 24 | 0 | 0 | 0 | 24 | 0 | 0 |  |  | 0 |  |  | TRY032 | Rack | Rack ST | 3-ST-120-4-M-TA4 | 1200x63x37x20; T=4.0 | pcs | pcs
TRY033 | 43 | Rack | Rack ST | 3-ST-150-4-M-TA4 | 1500x63x37x20; T=4.0 | pcs | 223 | 223 | 0 | 0 | 0 | 223 | 0 | 0 |  |  | 0 |  |  | TRY033 | Rack | Rack ST | 3-ST-150-4-M-TA4 | 1500x63x37x20; T=4.0 | pcs | pcs
TRY033.1 | 44 | Rack | Rack ST | 3-ST-160-4-M-TA4 | 1600x63x37; T=4.0 | pcs | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 |  |  | 0 |  |  | TRY033.1 | Rack | Rack ST | 3-ST-160-4-M-TA4 | 1600x63x37; T=4.0 | pcs | pcs
TRY033.2 | 45 | Rack | Rack ST | 3-ST-180-4-M-TA4 | 1800x63x37; T=4.0 | pcs | 56 | 56 | 0 | 0 | 0 | 56 | 0 | 0 |  |  | 0 |  |  | TRY033.2 | Rack | Rack ST | 3-ST-180-4-M-TA4 | 1800x63x37; T=4.0 | pcs | pcs
TRY034 | 46 | Rack | Rack ST | 3-ST-200-4-M-TA4 | 2000x63x37x20; T=4.0 | pcs | 321 | 321 | 0 | 0 | 0 | 321 | 0 | 0 |  |  | 0 |  |  | TRY034 | Rack | Rack ST | 3-ST-200-4-M-TA4 | 2000x63x37x20; T=4.0 | pcs | pcs
TRY034.1 | 47 | Rack | Rack ST | 3-ST-240-4-M-TA4 | 2400x63x37; T=4.0 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | TRY034.1 | Rack | Rack ST | 3-ST-240-4-M-TA4 | 2400x63x37; T=4.0 | pcs | pcs
TRY035 | 48 | Rack | Rack ST | 3-ST-260-4-M-TA4 | 2600x63x37x20; T=4.0 | pcs | 244 | 244 | 0 | 0 | 119 | 125 | 119 | 18 |  |  | 101 |  |  | TRY035 | Rack | Rack ST | 3-ST-260-4-M-TA4 | 2600x63x37x20; T=4.0 | pcs | pcs
TRY035.1 | 49 | Rack | Rack ST | 3-ST-280-4-M-TA4 | 2800x63x37; T=4.0 | pcs | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 |  |  | 0 |  |  | TRY035.1 | Rack | Rack ST | 3-ST-280-4-M-TA4 | 2800x63x37; T=4.0 | pcs | pcs
TRY035.2 | 50 | Rack | Rack ST | 3-ST-300-4-M-TA4 | 3000x63x37; T=4.0 | pcs | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 |  |  | 0 |  |  | TRY035.2 | Rack | Rack ST | 3-ST-300-4-M-TA4 | 3000x63x37; T=4.0 | pcs | pcs
TRY036 | 51 | Rack | Rack ST | 3-ST-320-4-M-TA4 | 3200x63x37x20; T=4.0 | pcs | 76 | 76 | 0 | 0 | 0 | 76 | 0 | 0 |  |  | 0 |  |  | TRY036 | Rack | Rack ST | 3-ST-320-4-M-TA4 | 3200x63x37x20; T=4.0 | pcs | pcs
TRY037 | 52 | Rack | Rack ST | 3-ST-380-4-M-TA4 | 3800x63x37x20; T=4.0 | pcs | 116 | 116 | 0 | 0 | 0 | 116 | 0 | 0 |  |  | 0 |  |  | TRY037 | Rack | Rack ST | 3-ST-380-4-M-TA4 | 3800x63x37x20; T=4.0 | pcs | pcs
TRY037.1 | 53 | Rack | Double rack STD | 3-STD-50-4-M-TA4 | 500x63x105; T=4.0 | pcs | 17 | 17 | 0 | 0 | 0 | 17 | 0 | 0 |  |  | 0 |  |  | TRY037.1 | Rack | Double rack STD | 3-STD-50-4-M-TA4 | 500x63x105; T=4.0 | pcs | pcs
TRY038 | 54 | Rack | Double rack STD | 3-STD-70-4-M-TA4 | 700x63x105; T=4.0 | pcs | 46 | 46 | 0 | 0 | 0 | 46 | 0 | 0 |  |  | 0 |  |  | TRY038 | Rack | Double rack STD | 3-STD-70-4-M-TA4 | 700x63x105; T=4.0 | pcs | pcs
TRY039 | 55 | Rack | Double rack STD | 3-STD-90-4-M-TA4 | 900x63x105; T=4.0 | pcs | 151 | 151 | 0 | 0 | 0 | 151 | 0 | 0 |  |  | 0 |  |  | TRY039 | Rack | Double rack STD | 3-STD-90-4-M-TA4 | 900x63x105; T=4.0 | pcs | pcs
TRY040 | 56 | Rack | Double rack STD | 3-STD-120-4-M-TA4 | 1200x63x 105; T=4.0 | pcs | 14 | 14 | 0 | 0 | 0 | 14 | 0 | 0 |  |  | 0 |  |  | TRY040 | Rack | Double rack STD | 3-STD-120-4-M-TA4 | 1200x63x 105; T=4.0 | pcs | pcs
TRY041 | 57 | Rack | Double rack STD | 3-STD-150-4-M-TA4 | 1500x63x 105; T=4.0 | pcs | 22 | 22 | 0 | 0 | 0 | 22 | 0 | 0 |  |  | 0 |  |  | TRY041 | Rack | Double rack STD | 3-STD-150-4-M-TA4 | 1500x63x 105; T=4.0 | pcs | pcs
TRY042 | 58 | Rack | Double rack STD | 3-STD-180-4-M-TA4 | 1800x63x105; T=4.0 | pcs | 38 | 38 | 0 | 0 | 0 | 38 | 0 | 0 |  |  | 0 |  |  | TRY042 | Rack | Double rack STD | 3-STD-180-4-M-TA4 | 1800x63x105; T=4.0 | pcs | pcs
TRY043 | 59 | Rack | Double rack STD | 3-STD-200-4-M-TA4 | 2000x63x105; T=4.0 | pcs | 39 | 39 | 0 | 0 | 0 | 39 | 0 | 0 |  |  | 0 |  |  | TRY043 | Rack | Double rack STD | 3-STD-200-4-M-TA4 | 2000x63x105; T=4.0 | pcs | pcs
TRY043.1 | 60 | Rack | Double rack STD | 3-STD-400-4-M-TA4 | 4000x63x109; T=4.0 | pcs | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 |  |  | 0 |  |  | TRY043.1 | Rack | Double rack STD | 3-STD-400-4-M-TA4 | 4000x63x109; T=4.0 | pcs | pcs
TRY044 | 61 | Rack | Double rack STD | 3-STD-500-4-M-TA4 | 5000x63x109; T=4.0 | pcs | 72 | 72 | 0 | 0 | 0 | 72 | 0 | 0 |  |  | 0 |  |  | TRY044 | Rack | Double rack STD | 3-STD-500-4-M-TA4 | 5000x63x109; T=4.0 | pcs | pcs
TRY045 | 62 | brace | Stiffening brace SZh-100-4 | 3-SZh-100-M-TA4 | 1000x64x37; T=4.0 | pcs | 18 | 18 | 0 | 0 | 0 | 18 | 0 | 0 |  |  | 0 |  |  | TRY045 | brace | Stiffening brace SZh-100-4 | 3-SZh-100-M-TA4 | 1000x64x37; T=4.0 | pcs | pcs
TRY046 | 63 | Clamp&Gusset | Simple gusset KP for racks ST | 3-KP-4-M-TA4 | 170x72x110; T=4.0 | pcs | 74 | 74 | 0 | 0 | 56 | 18 | 56 | 0 |  |  | 56 |  |  | TRY046 | Simple gusset | Simple gusset KP for racks ST | 3-KP-4-M-TA4 | 170x72x110; T=4.0 | pcs | pcs
TRY047 | 64 |  | Transition angle UP | 3-UP-4-M-TA4 | 60x60; T=4.0 | pcs | 1176 | 1176 | 0 | 0 | 0 | 1176 | 0 | 0 |  |  | 0 |  |  | TRY047 |  | Transition angle UP | 3-UP-4-M-TA4 | 60x60; T=4.0 | pcs | pcs
TRY048 | 65 |  | Mounting unit UK-50 | 3-UK-50 | 70x30x32; T=2.0 | pcs | 56 | 56 | 0 | 0 | 0 | 56 | 0 | 0 |  |  | 0 |  |  | TRY048 |  | Mounting unit UK-50 | 3-UK-50 | 70x30x32; T=2.0 | pcs | pcs
TRY049 | 66 | Clamp&Gusset | Side gusset KB for racks ST | 3-KB-4-M-TA4 | 150x72x70; T=4.0 | pcs | 4700 | 4700 | 0 | 0 | 1046 | 3654 | 1046 | 90 |  |  | 956 |  |  | TRY049 | Side gusset | Side gusset KB for racks ST | 3-KB-4-M-TA4 | 150x72x70; T=4.0 | pcs | pcs
TRY050 | 67 | Clamp&Gusset | Double gusset KD for racks STD | 3-KD-4-M-TA4 | 109x72x72x110; T=4.0 | pcs | 153 | 153 | 0 | 0 | 141 | 12 | 141 | 0 |  |  | 141 |  |  | TRY050 | Double gusset | Double gusset KD for racks STD | 3-KD-4-M-TA4 | 109x72x72x110; T=4.0 | pcs | pcs
TRY051 | 68 | Clamp&Gusset | Double reinforced gusset KOU for racks ST with strut RP | 3-KDU-4-M-TA4 | 250x72x110; T=4.0 | pcs | 236 | 236 | 0 | 0 | 0 | 236 | 0 | 0 |  |  | 0 |  |  | TRY051 | Double gusset | Double reinforced gusset KOU for racks ST with strut RP | 3-KDU-4-M-TA4 | 250x72x110; T=4.0 | pcs | pcs
TRY051.1 | 69 |  | Base OSD for racks STD | 3-OSD-4-M-TA4 | 109x50x260; T=4.0 | pcs | 16 | 16 | 0 | 0 | 0 | 16 | 0 | 0 |  |  | 0 |  |  | TRY051.1 |  | Base OSD for racks STD | 3-OSD-4-M-TA4 | 109x50x260; T=4.0 | pcs | pcs
TRY052 | 70 |  | Base OSD for racks STD | 3-OSD-4-M-TA4 | 109x72x50x260; T=4.0 | pcs | 168 | 168 | 0 | 0 | 0 | 168 | 0 | 0 |  |  | 0 |  |  | TRY052 |  | Base OSD for racks STD | 3-OSD-4-M-TA4 | 109x72x50x260; T=4.0 | pcs | pcs
TRY053 | 71 | Clamp&Gusset | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 4926 | 4926 | 0 | 0 | 1102 | 3824 | 1102 | 90 |  |  | 1012 |  |  | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | pcs
TRY054 | 72 | Clamp&Gusset | Transition clamp SP 150P for gussets for welding | 3-SP-150P-M-TA4 | 150x72x59; T=4.0 | pcs | 336 | 336 | 0 | 0 | 0 | 336 | 0 | 0 |  |  | 0 |  |  | TRY054 | Transition clamp for welding | Transition clamp SP 150P for gussets for welding | 3-SP-150P-M-TA4 | 150x72x59; T=4.0 | pcs | pcs
TRY055 | 73 |  | Hilti anchor | HDA-P M12 | HDA-P M12x125/30 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | TRY055 |  | Hilti anchor | HDA-P M12 | HDA-P M12x125/30 | pcs | pcs
TRY055.1 | 74 |  | Hilti anchor | HDA-P M10 | HDA-P M10x100/20 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | TRY055.1 |  | Hilti anchor | HDA-P M10 | HDA-P M10x100/20 | pcs | pcs
TRY056 | 75 |  | Section | - | 200x100x8; L=400 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | TRY056 |  | Section | - | 200x100x8; L=400 | pcs | pcs
TRY057 | 76 |  | Section | - | 200x100x8; L=200 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | TRY057 |  | Section | - | 200x100x8; L=200 | pcs | pcs
[20 empty] | 1.2.13 |  | 0 |  |  | 0 | 0
▶▶
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26

## Cable Tray-income
POR CONTROL LOG - Income
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [7 empty] | from Doosan to Daesun
| No | RSI No | POR | Date | Material No. | Sortation | Items / Services | Applicable Code & Standards | Size | Unit | Q'TY | Remarks
| 1 | RSI2026001190 | 9-072-D-450-1043-E | 2026-03-28 | TRY046 | Simple gusset | Simple gusset KP for racks ST | 3-KP-4-M-TA4 | 170x72x110; T=4.0 | pcs | 56
| 2 | RSI2026001190 | 9-072-D-450-1043-E | 2026-03-28 | TRY049 | Side gusset | Side gusset KB for racks ST | 3-KB-4-M-TA4 | 150x72x70; T=4.0 | pcs | 1046
| 3 | RSI2026001190 | 9-072-D-450-1043-E | 2026-03-28 | TRY050 | Double gusset | Double gusset KD for racks STD | 3-KD-4-M-TA4 | 109x72x72x110; T=4.0 | pcs | 141
| 4 | RSI2026001190 | 9-072-D-450-1043-E | 2026-03-28 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1102
| 5 | RSI2026001809 | 9-072-D-450-1043-E | 2026-04-29 | TRY027 | Console | Console KS3-340 | 3-KS3-340-M-TA4 | 344x45x146; T=2.0 | pcs | 423
| 6 | RSI2026001809 | 9-072-D-450-1043-E | 2026-04-29 | TRY035 | Rack | Rack ST | 3-ST-60-4-M-TA4 | 600x63x37; T=4.0 | pcs | 119
7
8
9
[14 empty] | 12893.6 | -12893.6
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6 | 6
7 | 7
8 | 8
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
15 | 15
16 | 16
17 | 17
18 | 18
19 | 19
20 | 20
21 | 21
22 | 22
23 | 23
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43
44 | 44
45 | 45
46 | 46
47 | 47
48 | 48
49 | 49
50 | 50
51 | 51
52 | 52
53 | 53
54 | 54
55 | 55
56 | 56
57 | 57
58 | 58
59 | 59
60 | 60
61 | 61
62 | 62
63 | 63
64 | 64
65 | 65
66 | 66
67 | 67
68 | 68
69 | 69
70 | 70
71 | 71
72 | 72
73 | 73
74 | 74
75 | 75
76 | 76
77 | 77
78 | 78
79 | 79
80 | 80
81 | 81 | [11 empty] | 1 pcs
82 | 82 | [11 empty] | 1 roll
83 | 83 | [11 empty] | 30 pcs
84 | 84 | [11 empty] | 1 roll
85 | 85 | [11 empty] | 2 roll
86 | 86 | [11 empty] | 28 pcs
87 | 87
88 | 88
89 | 89 | [11 empty] | 1 roll
90 | 90
91 | 91
92 | 92
93 | 93
94 | 94 | [11 empty] | 2 roll
95 | 95
96 | 96
97 | 97
98 | 98 | [11 empty] | 0
99 | 99 | [12 empty] | 40690
100 | 100 | [12 empty] | 0
101 | 101 | [12 empty] | 40690
102 | 102
103 | 103
104 | 104
105 | 105
106 | 106
107 | 107
108 | 108
109 | 109
110 | 110
111 | 111
112 | 112
113 | 113
114 | 114
115 | 115
116 | 116
117 | 117
118 | 118
119 | 119
120 | 120
121 | 121
122 | 122
123 | 123
124 | 124
125 | 125
126 | 126
127 | 127
128 | 128
129 | 129
130 | 130
131 | 131
132 | 132
133 | 133
134 | 134
135 | 135
136 | 136
137 | 137
138 | 138
139 | 139
140 | 140
141 | 141
[6 empty] | 3 | 4 | 5 | 6 | 7

## Cable Tray-Log-out
POR CONTROL LOG - Issue
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [5 empty] | from Warehouse & Workshop to Site
| No | Date | Material No. | Sortation | Items / Services | Applicable Code & Standards | Size | Unit | Unit # | BLDG | Q'TY | User | Remarks
| 1 | 2026-03-30 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 30 | Hussen
| 2 | 2026-04-04 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 10 | Hussen
| 3 | 2026-04-08 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 15 | Saad
| 4 | 2026-04-09 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 15 | ABDELSAMI
| 5 | 2026-04-11 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 6 | ABDELSAMI
| 6 | 2026-04-12 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 9 | ABDELSAMI
| 7 | 2026-04-29 | TRY053 | Transition clamp | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 1 | 10USG | 5 | ABDELSAMI
| 8 | 2026-05-01 | TRY035 | Rack | Rack ST | 3-ST-60-4-M-TA4 | 600x63x37; T=4.0 | pcs | 1 | 10USG | 18 | Hussen
| 9 | 2026-05-01 | TRY049 | Side gusset | Side gusset KB for racks ST | 3-KB-4-M-TA4 | 150x72x70; T=4.0 | pcs | 1 | 10USG | 90 | Hussen
| 10 | 2026-05-04 | TRY027 | Console | Console KS3-340 | 3-KS3-340-M-TA4 | 344x45x146; T=2.0 | pcs | 1 | 10USG | 56 | Hussen
| 11 | 2026-05-05 | TRY027 | Console | Console KS3-340 | 3-KS3-340-M-TA4 | 344x45x146; T=2.0 | pcs | 1 | 10USG | 88 | Hussen
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6 | 6
7 | 7
8 | 8
9 | 9
10 | 10
11 | 11
12 | 12
13 | 13
14 | 14
15 | 15
16 | 16
17 | 17
18 | 18
19 | 19
20 | 20
21 | 21
22 | 22
23 | 23
24 | 24
25 | 25
26 | 26
27 | 27
28 | 28
29 | 29
30 | 30
31 | 31
32 | 32
33 | 33
34 | 34
35 | 35
36 | 36
37 | 37
38 | 38
39 | 39
40 | 40
41 | 41
42 | 42
43 | 43 | [7 empty] | 4
44 | 44 | [7 empty] | 4
45 | 45 | [7 empty] | 3
46 | 46 | [7 empty] | 3
47 | 47 | [7 empty] | 3
48 | 48
49 | 49
50 | 50 | [7 empty] | 4
51 | 51 | [7 empty] | 1
52 | 52 | [7 empty] | 4
53 | 53 | [7 empty] | 1
54 | 54 | [7 empty] | 2
55 | 55 | [7 empty] | 2
56 | 56 | [7 empty] | 3
57 | 57
58 | 58
59 | 59
60 | 60
61 | 61
62 | 62
63 | 63
64 | 64
65 | 65
66 | 66
67 | 67
68 | 68
69 | 69 | [7 empty] | 4
70 | 70
71 | 71
72 | 72
73 | 73
74 | 74
75 | 75
76 | 76
77 | 77
78 | 78
79 | 79
80 | 80
81 | 81
82 | 82
83 | 83
84 | 84
85 | 85
86 | 86
87 | 87
88 | 88
89 | 89
90 | 90
91 | 91
92 | 92
93 | 93
94 | 94
95 | 95
96 | 96
97 | 97
98 | 98
99 | 99
100 | 100
101 | 101
102 | 102
103 | 103
104 | 104
105 | 105
106 | 106
107 | 107
108 | 108
109 | 109
110 | 110
111 | 111
112 | 112
113 | 113
114 | 114
115 | 115
116 | 116
117 | 117
118 | 118
119 | 119
120 | 120
121 | 121
122 | 122
123 | 123
124 | 124
125 | 125
126 | 126
127 | 127
128 | 128
129 | 129
130 | 130
131 | 131
132 | 132
133 | 133
134 | 134
135 | 135
136 | 136
137 | 137
138 | 138
139 | 139
140 | 140
141 | 141
142 | 142
143 | 143
144 | 144
145 | 145
146 | 146
147 | 147
148 | 148
149 | 149
150 | 150
151 | 151
152 | 152
153 | 153
154 | 154
155 | 155
156 | 156
157 | 157
158 | 158
159 | 159
160 | 160
161 | 161
162 | 162
163 | 163
164 | 164
165 | 165
166 | 166
167 | 167
168 | 168
169 | 169
170 | 170
171 | 171
172 | 172
173 | 173
174 | 174
175 | 175
176 | 176
177 | 177
178 | 178
179 | 179
180 | 180
181 | 181
182 | 182
183 | 183
184 | 184
185 | 185
186 | 186
187 | 187
188 | 188
189 | 189
190 | 190
191 | 191
192 | 192
193 | 193
194 | 194
195 | 195
196 | 196
197 | 197
198 | 198
199 | 199
200 | 200
201 | 201
202 | 202
203 | 203
204 | 204
205 | 205
206 | 206
207 | 207
208 | 208
209 | 209
210 | 210
211 | 211
212 | 212
213 | 213
214 | 214
215 | 215
216 | 216
217 | 217
218 | 218
219 | 219
220 | 220
221 | 221
222 | 222
223 | 223
224 | 224
225 | 225
226 | 226
227 | 227
228 | 228
229 | 229
230 | 230
231 | 231
232 | 232
233 | 233
234 | 234
235 | 235
236 | 236
237 | 237
238 | 238
239 | 239
240 | 240
241 | 241
242 | 242
243 | 243 | [7 empty] | 1
244 | 244
245 | 245 | [7 empty] | 1
246 | 246 | [7 empty] | 2
247 | 247 | [7 empty] | 2
248 | 248 | [7 empty] | 4
249 | 249 | [7 empty] | 1
250 | 250 | [7 empty] | 2
251 | 251 | [7 empty] | 1
252 | 252 | [7 empty] | 1
253 | 253 | [7 empty] | 2
254 | 254 | [7 empty] | 1
255 | 255 | [7 empty] | 1
256 | 256 | [7 empty] | 1
257 | 257 | [7 empty] | 1
258 | 258 | [7 empty] | 2
259 | 259 | [7 empty] | 2
260 | 260 | [7 empty] | 2
261 | 261 | [7 empty] | 2
262 | 262 | [7 empty] | 4
263 | 263 | [7 empty] | 1
264 | 264 | [7 empty] | 3
265 | 265 | [7 empty] | 1
266 | 266 | [7 empty] | 1
267 | 267 | [7 empty] | 1
268 | 268 | [7 empty] | 2
269 | 269 | [7 empty] | 1
270 | 270 | [7 empty] | 1
271 | 271 | [7 empty] | 1
272 | 272 | [7 empty] | 2
273 | 273 | [7 empty] | 1
274 | 274 | [7 empty] | 2
275 | 275 | [7 empty] | 2
276 | 276 | [7 empty] | 4
277 | 277 | [7 empty] | 1
278 | 278 | [7 empty] | 2
279 | 279 | [7 empty] | 4
280 | 280 | [7 empty] | 1
281 | 281 | [7 empty] | 3
282 | 282 | [7 empty] | 1
283 | 283 | [7 empty] | 1
284 | 284 | [7 empty] | 1
285 | 285 | [7 empty] | 2
286 | 286 | [7 empty] | 1
287 | 287 | [7 empty] | 1
288 | 288 | [7 empty] | 2
289 | 289 | [7 empty] | 4
290 | 290 | [7 empty] | 4
291 | 291 | [7 empty] | 1
292 | 292 | [7 empty] | 3
293 | 293 | [7 empty] | 1
294 | 294 | [7 empty] | 1
295 | 295 | [7 empty] | 2
296 | 296 | [7 empty] | 3
297 | 297 | [7 empty] | 1
298 | 298 | [7 empty] | 2
299 | 299 | [7 empty] | 1
300 | 300 | [7 empty] | 3
301 | 301 | [7 empty] | 3
302 | 302 | [7 empty] | 4
303 | 303 | [7 empty] | 2
304 | 304 | [7 empty] | 1
305 | 305 | [7 empty] | 1
306 | 306 | [7 empty] | 1
307 | 307 | [7 empty] | 4
308 | 308 | [7 empty] | 1
309 | 309 | [7 empty] | 1
310 | 310 | [7 empty] | 3
311 | 311 | [7 empty] | 2
312 | 312 | [7 empty] | 2
313 | 313 | [7 empty] | 2
314 | 314 | [7 empty] | 4
315 | 315 | [7 empty] | 1
316 | 316 | [7 empty] | 3
317 | 317 | [7 empty] | 1
318 | 318 | [7 empty] | 2
319 | 319 | [7 empty] | 3
320 | 320 | [7 empty] | 1
321 | 321 | [7 empty] | 1
322 | 322 | [7 empty] | 3
323 | 323 | [7 empty] | 2
324 | 324 | [7 empty] | 4
325 | 325 | [7 empty] | 1
326 | 326 | [7 empty] | 1
327 | 327 | [7 empty] | 2
328 | 328 | [7 empty] | 1
329 | 329 | [7 empty] | 1
330 | 330 | [7 empty] | 2
331 | 331 | [7 empty] | 3
332 | 332
333 | 333 | [7 empty] | 4
334 | 334 | [7 empty] | 2
335 | 335 | [7 empty] | 1
336 | 336 | [7 empty] | 3
337 | 337 | [7 empty] | 3
338 | 338 | [7 empty] | 1
339 | 339 | [7 empty] | 4
340 | 340 | [7 empty] | C
341 | 341 | [7 empty] | 1
342 | 342 | [7 empty] | 2
343 | 343 | [7 empty] | 1
344 | 344 | [7 empty] | 4
345 | 345 | [7 empty] | C
346 | 346 | [7 empty] | 1
347 | 347 | [7 empty] | 3
348 | 348 | [7 empty] | 1
349 | 349 | [7 empty] | 1
350 | 350 | [7 empty] | 3
351 | 351 | [7 empty] | 3
352 | 352 | [7 empty] | 1
353 | 353 | [7 empty] | 4
354 | 354 | [7 empty] | 1
355 | 355 | [7 empty] | 1
356 | 356 | [7 empty] | C
357 | 357 | [7 empty] | 2
358 | 358 | [7 empty] | 2
359 | 359 | [7 empty] | 3
360 | 360 | [7 empty] | 1
361 | 361 | [7 empty] | C
362 | 362 | [7 empty] | 1
363 | 363 | [7 empty] | 3
364 | 364 | [7 empty] | C
365 | 365 | [7 empty] | 1
366 | 366 | [7 empty] | 4
367 | 367 | [7 empty] | 4
368 | 368 | [7 empty] | 1
369 | 369 | [7 empty] | C
370 | 370 | [7 empty] | 1
371 | 371 | [7 empty] | 2
372 | 372 | [7 empty] | 1
373 | 373 | [7 empty] | 1
374 | 374 | [7 empty] | 1
375 | 375 | [7 empty] | C
376 | 376 | [7 empty] | 3
377 | 377 | [7 empty] | 1
378 | 378 | [7 empty] | 1
379 | 379 | [7 empty] | 2
380 | 380 | [7 empty] | 1
381 | 381 | [7 empty] | 1
382 | 382 | [7 empty] | 1
383 | 383 | [7 empty] | C
384 | 384 | [7 empty] | 1
385 | 385 | [7 empty] | 2
386 | 386 | [7 empty] | 1
387 | 387 | [7 empty] | 1
388 | 388 | [7 empty] | 1
389 | 389 | [7 empty] | 1
390 | 390 | [7 empty] | 10
391 | 391 | [7 empty] | 1
392 | 392 | [7 empty] | 1
393 | 393 | [7 empty] | 2
394 | 394 | [7 empty] | 2
395 | 395 | [7 empty] | 1
396 | 396 | [7 empty] | 2
397 | 397 | [7 empty] | 1
398 | 398 | [7 empty] | 1
399 | 399 | [7 empty] | 1
400 | 400 | [7 empty] | 2
401 | 401 | [7 empty] | 2
402 | 402 | [7 empty] | 1
403 | 403 | [7 empty] | 1
404 | 404 | [7 empty] | 2
405 | 405 | [7 empty] | 1
406 | 406 | [7 empty] | 1
407 | 407 | [7 empty] | 1
408 | 408 | [7 empty] | 2
409 | 409 | [7 empty] | 2
410 | 410 | [7 empty] | 1
411 | 411 | [7 empty] | 1
412 | 412 | [7 empty] | 2
413 | 413 | [7 empty] | 2
414 | 414 | [7 empty] | C
415 | 415 | [7 empty] | 1
416 | 416 | [7 empty] | 1
417 | 417 | [7 empty] | C
418 | 418 | [7 empty] | 4
419 | 419 | [7 empty] | 2
420 | 420 | [7 empty] | 1
421 | 421 | [7 empty] | 2
422 | 422 | [7 empty] | 3
423 | 423 | [7 empty] | 1
424 | 424 | [7 empty] | 1
425 | 425 | [7 empty] | 1
426 | 426 | [7 empty] | 3
427 | 427 | [7 empty] | 2
428 | 428 | [7 empty] | 1
429 | 429 | [7 empty] | C
430 | 430 | [7 empty] | C
431 | 431 | [7 empty] | 2
432 | 432 | [7 empty] | 3
433 | 433 | [7 empty] | 1
434 | 434 | [7 empty] | 3
435 | 435 | [7 empty] | 1
436 | 436 | [7 empty] | 1
437 | 437 | [7 empty] | 2
438 | 438 | [7 empty] | 1
439 | 439 | [7 empty] | 1
440 | 440 | [7 empty] | 1
441 | 441 | [7 empty] | 2
442 | 442 | [7 empty] | 1
443 | 443 | [7 empty] | 1
444 | 444 | [7 empty] | 3
445 | 445 | [7 empty] | 1
446 | 446 | [7 empty] | 2
447 | 447 | [7 empty] | 1
448 | 448 | [7 empty] | 1
449 | 449 | [7 empty] | 1
450 | 450 | [7 empty] | 1
451 | 451 | [7 empty] | 2
452 | 452 | [7 empty] | 2
453 | 453 | [7 empty] | 1
454 | 454 | [7 empty] | 2
455 | 455 | [7 empty] | C
456 | 456 | [7 empty] | 1
457 | 457 | [7 empty] | 3
458 | 458 | [7 empty] | 1
459 | 459 | [7 empty] | 1
460 | 460 | [7 empty] | 2
461 | 461 | [7 empty] | C
462 | 462 | [7 empty] | 3
463 | 463 | [7 empty] | 3
464 | 464 | [7 empty] | C
465 | 465 | [7 empty] | 1
466 | 466 | [7 empty] | 3
467 | 467 | [7 empty] | 2
468 | 468 | [7 empty] | 3
469 | 469 | [7 empty] | 1
470 | 470 | [7 empty] | 1
471 | 471 | [7 empty] | 2
472 | 472 | [7 empty] | 3
473 | 473 | [7 empty] | 1
474 | 474 | [7 empty] | 2
475 | 475 | [7 empty] | 3
476 | 476 | [7 empty] | 1
477 | 477 | [7 empty] | 2
478 | 478 | [7 empty] | C
479 | 479 | [7 empty] | 3
480 | 480 | [7 empty] | 1
481 | 481 | [7 empty] | 1
482 | 482 | [7 empty] | 1
483 | 483 | [7 empty] | 2
484 | 484 | [7 empty] | 1
485 | 485 | [7 empty] | 2
486 | 486 | [7 empty] | 1
487 | 487 | [7 empty] | 1
488 | 488 | [7 empty] | 1
489 | 489 | [7 empty] | 1
490 | 490 | [7 empty] | 3
491 | 491 | [7 empty] | 3
492 | 492 | [7 empty] | 2
493 | 493 | [7 empty] | 1
494 | 494 | [7 empty] | 1
495 | 495 | [7 empty] | 3
496 | 496 | [7 empty] | 1
497 | 497 | [7 empty] | 1
498 | 498 | [7 empty] | 2
499 | 499 | [7 empty] | 2
500 | 500 | [7 empty] | 1
501 | 501 | [7 empty] | 1
502 | 502 | [7 empty] | 3
503 | 503 | [7 empty] | 2
504 | 504 | [7 empty] | 3
505 | 505 | [7 empty] | 1
506 | 506 | [7 empty] | 1
507 | 507 | [7 empty] | 2
508 | 508 | [7 empty] | 3
509 | 509 | [7 empty] | 1
510 | 510 | [7 empty] | 4
511 | 511 | [7 empty] | 2
512 | 512 | [7 empty] | 1
513 | 513 | [7 empty] | 2
514 | 514 | [7 empty] | 3
515 | 515 | [7 empty] | 1
516 | 516 | [7 empty] | 1
517 | 517 | [7 empty] | 1
518 | 518 | [7 empty] | 3
519 | 519 | [7 empty] | 2
520 | 520 | [7 empty] | 1
521 | 521 | [7 empty] | C
522 | 522 | [7 empty] | C
523 | 523 | [7 empty] | 2
524 | 524 | [7 empty] | 3
525 | 525 | [7 empty] | 1
526 | 526 | [7 empty] | 1
527 | 527 | [7 empty] | 2
528 | 528 | [7 empty] | 4
529 | 529 | [7 empty] | 2
530 | 530 | [7 empty] | 1
531 | 531 | [7 empty] | 2
532 | 532 | [7 empty] | 1
533 | 533 | [7 empty] | 1
534 | 534 | [7 empty] | 1
535 | 535 | [7 empty] | 2
536 | 536 | [7 empty] | 4
537 | 537 | [7 empty] | C
538 | 538 | [7 empty] | C
539 | 539 | [7 empty] | 1
540 | 540 | [7 empty] | 1
541 | 541 | [7 empty] | 1
542 | 542 | [7 empty] | 1
543 | 543 | [7 empty] | C
544 | 544 | [7 empty] | C
545 | 545 | [7 empty] | 1
546 | 546 | [7 empty] | 1
547 | 547 | [7 empty] | 1
548 | 548 | [7 empty] | 3
549 | 549 | [7 empty] | C
550 | 550 | [7 empty] | C
551 | 551 | [7 empty] | 1
552 | 552 | [7 empty] | 2
553 | 553 | [7 empty] | 4
554 | 554 | [7 empty] | 3
555 | 555 | [7 empty] | 4
556 | 556 | [7 empty] | 2
557 | 557 | [7 empty] | 1
558 | 558 | [7 empty] | 2
559 | 559 | [7 empty] | 3
560 | 560 | [7 empty] | 1
561 | 561 | [7 empty] | 1
562 | 562 | [7 empty] | 2
563 | 563 | [7 empty] | 2
564 | 564 | [7 empty] | 1
565 | 565 | [7 empty] | 1
566 | 566 | [7 empty] | 3
567 | 567 | [7 empty] | 2
568 | 568 | [7 empty] | 3
569 | 569 | [7 empty] | 1
570 | 570 | [7 empty] | 1
571 | 571 | [7 empty] | 2
572 | 572 | [7 empty] | 3
573 | 573 | [7 empty] | 1
574 | 574 | [7 empty] | 4
575 | 575 | [7 empty] | 2
576 | 576 | [7 empty] | 1
577 | 577 | [7 empty] | 2
578 | 578 | [7 empty] | 3
579 | 579 | [7 empty] | 1
580 | 580 | [7 empty] | 1
581 | 581 | [7 empty] | 1
582 | 582 | [7 empty] | 3
583 | 583 | [7 empty] | 2
584 | 584 | [7 empty] | 1
585 | 585 | [7 empty] | C
586 | 586 | [7 empty] | C
587 | 587 | [7 empty] | 1
588 | 588 | [7 empty] | 1
589 | 589 | [7 empty] | 1
590 | 590 | [7 empty] | 2
591 | 591 | [7 empty] | 2
592 | 592 | [7 empty] | 1
593 | 593 | [7 empty] | 1
594 | 594 | [7 empty] | 2
595 | 595 | [7 empty] | 1
596 | 596 | [7 empty] | 1
597 | 597 | [7 empty] | 1
598 | 598 | [7 empty] | 2
599 | 599 | [7 empty] | 2
600 | 600 | [7 empty] | 1
601 | 601 | [7 empty] | 1
602 | 602 | [7 empty] | 2
603 | 603 | [7 empty] | 4
604 | 604 | [7 empty] | 2
605 | 605 | [7 empty] | 1
606 | 606 | [7 empty] | 2
607 | 607 | [7 empty] | 1
608 | 608 | [7 empty] | 1
609 | 609 | [7 empty] | 1
610 | 610 | [7 empty] | 2
611 | 611 | [7 empty] | 4
612 | 612 | [7 empty] | C
613 | 613 | [7 empty] | C
614 | 614 | [7 empty] | 1
615 | 615 | [7 empty] | 2
616 | 616 | [7 empty] | 4
617 | 617 | [7 empty] | 3
618 | 618 | [7 empty] | 4
619 | 619 | [7 empty] | 2
620 | 620 | [7 empty] | 1
621 | 621 | [7 empty] | 2
622 | 622 | [7 empty] | 3
623 | 623 | [7 empty] | 1
624 | 624 | [7 empty] | 1
625 | 625 | [7 empty] | 2
626 | 626 | [7 empty] | 2
627 | 627 | [7 empty] | 1
628 | 628 | [7 empty] | 1
629 | 629 | [7 empty] | 3
630 | 630 | [7 empty] | 2
631 | 631 | [7 empty] | 3
632 | 632 | [7 empty] | 1
633 | 633 | [7 empty] | 1
634 | 634 | [7 empty] | 2
635 | 635 | [7 empty] | 3
636 | 636 | [7 empty] | 1
637 | 637 | [7 empty] | 4
638 | 638 | [7 empty] | 2
639 | 639 | [7 empty] | 1
640 | 640 | [7 empty] | 2
641 | 641 | [7 empty] | 3
642 | 642 | [7 empty] | 1
643 | 643 | [7 empty] | 1
644 | 644 | [7 empty] | 1
645 | 645 | [7 empty] | 1
646 | 646 | [7 empty] | 1
647 | 647 | [7 empty] | 1
648 | 648 | [7 empty] | C
649 | 649 | [7 empty] | C
650 | 650 | [7 empty] | 1
651 | 651 | [7 empty] | 1
652 | 652 | [7 empty] | 1
653 | 653 | [7 empty] | 2
654 | 654 | [7 empty] | 2
655 | 655 | [7 empty] | 1
656 | 656 | [7 empty] | 1
657 | 657 | [7 empty] | 2
658 | 658 | [7 empty] | 1
659 | 659 | [7 empty] | 1
660 | 660 | [7 empty] | 1
661 | 661 | [7 empty] | 2
662 | 662 | [7 empty] | 2
663 | 663 | [7 empty] | 1
664 | 664 | [7 empty] | 1
665 | 665 | [7 empty] | 1
666 | 666 | [7 empty] | 2
667 | 667 | [7 empty] | 2
668 | 668 | [7 empty] | 1
669 | 669 | [7 empty] | 1
670 | 670 | [7 empty] | 3
671 | 671 | [7 empty] | 2
672 | 672 | [7 empty] | 3
673 | 673 | [7 empty] | 1
674 | 674 | [7 empty] | 1
675 | 675 | [7 empty] | 2
676 | 676 | [7 empty] | 3
677 | 677 | [7 empty] | 1
678 | 678 | [7 empty] | 4
679 | 679 | [7 empty] | 2
680 | 680 | [7 empty] | 1
681 | 681 | [7 empty] | 2
682 | 682 | [7 empty] | 3
683 | 683 | [7 empty] | 1
684 | 684 | [7 empty] | 1
685 | 685 | [7 empty] | 1
686 | 686 | [7 empty] | 3
687 | 687 | [7 empty] | 2
688 | 688 | [7 empty] | 4
689 | 689 | [7 empty] | 4
690 | 690 | [7 empty] | 4
691 | 691 | [7 empty] | 4
692 | 692 | [7 empty] | 1
693 | 693 | [7 empty] | 1
694 | 694 | [7 empty] | 2
695 | 695 | [7 empty] | 2
696 | 696 | [7 empty] | 1
697 | 697 | [7 empty] | 1
698 | 698 | [7 empty] | 2
699 | 699 | [7 empty] | 1
700 | 700 | [7 empty] | 1
701 | 701 | [7 empty] | 1
702 | 702 | [7 empty] | 2
703 | 703 | [7 empty] | 2
704 | 704 | [7 empty] | 1
705 | 705 | [7 empty] | 1
706 | 706 | [7 empty] | 2
707 | 707 | [7 empty] | 4
708 | 708 | [7 empty] | 2
709 | 709 | [7 empty] | 1
710 | 710 | [7 empty] | 2
711 | 711 | [7 empty] | 1
712 | 712 | [7 empty] | 1
713 | 713 | [7 empty] | 1
714 | 714 | [7 empty] | 2
715 | 715 | [7 empty] | 2
716 | 716 | [7 empty] | 3
717 | 717 | [7 empty] | 1
718 | 718 | [7 empty] | 1
719 | 719 | [7 empty] | 1
720 | 720 | [7 empty] | 3
721 | 721 | [7 empty] | 2
722 | 722 | [7 empty] | 2
723 | 723 | [7 empty] | 3
724 | 724 | [7 empty] | 1
725 | 725 | [7 empty] | 1
726 | 726 | [7 empty] | 1
727 | 727 | [7 empty] | 3
728 | 728 | [7 empty] | 2
729 | 729 | [7 empty] | 1
730 | 730 | [7 empty] | C
731 | 731 | [7 empty] | C
732 | 732 | [7 empty] | 2
733 | 733 | [7 empty] | 3
734 | 734 | [7 empty] | 1
735 | 735 | [7 empty] | 3
736 | 736 | [7 empty] | 1
737 | 737 | [7 empty] | 1
738 | 738 | [7 empty] | 2
739 | 739 | [7 empty] | 1
740 | 740 | [7 empty] | 1
741 | 741 | [7 empty] | 1
742 | 742 | [7 empty] | 2
743 | 743 | [7 empty] | 1
744 | 744 | [7 empty] | 1
745 | 745 | [7 empty] | 3
746 | 746 | [7 empty] | 1
747 | 747 | [7 empty] | 2
748 | 748 | [7 empty] | 1
749 | 749 | [7 empty] | 1
750 | 750 | [7 empty] | 1
751 | 751 | [7 empty] | 1
752 | 752 | [7 empty] | 2
753 | 753 | [7 empty] | 2
754 | 754 | [7 empty] | 1
755 | 755 | [7 empty] | 2
756 | 756 | [7 empty] | C
757 | 757 | [7 empty] | 1
758 | 758 | [7 empty] | 3
759 | 759 | [7 empty] | 1
760 | 760 | [7 empty] | 1
761 | 761 | [7 empty] | 2
762 | 762 | [7 empty] | 1
763 | 763 | [7 empty] | 1
764 | 764 | [7 empty] | 2
765 | 765 | [7 empty] | 2
766 | 766 | [7 empty] | 1
767 | 767 | [7 empty] | 1
768 | 768 | [7 empty] | 2
769 | 769 | [7 empty] | 1
770 | 770 | [7 empty] | 1
771 | 771 | [7 empty] | 1
772 | 772 | [7 empty] | 2
773 | 773 | [7 empty] | 2
774 | 774 | [7 empty] | 1
775 | 775 | [7 empty] | 1
776 | 776 | [7 empty] | 2
777 | 777 | [7 empty] | 4
778 | 778 | [7 empty] | 2
779 | 779 | [7 empty] | 1
780 | 780 | [7 empty] | 2
781 | 781 | [7 empty] | 1
782 | 782 | [7 empty] | 1
783 | 783 | [7 empty] | 1
784 | 784 | [7 empty] | 2
785 | 785 | [7 empty] | 2
786 | 786 | [7 empty] | 3
787 | 787 | [7 empty] | 1
788 | 788 | [7 empty] | 1
789 | 789 | [7 empty] | 1
790 | 790 | [7 empty] | 3
791 | 791 | [7 empty] | 2
792 | 792 | [7 empty] | 2
793 | 793 | [7 empty] | C
794 | 794 | [7 empty] | C
795 | 795 | [7 empty] | 1
796 | 796 | [7 empty] | 1
797 | 797 | [7 empty] | 1
798 | 798 | [7 empty] | 2
799 | 799 | [7 empty] | 2
800 | 800 | [7 empty] | 1
801 | 801 | [7 empty] | 1
802 | 802 | [7 empty] | 2
803 | 803 | [7 empty] | 1
804 | 804 | [7 empty] | 1
805 | 805 | [7 empty] | 1
806 | 806 | [7 empty] | 2
807 | 807 | [7 empty] | 2
808 | 808 | [7 empty] | 1
809 | 809 | [7 empty] | 1
810 | 810 | [7 empty] | 2
811 | 811 | [7 empty] | 4
812 | 812 | [7 empty] | 2
813 | 813 | [7 empty] | 1
814 | 814 | [7 empty] | 2
815 | 815 | [7 empty] | 1
816 | 816 | [7 empty] | 1
817 | 817 | [7 empty] | 1
818 | 818 | [7 empty] | 2
819 | 819 | [7 empty] | 4
820 | 820 | [7 empty] | C
821 | 821 | [7 empty] | C
822 | 822 | [7 empty] | 1
823 | 823 | [7 empty] | 2
824 | 824 | [7 empty] | 4
825 | 825 | [7 empty] | 3
826 | 826 | [7 empty] | 4
827 | 827 | [7 empty] | 2
828 | 828 | [7 empty] | 1
829 | 829 | [7 empty] | 2
830 | 830 | [7 empty] | 1
831 | 831 | [7 empty] | 1
832 | 832 | [7 empty] | 1
833 | 833 | [7 empty] | 3
834 | 834 | [7 empty] | 2
835 | 835 | [7 empty] | 2
836 | 836 | [7 empty] | 3
837 | 837 | [7 empty] | 1
838 | 838 | [7 empty] | 1
839 | 839 | [7 empty] | 1
840 | 840 | [7 empty] | 3
841 | 841 | [7 empty] | 2
842 | 842 | [7 empty] | 1
843 | 843 | [7 empty] | C
844 | 844 | [7 empty] | C
845 | 845 | [7 empty] | 2
846 | 846 | [7 empty] | 3
847 | 847 | [7 empty] | 1
848 | 848 | [7 empty] | 3
849 | 849 | [7 empty] | 1
850 | 850 | [7 empty] | 1
851 | 851 | [7 empty] | 2
852 | 852 | [7 empty] | 1
853 | 853 | [7 empty] | 1
854 | 854 | [7 empty] | 1
855 | 855 | [7 empty] | 2
856 | 856 | [7 empty] | 2
857 | 857 | [7 empty] | 1
858 | 858 | [7 empty] | 1
859 | 859 | [7 empty] | 2
860 | 860 | [7 empty] | 1
861 | 861 | [7 empty] | 1
862 | 862 | [7 empty] | 1
863 | 863 | [7 empty] | 2
864 | 864 | [7 empty] | C
865 | 865 | [7 empty] | 1
866 | 866 | [7 empty] | 1
867 | 867 | [7 empty] | 2
868 | 868 | [7 empty] | 4
869 | 869 | [7 empty] | 2
870 | 870 | [7 empty] | 1
871 | 871 | [7 empty] | 2
872 | 872 | [7 empty] | 1
873 | 873 | [7 empty] | 1
874 | 874 | [7 empty] | 1
875 | 875 | [7 empty] | 2
876 | 876 | [7 empty] | 2
877 | 877 | [7 empty] | 3
878 | 878 | [7 empty] | 1
879 | 879 | [7 empty] | 1
880 | 880 | [7 empty] | 1
881 | 881 | [7 empty] | 3
882 | 882 | [7 empty] | 2
883 | 883 | [7 empty] | 2
884 | 884 | [7 empty] | 3
885 | 885 | [7 empty] | 1
886 | 886 | [7 empty] | 1
887 | 887 | [7 empty] | 1
888 | 888 | [7 empty] | 2
889 | 889 | [7 empty] | C
890 | 890 | [7 empty] | 1
891 | 891 | [7 empty] | 3
892 | 892 | [7 empty] | 1
893 | 893 | [7 empty] | 1
894 | 894 | [7 empty] | 2
895 | 895 | [7 empty] | C
896 | 896 | [7 empty] | 3
897 | 897 | [7 empty] | 3
898 | 898 | [7 empty] | C
899 | 899 | [7 empty] | 1
900 | 900 | [7 empty] | 3
901 | 901 | [7 empty] | 2
902 | 902 | [7 empty] | 3
903 | 903 | [7 empty] | 1
904 | 904 | [7 empty] | 1
905 | 905 | [7 empty] | 2
906 | 906 | [7 empty] | 3
907 | 907 | [7 empty] | 1
908 | 908 | [7 empty] | 2
909 | 909 | [7 empty] | 3
910 | 910 | [7 empty] | 1
911 | 911 | [7 empty] | 2
912 | 912 | [7 empty] | C
913 | 913 | [7 empty] | 3
914 | 914 | [7 empty] | 1
915 | 915 | [7 empty] | 1
916 | 916 | [7 empty] | 1
917 | 917 | [7 empty] | 2
918 | 918 | [7 empty] | 1
919 | 919 | [7 empty] | 2
920 | 920 | [7 empty] | 1
921 | 921 | [7 empty] | 1
922 | 922 | [7 empty] | 1
923 | 923 | [7 empty] | 1
924 | 924 | [7 empty] | 3
925 | 925 | [7 empty] | 3
926 | 926 | [7 empty] | 2
927 | 927 | [7 empty] | 1
928 | 928 | [7 empty] | 1
929 | 929 | [7 empty] | 3
930 | 930 | [7 empty] | 1
931 | 931 | [7 empty] | 1
932 | 932 | [7 empty] | 2
933 | 933 | [7 empty] | 2
934 | 934 | [7 empty] | 1
935 | 935 | [7 empty] | 1
936 | 936 | [7 empty] | 3
937 | 937 | [7 empty] | 2
938 | 938 | [7 empty] | 3
939 | 939 | [7 empty] | 1
940 | 940 | [7 empty] | 1
941 | 941 | [7 empty] | 2
942 | 942 | [7 empty] | 3
943 | 943 | [7 empty] | 1
944 | 944 | [7 empty] | 4
945 | 945 | [7 empty] | 2
946 | 946 | [7 empty] | 1
947 | 947 | [7 empty] | 2
948 | 948 | [7 empty] | 3
949 | 949 | [7 empty] | 1
950 | 950 | [7 empty] | 1
951 | 951 | [7 empty] | 1
952 | 952 | [7 empty] | 3
953 | 953 | [7 empty] | 2
954 | 954 | [7 empty] | 1
955 | 955 | [7 empty] | C
956 | 956 | [7 empty] | C
957 | 957 | [7 empty] | 2
958 | 958 | [7 empty] | 3
959 | 959 | [7 empty] | 1
960 | 960 | [7 empty] | 1
961 | 961 | [7 empty] | 2
962 | 962 | [7 empty] | 4
963 | 963 | [7 empty] | 2
964 | 964 | [7 empty] | 1
965 | 965 | [7 empty] | 2
966 | 966 | [7 empty] | C
967 | 967 | [7 empty] | 1
968 | 968 | [7 empty] | 1
969 | 969 | [7 empty] | 2
970 | 970 | [7 empty] | 4
971 | 971 | [7 empty] | 2
972 | 972 | [7 empty] | 1
973 | 973 | [7 empty] | 2
974 | 974 | [7 empty] | 1
975 | 975 | [7 empty] | 1
976 | 976 | [7 empty] | 1
977 | 977 | [7 empty] | 2
978 | 978 | [7 empty] | 2
979 | 979 | [7 empty] | 3
980 | 980 | [7 empty] | 1
981 | 981 | [7 empty] | 1
982 | 982 | [7 empty] | 1
983 | 983 | [7 empty] | 3
984 | 984 | [7 empty] | 2
985 | 985 | [7 empty] | 2
986 | 986 | [7 empty] | 3
987 | 987 | [7 empty] | 1
988 | 988 | [7 empty] | 1
989 | 989 | [7 empty] | 1
990 | 990 | [7 empty] | 2
991 | 991 | [7 empty] | C
992 | 992 | [7 empty] | 1
993 | 993 | [7 empty] | 3
994 | 994 | [7 empty] | 1
995 | 995 | [7 empty] | 1
996 | 996 | [7 empty] | 2
997 | 997 | [7 empty] | C
998 | 998 | [7 empty] | 3
999 | 999 | [7 empty] | 3
1000 | 1000 | [7 empty] | C
1001 | 1001 | [7 empty] | 1
1002 | 1002 | [7 empty] | 3
1003 | 1003 | [7 empty] | 2
1004 | 1004 | [7 empty] | 3
1005 | 1005 | [7 empty] | 1
1006 | 1006 | [7 empty] | 1
1007 | 1007 | [7 empty] | 3
1008 | 1008 | [7 empty] | 2
1009 | 1009 | [7 empty] | 3
1010 | 1010 | [7 empty] | 1
1011 | 1011 | [7 empty] | 1
1012 | 1012 | [7 empty] | 2
1013 | 1013 | [7 empty] | 3
1014 | 1014 | [7 empty] | 1
1015 | 1015 | [7 empty] | 4
1016 | 1016 | [7 empty] | 2
1017 | 1017 | [7 empty] | 1
1018 | 1018 | [7 empty] | 2
1019 | 1019 | [7 empty] | 3
1020 | 1020 | [7 empty] | 1
1021 | 1021 | [7 empty] | 1
1022 | 1022 | [7 empty] | 1
1023 | 1023 | [7 empty] | 3
1024 | 1024 | [7 empty] | 2
1025 | 1025 | [7 empty] | 1
1026 | 1026 | [7 empty] | 1
1027 | 1027 | [7 empty] | 1
1028 | 1028 | [7 empty] | 2
1029 | 1029 | [7 empty] | 3
1030 | 1030 | [7 empty] | 1
1031 | 1031 | [7 empty] | 1
1032 | 1032 | [7 empty] | 2
1033 | 1033 | [7 empty] | 4
1034 | 1034 | [7 empty] | 2
1035 | 1035 | [7 empty] | 1
1036 | 1036 | [7 empty] | 2
1037 | 1037 | [7 empty] | 2
1038 | 1038 | [7 empty] | 1
1039 | 1039 | [7 empty] | 1
1040 | 1040 | [7 empty] | 2
1041 | 1041 | [7 empty] | 3
1042 | 1042 | [7 empty] | 1
1043 | 1043 | [7 empty] | 1
1044 | 1044 | [7 empty] | 1
1045 | 1045 | [7 empty] | 3
1046 | 1046 | [7 empty] | 2
1047 | 1047 | [7 empty] | 1
1048 | 1048 | [7 empty] | 2
1049 | 1049 | [7 empty] | 4
1050 | 1050 | [7 empty] | 2
1051 | 1051 | [7 empty] | 3
1052 | 1052 | [7 empty] | 1
1053 | 1053 | [7 empty] | 1
1054 | 1054 | [7 empty] | 2
1055 | 1055 | [7 empty] | 4
1056 | 1056 | [7 empty] | 2
1057 | 1057 | [7 empty] | 1
1058 | 1058 | [7 empty] | 2
1059 | 1059 | [7 empty] | 3
1060 | 1060 | [7 empty] | 1
1061 | 1061 | [7 empty] | 4
1062 | 1062 | [7 empty] | 4
1063 | 1063 | [7 empty] | 4
1064 | 1064 | [7 empty] | 3
1065 | 1065 | [7 empty] | 1
1066 | 1066 | [7 empty] | 1
1067 | 1067 | [7 empty] | 1
1068 | 1068 | [7 empty] | 3
1069 | 1069 | [7 empty] | 2
1070 | 1070 | [7 empty] | 1
1071 | 1071 | [7 empty] | 2
1072 | 1072 | [7 empty] | 4
1073 | 1073 | [7 empty] | 2
1074 | 1074 | [7 empty] | 3
1075 | 1075 | [7 empty] | 1
1076 | 1076 | [7 empty] | 1
1077 | 1077 | [7 empty] | 2
1078 | 1078 | [7 empty] | 4
1079 | 1079 | [7 empty] | 2
1080 | 1080 | [7 empty] | 1
1081 | 1081 | [7 empty] | 2
1082 | 1082 | [7 empty] | W
1083 | 1083 | [7 empty] | 2
1084 | 1084 | [7 empty] | 1
1085 | 1085 | [7 empty] | 1
1086 | 1086 | [7 empty] | 2
1087 | 1087 | [7 empty] | 1
1088 | 1088 | [7 empty] | 1
1089 | 1089 | [7 empty] | 1
1090 | 1090 | [7 empty] | 2
1091 | 1091 | [7 empty] | 1
1092 | 1092 | [7 empty] | 1
1093 | 1093 | [7 empty] | 1
1094 | 1094 | [7 empty] | 2
1095 | 1095 | [7 empty] | 4
1096 | 1096 | [7 empty] | 1
1097 | 1097 | [7 empty] | 1
1098 | 1098 | [7 empty] | 2
1099 | 1099 | [7 empty] | 1
1100 | 1100 | [7 empty] | 1
1101 | 1101 | [7 empty] | 1
1102 | 1102 | [7 empty] | 2
1103 | 1103 | [7 empty] | 2
1104 | 1104 | [7 empty] | 3
1105 | 1105 | [7 empty] | 1
1106 | 1106 | [7 empty] | 1
1107 | 1107 | [7 empty] | 1
1108 | 1108 | [7 empty] | 3
1109 | 1109 | [7 empty] | 2
1110 | 1110 | [7 empty] | 2
1111 | 1111 | [7 empty] | 2
1112 | 1112 | [7 empty] | 4
1113 | 1113 | [7 empty] | 2
1114 | 1114 | [7 empty] | 1
1115 | 1115 | [7 empty] | 2
1116 | 1116 | [7 empty] | 2
1117 | 1117 | [7 empty] | 1
1118 | 1118 | [7 empty] | 1
1119 | 1119 | [7 empty] | 2
1120 | 1120 | [7 empty] | 3
1121 | 1121 | [7 empty] | 1
1122 | 1122 | [7 empty] | 1
1123 | 1123 | [7 empty] | 1
1124 | 1124 | [7 empty] | 3
1125 | 1125 | [7 empty] | 2
1126 | 1126 | [7 empty] | 1
1127 | 1127 | [7 empty] | 2
1128 | 1128 | [7 empty] | 4
1129 | 1129 | [7 empty] | 2
1130 | 1130 | [7 empty] | 3
1131 | 1131 | [7 empty] | 1
1132 | 1132 | [7 empty] | 1
1133 | 1133 | [7 empty] | 2
1134 | 1134 | [7 empty] | 4
1135 | 1135 | [7 empty] | 2
1136 | 1136 | [7 empty] | 1
1137 | 1137 | [7 empty] | 2
1138 | 1138 | [7 empty] | 3
1139 | 1139 | [7 empty] | 3
1140 | 1140 | [7 empty] | 1
1141 | 1141 | [7 empty] | 1
1142 | 1142 | [7 empty] | 1
1143 | 1143 | [7 empty] | 3
1144 | 1144 | [7 empty] | 2
1145 | 1145 | [7 empty] | 1
1146 | 1146 | [7 empty] | 2
1147 | 1147 | [7 empty] | 4
1148 | 1148 | [7 empty] | 2
1149 | 1149 | [7 empty] | 3
1150 | 1150 | [7 empty] | 1
1151 | 1151 | [7 empty] | 1
1152 | 1152 | [7 empty] | 2
1153 | 1153 | [7 empty] | 4
1154 | 1154 | [7 empty] | 2
1155 | 1155 | [7 empty] | 1
1156 | 1156 | [7 empty] | 2
1157 | 1157 | [7 empty] | W
1158 | 1158 | [7 empty] | 2
1159 | 1159 | [7 empty] | 1
1160 | 1160 | [7 empty] | 1
1161 | 1161 | [7 empty] | 2
1162 | 1162 | [7 empty] | 1
1163 | 1163 | [7 empty] | 1
1164 | 1164 | [7 empty] | 1
1165 | 1165 | [7 empty] | 2
1166 | 1166 | [7 empty] | 1
1167 | 1167 | [7 empty] | 1
1168 | 1168 | [7 empty] | 1
1169 | 1169 | [7 empty] | 2
1170 | 1170 | [7 empty] | 4
1171 | 1171 | [7 empty] | 1
1172 | 1172 | [7 empty] | 1
1173 | 1173 | [7 empty] | 2
1174 | 1174 | [7 empty] | 1
1175 | 1175 | [7 empty] | 1
1176 | 1176 | [7 empty] | 1
1177 | 1177 | [7 empty] | 2
1178 | 1178 | [7 empty] | 2
1179 | 1179 | [7 empty] | 3
1180 | 1180 | [7 empty] | 1
1181 | 1181 | [7 empty] | 1
1182 | 1182 | [7 empty] | 1
1183 | 1183 | [7 empty] | 3
1184 | 1184 | [7 empty] | 2
1185 | 1185 | [7 empty] | 2
1186 | 1186 | [7 empty] | 1
1187 | 1187 | [7 empty] | 1
1188 | 1188 | [7 empty] | 1
1189 | 1189 | [7 empty] | 2
1190 | 1190 | [7 empty] | 1
1191 | 1191 | [7 empty] | 1
1192 | 1192 | [7 empty] | 1
1193 | 1193 | [7 empty] | 2
1194 | 1194 | [7 empty] | 4
1195 | 1195 | [7 empty] | 1
1196 | 1196 | [7 empty] | 1
1197 | 1197 | [7 empty] | 2
1198 | 1198 | [7 empty] | 1
1199 | 1199 | [7 empty] | 1
1200 | 1200 | [7 empty] | 1
1201 | 1201 | [7 empty] | 1
1202 | 1202 | [7 empty] | 1
1203 | 1203 | [7 empty] | 3
1204 | 1204 | [7 empty] | 2
1205 | 1205 | [7 empty] | 1
1206 | 1206 | [7 empty] | 2
1207 | 1207 | [7 empty] | 4
1208 | 1208 | [7 empty] | 2
1209 | 1209 | [7 empty] | 3
1210 | 1210 | [7 empty] | 1
1211 | 1211 | [7 empty] | 1
1212 | 1212 | [7 empty] | 1
1213 | 1213 | [7 empty] | 1
1214 | 1214 | [7 empty] | 1
1215 | 1215 | [7 empty] | 4
1216 | 1216 | [7 empty] | 2
1217 | 1217 | [7 empty] | 3
1218 | 1218 | [7 empty] | 1
1219 | 1219 | [7 empty] | 1
1220 | 1220 | [7 empty] | 2
1221 | 1221 | [7 empty] | 4
1222 | 1222 | [7 empty] | 2
1223 | 1223 | [7 empty] | 1
1224 | 1224 | [7 empty] | 2
1225 | 1225 | [7 empty] | 3
1226 | 1226 | [7 empty] | 3
1227 | 1227 | [7 empty] | 1
1228 | 1228 | [7 empty] | 1
1229 | 1229 | [7 empty] | 1
1230 | 1230 | [7 empty] | 3
1231 | 1231 | [7 empty] | 2
1232 | 1232 | [7 empty] | 1
1233 | 1233 | [7 empty] | 2
1234 | 1234 | [7 empty] | C
1235 | 1235 | [7 empty] | 1
1236 | 1236 | [7 empty] | 1
1237 | 1237 | [7 empty] | 2
1238 | 1238 | [7 empty] | 4
1239 | 1239 | [7 empty] | 1
1240 | 1240 | [7 empty] | 1
1241 | 1241 | [7 empty] | 2
1242 | 1242 | [7 empty] | 1
1243 | 1243 | [7 empty] | 1
1244 | 1244 | [7 empty] | 1
1245 | 1245 | [7 empty] | 1
1246 | 1246 | [7 empty] | 1
1247 | 1247 | [7 empty] | 3
1248 | 1248 | [7 empty] | 2
1249 | 1249 | [7 empty] | 1
1250 | 1250 | [7 empty] | 1
1251 | 1251 | [7 empty] | 2
1252 | 1252 | [7 empty] | 4
1253 | 1253 | [7 empty] | 2
1254 | 1254 | [7 empty] | 3
1255 | 1255 | [7 empty] | 1
1256 | 1256 | [7 empty] | 1
1257 | 1257 | [7 empty] | 1
1258 | 1258 | [7 empty] | 1
1259 | 1259 | [7 empty] | 2
1260 | 1260 | [7 empty] | 3
1261 | 1261 | [7 empty] | 3
1262 | 1262 | [7 empty] | 1
1263 | 1263 | [7 empty] | 1
1264 | 1264 | [7 empty] | 1
1265 | 1265 | [7 empty] | 3
1266 | 1266 | [7 empty] | 2
1267 | 1267 | [7 empty] | 1
1268 | 1268 | [7 empty] | 2
1269 | 1269 | [7 empty] | 4
1270 | 1270 | [7 empty] | 2
1271 | 1271 | [7 empty] | 3
1272 | 1272 | [7 empty] | 1
1273 | 1273 | [7 empty] | 1
1274 | 1274 | [7 empty] | 2
1275 | 1275 | [7 empty] | 1
1276 | 1276 | [7 empty] | 1
1277 | 1277 | [7 empty] | 1
1278 | 1278 | [7 empty] | 2
1279 | 1279 | [7 empty] | 4
1280 | 1280 | [7 empty] | 1
1281 | 1281 | [7 empty] | 2
1282 | 1282 | [7 empty] | 1
1283 | 1283 | [7 empty] | 1
1284 | 1284 | [7 empty] | 1
1285 | 1285 | [7 empty] | 2
1286 | 1286 | [7 empty] | 1
1287 | 1287 | [7 empty] | 1
1288 | 1288 | [7 empty] | 1
1289 | 1289 | [7 empty] | 2
1290 | 1290 | [7 empty] | 4
1291 | 1291 | [7 empty] | 1
1292 | 1292 | [7 empty] | 1
1293 | 1293 | [7 empty] | 2
1294 | 1294 | [7 empty] | 1
1295 | 1295 | [7 empty] | 1
1296 | 1296 | [7 empty] | 1
1297 | 1297 | [7 empty] | 3
1298 | 1298 | [7 empty] | 1
1299 | 1299 | [7 empty] | 1
1300 | 1300 | [7 empty] | 1
1301 | 1301 | [7 empty] | 3
1302 | 1302 | [7 empty] | 2
1303 | 1303 | [7 empty] | 1
1304 | 1304 | [7 empty] | 2
1305 | 1305 | [7 empty] | 4
1306 | 1306 | [7 empty] | 2
1307 | 1307 | [7 empty] | 3
1308 | 1308 | [7 empty] | 2
1309 | 1309 | [7 empty] | 1
1310 | 1310 | [7 empty] | 2
1311 | 1311 | [7 empty] | 4
1312 | 1312 | [7 empty] | 2
1313 | 1313 | [7 empty] | 3
1314 | 1314 | [7 empty] | 1
1315 | 1315 | [7 empty] | 1
1316 | 1316 | [7 empty] | 2
1317 | 1317 | [7 empty] | 4
1318 | 1318 | [7 empty] | 2
1319 | 1319 | [7 empty] | 2
1320 | 1320 | [7 empty] | 4
1321 | 1321 | [7 empty] | 1
1322 | 1322 | [7 empty] | 2
1323 | 1323 | [7 empty] | 1
1324 | 1324 | [7 empty] | 1
1325 | 1325 | [7 empty] | 1
1326 | 1326 | [7 empty] | 2
1327 | 1327 | [7 empty] | 1
1328 | 1328 | [7 empty] | 1
1329 | 1329 | [7 empty] | 1
1330 | 1330 | [7 empty] | 2
1331 | 1331 | [7 empty] | 4
1332 | 1332 | [7 empty] | 1
1333 | 1333 | [7 empty] | 1
1334 | 1334 | [7 empty] | 2
1335 | 1335 | [7 empty] | 1
1336 | 1336 | [7 empty] | 1
1337 | 1337 | [7 empty] | 1
1338 | 1338 | [7 empty] | 3
1339 | 1339 | [7 empty] | 1
1340 | 1340 | [7 empty] | 1
1341 | 1341 | [7 empty] | 1
1342 | 1342 | [7 empty] | 3
1343 | 1343 | [7 empty] | 2
1344 | 1344 | [7 empty] | 1
1345 | 1345 | [7 empty] | 2
1346 | 1346 | [7 empty] | 4
1347 | 1347 | [7 empty] | 2
1348 | 1348 | [7 empty] | 3
1349 | 1349 | [7 empty] | 2
1350 | 1350 | [7 empty] | 1
1351 | 1351 | [7 empty] | 2
1352 | 1352 | [7 empty] | 4
1353 | 1353 | [7 empty] | 2
1354 | 1354 | [7 empty] | 3
1355 | 1355 | [7 empty] | 1
1356 | 1356 | [7 empty] | 1
1357 | 1357 | [7 empty] | 2
1358 | 1358 | [7 empty] | 4
1319 | 1319 | [7 empty] | 2
1320 | 1320 | [7 empty] | 4
1321 | 1321 | [7 empty] | 4
1322 | 1322 | [7 empty] | 1
1323 | 1323 | [7 empty] | 1
1324 | 1324 | [7 empty] | 1
1325 | 1325 | [7 empty] | 3
1326 | 1326 | [7 empty] | 2
1327 | 1327 | [7 empty] | 1
1328 | 1328 | [7 empty] | 1
1329 | 1329 | [7 empty] | 2
1330 | 1330 | [7 empty] | 4
1331 | 1331 | [7 empty] | 2
1332 | 1332 | [7 empty] | 3
1333 | 1333 | [7 empty] | 1
1334 | 1334 | [7 empty] | 1
1335 | 1335 | [7 empty] | 1
1336 | 1336 | [7 empty] | 1
1337 | 1337 | [7 empty] | 2
1338 | 1338 | [7 empty] | 3
1339 | 1339 | [7 empty] | 3
1340 | 1340 | [7 empty] | 1
1341 | 1341 | [7 empty] | 1
1342 | 1342 | [7 empty] | 1
1343 | 1343 | [7 empty] | 3
1344 | 1344 | [7 empty] | 2
1345 | 1345 | [7 empty] | 1
1346 | 1346 | [7 empty] | 2
1347 | 1347 | [7 empty] | 4
1348 | 1348 | [7 empty] | 1
1349 | 1349 | [7 empty] | 2
1350 | 1350 | [7 empty] | 1
1351 | 1351 | [7 empty] | 1
1352 | 1352 | [7 empty] | 1
1353 | 1353 | [7 empty] | 3
1354 | 1354 | [7 empty] | 1
1355 | 1355 | [7 empty] | 1
1356 | 1356 | [7 empty] | 1
1357 | 1357 | [7 empty] | 3
1358 | 1358 | [7 empty] | 2
1319 | 1319 | [7 empty] | 1
1320 | 1320 | [7 empty] | 2
1321 | 1321 | [7 empty] | 4
1322 | 1322 | [7 empty] | 2
1323 | 1323 | [7 empty] | 3
1324 | 1324 | [7 empty] | 2
1325 | 1325 | [7 empty] | 1
1326 | 1326 | [7 empty] | 2
1327 | 1327 | [7 empty] | 4
1328 | 1328 | [7 empty] | 2
1329 | 1329 | [7 empty] | 3
1330 | 1330 | [7 empty] | 1
1331 | 1331 | [7 empty] | 1
1332 | 1332 | [7 empty] | 2
1333 | 1333 | [7 empty] | 4
1334 | 1334 | [7 empty] | 2
1335 | 1335 | [7 empty] | 4
1336 | 1336 | [7 empty] | 4
1337 | 1337 | [7 empty] | 1
1338 | 1338 | [7 empty] | 1
1339 | 1339 | [7 empty] | 1
1340 | 1340 | [7 empty] | 3
1341 | 1341 | [7 empty] | 2
1342 | 1342 | [7 empty] | 1
1343 | 1343 | [7 empty] | 1
1344 | 1344 | [7 empty] | 2
1345 | 1345 | [7 empty] | 4
1346 | 1346 | [7 empty] | 2
1347 | 1347 | [7 empty] | 3
1348 | 1348 | [7 empty] | 1
1349 | 1349 | [7 empty] | 1
1350 | 1350 | [7 empty] | 1
1351 | 1351 | [7 empty] | 1
1352 | 1352 | [7 empty] | 2
1353 | 1353 | [7 empty] | 3
1354 | 1354 | [7 empty] | 3
1355 | 1355 | [7 empty] | 1
1356 | 1356 | [7 empty] | 1
1357 | 1357 | [7 empty] | 1
1358 | 1358 | [7 empty] | 3
1319 | 1319 | [7 empty] | 2
1320 | 1320 | [7 empty] | 1
1321 | 1321 | [7 empty] | 2
1322 | 1322 | [7 empty] | 4
1323 | 1323 | [7 empty] | W
1324 | 1324 | [7 empty] | 1
1325 | 1325 | [7 empty] | 1
1326 | 1326 | [7 empty] | 1
1327 | 1327 | [7 empty] | 3
1328 | 1328 | [7 empty] | 2
1329 | 1329 | [7 empty] | 1
1330 | 1330 | [7 empty] | 1
1331 | 1331 | [7 empty] | 2
1332 | 1332 | [7 empty] | 4
1333 | 1333 | [7 empty] | 2
1334 | 1334 | [7 empty] | 3
1335 | 1335 | [7 empty] | 1
1336 | 1336 | [7 empty] | 1
1337 | 1337 | [7 empty] | 1
1338 | 1338 | [7 empty] | 1
1339 | 1339 | [7 empty] | 2
1340 | 1340 | [7 empty] | 3
1341 | 1341 | [7 empty] | 3
1342 | 1342 | [7 empty] | 1
1343 | 1343 | [7 empty] | 1
1344 | 1344 | [7 empty] | 1
1345 | 1345 | [7 empty] | 3
1346 | 1346 | [7 empty] | 2
1347 | 1347 | [7 empty] | 1
1348 | 1348 | [7 empty] | 2
1349 | 1349 | [7 empty] | 4
1350 | 1350 | [7 empty] | 3
1351 | 1351 | [7 empty] | 1
1352 | 1352 | [7 empty] | 1
1353 | 1353 | [7 empty] | 1
1354 | 1354 | [7 empty] | 3
1355 | 1355 | [7 empty] | 2
1356 | 1356 | [7 empty] | 1
1357 | 1357 | [7 empty] | 2
1358 | 1358 | [7 empty] | 4
1359 | 1359 | [7 empty] | 4
1360 | 1360 | [7 empty] | 2
1361 | 1361 | [7 empty] | 3
1362 | 1362 | [7 empty] | 2
1363 | 1363 | [7 empty] | 1
1364 | 1364 | [7 empty] | 2
1365 | 1365 | [7 empty] | 4
1366 | 1366 | [7 empty] | 2
1367 | 1367 | [7 empty] | 3
1368 | 1368 | [7 empty] | 1
1369 | 1369 | [7 empty] | 1
1370 | 1370 | [7 empty] | 4
1371 | 1371 | [7 empty] | 4
1372 | 1372 | [7 empty] | 1
1373 | 1373 | [7 empty] | 1
1374 | 1374 | [7 empty] | 1
1375 | 1375 | [7 empty] | 3
1376 | 1376 | [7 empty] | 2
1377 | 1377 | [7 empty] | 1
1378 | 1378 | [7 empty] | 1
1379 | 1379 | [7 empty] | 2
1380 | 1380 | [7 empty] | 4
1381 | 1381 | [7 empty] | 2
1382 | 1382 | [7 empty] | 3
1383 | 1383 | [7 empty] | 1
1384 | 1384 | [7 empty] | 2
1385 | 1385 | [7 empty] | 1
1386 | 1386 | [7 empty] | 2
1387 | 1387 | [7 empty] | 4
1388 | 1388 | [7 empty] | 2
1389 | 1389
1390 | 1390
1391 | 1391
1392 | 1392
1393 | 1393
1394 | 1394
1395 | 1395
1396 | 1396
1397 | 1397
1398 | 1398
1399 | 1399
1400 | 1400
1401 | 1401
1402 | 1402
1403 | 1403
1404 | 1404
1405 | 1405
1406 | 1406
1407 | 1407
1408 | 1408
1409 | 1409
1410 | 1410
1411 | 1411
1412 | 1412
1413 | 1413
1414 | 1414
1415 | 1415
1416 | 1416
1417 | 1417
1418 | 1418
1419 | 1419
1420 | 1420
1421 | 1421
1422 | 1422
1423 | 1423
1424 | 1424
1425 | 1425
1426 | 1426
1427 | 1427
1428 | 1428
1429 | 1429
1430 | 1430
1431 | 1431
1432 | 1432
1433 | 1433
1434 | 1434
1435 | 1435
1436 | 1436
1437 | 1437
1438 | 1438
1439 | 1439
1440 | 1440
1441 | 1441
1442 | 1442
1443 | 1443
1444 | 1444
1445 | 1445
1446 | 1446
1447 | 1447
1448 | 1448
1449 | 1449
1450 | 1450
1451 | 1451
1452 | 1452
1453 | 1453
1454 | 1454
1455 | 1455
1456 | 1456
1457 | 1457
1458 | 1458
1459 | 1459

## 임시동력입.출고현황
| ■ 임시동력 자재 입.출고 현황 (Status of temporary power materials) | [11 empty] | ※ Update every Sunday!!
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [14 empty] | 2026-06-01
| No | 품목 | 자재명 | Applicable Code & Standards | 규격 | 단위 | 계약 수량 | DOOSAN |  |  |  |  | DAESUN |  |  | Remark |  | Material No.
[8 empty] | 발주 | 미입고 | 입고 | 불출 | 재고 | 입고 | 불출 | 재고
Code |  | Sortation | Items / Services |  | Size | Unit | Q'ty | Purch | No come | Incoming | Handover to DAESUN | Stock | In | Out | Stock
GEN-001 | 1 | D/G | Generator |  | 400KVA | 대 |  | 2 | 0 | 2 | 2 | 0 | 2 | 1 | 1 |  |  | GEN-001
GEN-002 | 2 | D/G | Generator |  | 300KVA | 대 |  | 25 | 0 | 25 | 25 | 0 | 25 | 20 | 5 | 3 out fo repair |  | GEN-002
GEN-003 | 3 | D/G | Generator |  | 150KVA | 대 |  | 18 | 0 | 18 | 18 | 0 | 18 | 17 | 1 | 1 out fo repair |  | GEN-003
GEN-004 | 4 | D/G | Generator |  | 100KVA | 대 |  | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 |  |  | GEN-004
GEN-005 | 5 | D/G | Generator |  | 80KVA | 대 |  | 4 | 0 | 4 | 4 | 0 | 4 | 4 | 0 |  |  | GEN-005
GEN-006 | 6 | D/G | Generator |  | 50KVA | 대 |  | 2 | 0 | 2 | 2 | 0 | 2 | 1 | 1 |  |  | GEN-006 |  | 1대 고장 | 1500000
|  | 소계(Subtotal) | [5 empty] | 52 | 0 | 52 | 52 | 0 | 52 | 44 | 8
PNL-001 | 1 | Panel | Electrical Panel |  | 800A | EA |  | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 |  |  | PNL-001 |  | DP
PNL-002 | 2 | Panel | Electrical Panel |  | 630A | EA |  | 9 | 0 | 9 | 9 | 0 | 9 | 8 | 1 |  |  | PNL-002 |  | DP
PNL-003 | 3 | Panel | Electrical Panel |  | 400A | EA |  | 8 | 0 | 8 | 8 | 0 | 8 | 4 | 4 |  |  | PNL-003 |  | DP
PNL-004 | 4 | Panel | Electrical Panel |  | 300A | EA |  | 6 | 2 | 4 | 4 | 0 | 4 | 2 | 2 |  |  | PNL-004 |  | DP
PNL-005 | 5 | Panel | Electrical Panel |  | 250A | EA |  | 20 | 0 | 20 | 20 | 0 | 20 | 18 | 2 |  |  | PNL-005 |  | DP
PNL-005.1 |  | Panel | Electrical Panel |  | 200A | EA |  | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PNL-005.1 | 2026.02.22,추가 | DP
PNL-006 | 6 | Panel | Electrical Panel |  | 160A | EA |  | 53 | 0 | 53 | 53 | 0 | 53 | 45 | 8 |  |  | PNL-006 |  | DP
PNL-007 | 7 | Panel | Electrical Panel |  | 125A | EA |  | 22 | 0 | 22 | 22 | 0 | 22 | 19 | 3 |  |  | PNL-007 | 125A, Power | DP
PNL-009 | 9 | Panel | Electrical Panel |  | 100A | EA |  | 48 | 0 | 48 | 48 | 0 | 48 | 31 | 17 | TYPE(K10EA/G-120EA) |  | PNL-009 |  | DP
PNL-014 | 10 | Panel | Electrical Panel |  | 63A | EA |  | 60 | 0 | 60 | 60 | 0 | 60 | 25 | 35 |  |  | PNL-014 | 2025.09.07,추가 | DP
PNL-010 | 11 | Panel | Electrical Panel |  | 50A | EA |  | 15 | 0 | 15 | 15 | 0 | 15 | 13 | 2 |  |  | PNL-010 |  | DP
PNL-011 | 12 | Panel | Electrical Panel |  | 32A | EA |  | 3 | 0 | 3 | 3 | 0 | 3 | 3 | 0 |  |  | PNL-011 |  | DP
PNL-012 | 13 | Panel | MTS Panel |  | 200A | EA |  |  | 0 | 0 | 0 | 0 | 2 | 2 | 0 | DAESUN income |  | PNL-012 | 2025.05.26,추가 | MTS
PNL-013 | 14 | Panel | MTS Panel |  | 100A | EA |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 0 | DAESUN income |  | PNL-013 | 2025.05.26,추가 | MTS
PNL-015 | 15 | Panel | MTS Panel |  | 250A | EA |  |  | 0 | 0 |  | 0 | 2 | 2 | 0 | DAESUN income |  | PNL-015 | 2025.12.14,추가 | MTS
|  | 소계(Subtotal) | [5 empty] | 250 | 7 | 243 | 243 | 0 | 248 | 173 | 75
CAL-001 | 1 | Cable | AL Cable |  | 3C x 240+120mm2 [ALU] | M |  | 1100 | 0 | 1100 | 1100 | 0 | 1100 | 24 | 1076 | Aluminum | 1 | CAL-001
CAL-028 | 2 | Cable | AL Cable |  | 3C x 185+95mm2 [ALU] | M |  | 2000 | 0 | 2000 | 2000 | 0 | 2000 | 377 | 1623 | Aluminum | 2 | CAL-028
CAL-002 | 3 | Cable | AL Cable |  | 3C x 150+70mm2 [ALU] | M |  | 2300 | 0 | 2300 | 2300 | 0 | 2300 | 466 | 1834 | Aluminum | 3 | CAL-002
CAL-003 | 4 | Cable | AL Cable |  | 3C x 120+70mm2 [ALU] | M |  | 2500 | 0 | 2500 | 2500 | 0 | 2500 | 714 | 1786 | Aluminum | 4 | CAL-003
CAL-004 | 5 | Cable | AL Cable |  | 3C x 95+50mm2 [ALU] | M |  | 3500 | 0 | 3500 | 3500 | 0 | 3500 | 1200 | 2300 | Aluminum | 5 | CAL-004
CAL-005 | 6 | Cable | AL Cable |  | 3C x 70+35mm2 [ALU] | M |  | 2000 | 0 | 2000 | 2000 | 0 | 2000 | 556 | 1444 | Aluminum | 6 | CAL-005
CAL-006 | 7 | Cable | AL Cable |  | 3C x 50+25mm2 [ALU] | M |  | 6000 | 0 | 6000 | 6000 | 0 | 6000 | 3723 | 2277 | Aluminum | 7 | CAL-006
CAL-007 | 8 | Cable | AL Cable |  | 4C x 35mm2 [ALU] | M |  | 500 | 0 | 500 | 500 | 0 | 500 | 500 | 0 | Aluminum | 8 | CAL-007
CAL-008 | 9 | Cable | CV Cable |  | 3C X 185+95mm2 | M |  | 78 | 0 | 78 | 78 | 0 | 78 | 78 | 0 |  | 9 | CAL-008
CAL-029 | 10 | Cable | CV Cable |  | 3C X 95+50mm2 | M |  | 100 | 0 | 100 | 100 | 0 | 100 | 45 | 55 |  | 10 | CAL-029
CAL-009 | 11 | Cable | CV Cable |  | 3C X 70+35mm2 | M |  | 20 | 0 | 20 | 20 | 0 | 20 | 20 | 0 |  | 11 | CAL-009
CAL-010 | 12 | Cable | CV Cable |  | 3C X 50+25mm2 | M |  | 244 | 0 | 244 | 244 | 0 | 244 | 244 | 0 |  | 12 | CAL-010
CAL-011 | 13 | Cable | CV Cable |  | 4C x 35mm2 | M |  | 2062 | 0 | 2062 | 2062 | 0 | 2062 | 749 | 1313 |  | 13 | CAL-011
CAL-012 | 14 | Cable | CV Cable |  | 4C x 25mm2 | M |  | 2300 | 0 | 2300 | 2300 | 0 | 2300 | 0 | 2300 |  | 14 | CAL-012
CAL-013 | 15 | Cable | CV Cable |  | 4C x 16mm2 | M |  | 5500 | 0 | 5500 | 5500 | 0 | 5500 | 3291 | 2209 |  | 15 | CAL-013
CAL-014 | 16 | Cable | CV Cable |  | 4C x 10mm2 | M |  | 4000 | 0 | 4000 | 4000 | 0 | 4000 | 1513 | 2487 |  | 16 | CAL-014
CAL-015 | 17 | Cable | CV Cable |  | 4C x 6mm2 | M |  | 4500 | 0 | 4500 | 4500 | 0 | 4500 | 4450 | 50 |  | 17 | CAL-015
CAL-030 | 18 | Cable | CV Cable |  | 4C x 4mm2 | M |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 | 687 | 313 |  | 18 | CAL-030
CAL-016 | 19 | Cable | CV Cable |  | 3C x 10mm2 | M |  | 3623 | 0 | 3623 | 3623 | 0 | 3623 | 1436 | 2187 |  | 19 | CAL-016
CAL-017 | 20 | Cable | CV Cable |  | 3C x 6mm2 | M |  | 6000 | 0 | 6000 | 6000 | 0 | 6000 | 2762 | 3238 |  | 20 | CAL-017
CAL-018 | 21 | Cable | CV Cable |  | 3C x 4mm2 | M |  | 7000 | 0 | 7000 | 7000 | 0 | 7000 | 4465 | 2535 |  | 21 | CAL-018
CAL-027 | 22 | Cable | CV Cable |  | 3C x 3mm2 | M |  | 7000 | 0 | 7000 | 7000 | 0 | 7000 | 6574 | 426 |  | 22 | CAL-027
CAL-019 | 23 | Cable | CV Cable |  | 3C x 2.5mm2 | M |  | 18000 | 0 | 18000 | 18000 | 0 | 18000 | 18000 | 0 |  | 23 | CAL-019
CAL-020 | 24 | Cable | CV Cable |  | 3C x 1.5mm2 | M |  | 6000 | 0 | 6000 | 6000 | 0 | 6000 | 6000 | 0 |  | 24 | CAL-020
CAL-021 | 25 | Cable | CV Cable |  | 2C x 16mm2 | M |  | 163 | 0 | 163 | 163 | 0 | 163 | 45 | 118 |  | 25 | CAL-021
CAL-022 | 26 | Cable | Grounding Cable |  | 1C x 70mm2 | M |  | 800 | 0 | 800 | 800 | 0 | 800 | 344 | 456 |  | 26 | CAL-022
CAL-023 | 27 | Cable | Grounding Cable |  | 1C x 35mm2 | M |  | 500 | 0 | 500 | 500 | 0 | 500 | 128 | 372 |  | 27 | CAL-023
CAL-024 | 28 | Cable | Grounding Cable |  | 1C x 25mm2 | M |  | 500 | 0 | 500 | 500 | 0 | 500 | 210 | 290 |  | 28 | CAL-024
CAL-025 | 29 | Cable | Grounding Cable |  | 1C x 16mm2 | M |  | 3000 | 0 | 3000 | 3000 | 0 | 3000 | 1082 | 1918 |  | 29 | CAL-025
CAL-026 | 30 | Cable | Grounding Cable |  | 1C x 10mm2 | M |  | 1200 | 0 | 1200 | 1200 | 0 | 1200 | 670 | 530 |  | 30 | CAL-026
|  | 소계(Subtotal) | [5 empty] | 93490 | 0 | 93490 | 93490 | 0 | 93490 | 60353 | 33137
LTG-001 | 1 | LTG | Lighting Fixture |  | 400W | EA |  | 1000 | 0 | 1000 | 1000 | 0 | 1000 | 960 | 40 | Damage (10EA) 포함 |  | LTG-001
LTG-002 | 2 | LTG | Lighting Fixture |  | 200W | EA |  | 750 | 0 | 750 | 750 | 0 | 750 | 649 | 101 | Damage (3EA) 포함 |  | LTG-002
LTG-003 | 3 | LTG | Lighting Fixture |  | 100W | EA |  | 400 | 0 | 400 | 400 | 0 | 400 | 400 | 0 |  |  | LTG-003
LTG-004 | 4 | LTG | Lighting Fixture |  | 50W | EA |  | 400 | 0 | 400 | 400 | 0 | 400 | 195 | 205 |  |  | LTG-004
|  | 소계(Subtotal) | [5 empty] | 2550 | 0 | 2550 | 2550 | 0 | 2550 | 2204 | 346
MCB-001 | 1 | MCB | MCB |  | 1P - 16A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 19 | 31 |  |  | MCB-001 | 2025.09.07,추가
MCB-002 | 2 | MCB | MCB |  | 1P - 25A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 12 | 38 |  |  | MCB-002 | 2025.09.07,추가
MCB-003 | 3 | MCB | MCB |  | 1P - 32A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 9 | 41 |  |  | MCB-003 | 2025.09.07,추가
MCB-004 | 4 | MCB | MCB |  | 3P - 32A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 7 | 43 |  |  | MCB-004 | 2025.09.07,추가
MCB-005 | 5 | MCB | MCB |  | 3P - 63A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 12 | 38 |  |  | MCB-005 | 2025.09.07,추가
MCB-006 | 6 | MCB | RCBO |  | 1P + N -16A - 30 mA | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 14 | 36 |  |  | MCB-006 | 2025.09.07,추가
MCB-007 | 7 | MCB | RCBO |  | 1P + N -25A - 30 mA | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 5 | 45 |  |  | MCB-007 | 2025.09.07,추가
MCB-008 | 8 | MCB | RCBO |  | 1P + N -32A - 30 mA | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 16 | 34 |  |  | MCB-008 | 2025.09.07,추가
MCB-009 | 9 | MCB | RCCB |  | 4P - 32A - 30 mA | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 50 | 0 |  |  | MCB-009 | 2025.09.07,추가
MCB-010 | 10 | MCB | RCCB |  | 4P - 63A - 30 mA | EA |  | 40 | 0 | 40 | 40 | 0 | 40 | 14 | 26 |  |  | MCB-010 | 2025.09.07,추가
MCB-011 | 11 | MCB | MCCB |  | 100 A ( adj. magnetic) | EA |  | 5 | 0 | 5 | 5 | 0 | 5 | 0 | 5 |  |  | MCB-011 | 2025.09.07,추가
MCB-012 | 12 | MCB | MCCB |  | 160 A ( adj. magnetic) | EA |  | 5 | 0 | 5 | 5 | 0 | 5 | 4 | 1 |  |  | MCB-012 | 2025.09.07,추가
MCB-013 | 13 | MCB | MCCB |  | 250 A ( adj. magnetic) | EA |  | 5 | 0 | 5 | 5 | 0 | 5 | 4 | 1 |  |  | MCB-013 | 2025.09.07,추가
|  | 소계(Subtotal) | [5 empty] | 505 | 0 | 505 | 505 | 0 | 505 | 166 | 339
PLG-001 | 1 | power plug | Industrial Socket |  | 3P - 16A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 50 | 0 |  |  | PLG-001 | 2025.09.07,추가
PLG-002 | 2 | power plug | Industrial Socket |  | 3P - 32A | EA |  | 30 | 0 | 30 | 30 | 0 | 30 | 10 | 20 |  |  | PLG-002 | 2025.09.07,추가
PLG-003 | 3 | power plug | Industrial Socket |  | 5P - 32A | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 29 | 21 |  |  | PLG-003 | 2025.09.07,추가
PLG-004 | 4 | power plug | Industrial Socket |  | 5P - 63A | EA |  | 20 | 0 | 20 | 20 | 0 | 20 | 17 | 3 |  |  | PLG-004 | 2025.09.07,추가
|  | 소계(Subtotal) |  |  |  | EA |  | 150 | 0 | 150 | 150 | 0 | 150 | 106 | 44
LMP-001 | 1 | Other | Indication Lamp |  | Red | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 9 | 41 |  |  | LMP-001 | 2025.09.07,추가
LMP-002 | 2 | Other | Indication Lamp |  | Yellow | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 2 | 48 |  |  | LMP-002 | 2025.09.07,추가
LMP-003 | 3 | Other | Indication Lamp |  | Blue | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 2 | 48 |  |  | LMP-003 | 2025.09.07,추가
LOK-001 | 4 | Other | Metal Panel Lock with Key |  | Universal type | EA |  | 50 | 0 | 50 | 50 | 0 | 50 | 0 | 50 |  |  | LOK-001 | 2025.09.07,추가
|  | 소계(Subtotal) |  |  |  | EA |  | 200 | 0 | 200 | 200 | 0 | 200 | 13 | 187
[8 empty] | 97197 | 7 | 97190 | 97190 | 0 | 97195 | 63059 | 34136
[8 empty] | 73510 | 7389 | 66121 | 66121 | 0 | 66124 | 41916 | 24208
[8 empty] | 23687 | -7382 | 31069 | 31069 | 0 | 31071 | 21143 | 9928

## T-Power-income
POR CONTROL LOG - Income
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [6 empty] | from Doosan to Daesun
| No | RSI No | Date | Material No. | Sortation | Items / Services | Applicable Code & Standards | Size | Unit | Q'TY | Remarks
[5 empty] | 3 | 4 | 5 | 6 | 7
1 | 1 |  |  | GEN-001 | D/G | Generator | 0 | 400KVA | 대 | 2 | 이전RSI 화인후 수정
2 | 2 |  |  | GEN-002 | D/G | Generator | 0 | 300KVA | 대 | 19 | 이전RSI 화인후 수정
3 | 3 |  |  | GEN-003 | D/G | Generator | 0 | 150KVA | 대 | 16 | 이전RSI 화인후 수정
4 | 4 |  |  | GEN-004 | D/G | Generator | 0 | 100KVA | 대 | 1 | 이전RSI 화인후 수정
5 | 5 |  |  | GEN-005 | D/G | Generator | 0 | 80KVA | 대 | 4 | 이전RSI 화인후 수정
6 | 6 |  |  | GEN-006 | D/G | Generator | 0 | 50KVA | 대 | 2 | 이전RSI 화인후 수정
7 | 7 |  |  | PNL-001 | Panel | Electrical Panel | 0 | 800A | EA | 1 | 이전RSI 화인후 수정
8 | 8 |  |  | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA | 5 | 이전RSI 화인후 수정
9 | 9 |  |  | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 0 | 이전RSI 화인후 수정
10 | 10 |  |  | PNL-004 | Panel | Electrical Panel | 0 | 300A | EA | 4 | 이전RSI 화인후 수정
11 | 11 |  |  | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 9 | 이전RSI 화인후 수정
12 | 12 |  |  | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 31 | 이전RSI 화인후 수정
13 | 13 |  |  | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA | 0 | 이전RSI 화인후 수정
14 | 14 |  |  | PNL-008 | 0 | 0 | 0 | 0 | 0 | 0 | 이전RSI 화인후 수정
15 | 15 |  |  | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 18 | 이전RSI 화인후 수정
16 | 16 |  |  | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA |  | 이전RSI 화인후 수정
17 | 17 |  |  | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 0 | 이전RSI 화인후 수정
18 | 18 |  |  | PNL-011 | Panel | Electrical Panel | 0 | 32A | EA | 0 | 이전RSI 화인후 수정
19 | 19 |  |  | PNL-012 | Panel | MTS Panel | 0 | 200A | EA | -2 | 이전RSI 화인후 수정
20 | 20 |  |  | PNL-013 | Panel | MTS Panel | 0 | 100A | EA | -1 | 이전RSI 화인후 수정
21 | 21 |  |  | CAL-001 | Cable | AL Cable | 0 | 3C x 240+120mm2 [ALU] | M | 100 | 이전RSI 화인후 수정
22 | 22 |  |  | CAL-028 | Cable | AL Cable | 0 | 3C x 185+95mm2 [ALU] | M | 5 | 이전RSI 화인후 수정
23 | 23 |  |  | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M | 500 | 이전RSI 화인후 수정
24 | 24 |  |  | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M | -3 | 이전RSI 화인후 수정
25 | 25 |  |  | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M |  | 이전RSI 화인후 수정
26 | 26 |  |  | CAL-005 | Cable | AL Cable | 0 | 3C x 70+35mm2 [ALU] | M | 0 | 이전RSI 화인후 수정
27 | 27 |  |  | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | -5 | 이전RSI 화인후 수정
28 | 28 |  |  | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 0 | 이전RSI 화인후 수정
29 | 29 |  |  | CAL-008 | Cable | CV Cable | 0 | 3C X 185+95mm2 | M | 78 | 이전RSI 화인후 수정
30 | 30 |  |  | CAL-029 | Cable | CV Cable | 0 | 3C X 95+50mm2 | M | 0 | 이전RSI 화인후 수정
31 | 31 |  |  | CAL-009 | Cable | CV Cable | 0 | 3C X 70+35mm2 | M | 20 | 이전RSI 화인후 수정
32 | 32 |  |  | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M | 244 | 이전RSI 화인후 수정
33 | 33 |  |  | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 462 | 이전RSI 화인후 수정
34 | 34 |  |  | CAL-012 | Cable | CV Cable | 0 | 4C x 25mm2 | M | 0 | 이전RSI 화인후 수정
35 | 35 |  |  | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1000 | 이전RSI 화인후 수정
36 | 36 |  |  | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1500 | 이전RSI 화인후 수정
37 | 37 |  |  | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 2000 | 이전RSI 화인후 수정
38 | 38 |  |  | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 0 | 이전RSI 화인후 수정
39 | 39 |  |  | CAL-016 | Cable | CV Cable | 0 | 3C x 10mm2 | M | 2623 | 이전RSI 화인후 수정
40 | 40 |  |  | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1500 | 이전RSI 화인후 수정
41 | 41 |  |  | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1045 | 이전RSI 화인후 수정
42 | 42 |  |  | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1998 | 이전RSI 화인후 수정
43 | 43 |  |  | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2039 | 이전RSI 화인후 수정
44 | 44 |  |  | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | -22 | 이전RSI 화인후 수정
45 | 45 |  |  | CAL-021 | Cable | CV Cable | 0 | 2C x 16mm2 | M | -1837 | 이전RSI 화인후 수정
46 | 46 |  |  | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 500 | 이전RSI 화인후 수정
47 | 47 |  |  | CAL-023 | Cable | Grounding Cable | 0 | 1C x 35mm2 | M | 500 | 이전RSI 화인후 수정
48 | 48 |  |  | CAL-024 | Cable | Grounding Cable | 0 | 1C x 25mm2 | M | 500 | 이전RSI 화인후 수정
49 | 49 |  |  | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 0 | 이전RSI 화인후 수정
50 | 50 |  |  | CAL-026 | Cable | Grounding Cable | 0 | 1C x 10mm2 | M | 700 | 이전RSI 화인후 수정
51 | 51 |  |  | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 300 | 이전RSI 화인후 수정
52 | 52 |  |  | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 314 | 이전RSI 화인후 수정
53 | 53 |  |  | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 200 | 이전RSI 화인후 수정
54 | 54 |  |  | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 0 | 이전RSI 화인후 수정
55 | 55 |  |  | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | 0 | 이전RSI 화인후 수정
56 | 56 |  |  | MCB-002 | MCB | MCB | 0 | 1P - 25A | EA | 0 | 이전RSI 화인후 수정
57 | 57 |  |  | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | 0 | 이전RSI 화인후 수정
58 | 58 |  |  | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA | -50 | 이전RSI 화인후 수정
59 | 59 |  |  | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 0 | 이전RSI 화인후 수정
60 | 60 |  |  | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | 0 | 이전RSI 화인후 수정
61 | 61 |  |  | MCB-007 | MCB | RCBO | 0 | 1P + N -25A - 30 mA | EA | 0 | 이전RSI 화인후 수정
62 | 62 |  |  | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 0 | 이전RSI 화인후 수정
63 | 63 |  |  | MCB-009 | MCB | RCCB | 0 | 4P - 32A - 30 mA | EA | 0 | 이전RSI 화인후 수정
64 | 64 |  |  | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 0 | 이전RSI 화인후 수정
65 | 65 |  |  | MCB-011 | MCB | MCCB | 0 | 100 A ( adj. magnetic) | EA | 0 | 이전RSI 화인후 수정
66 | 66 |  |  | MCB-012 | MCB | MCCB | 0 | 160 A ( adj. magnetic) | EA | 0 | 이전RSI 화인후 수정
67 | 67 |  |  | MCB-013 | MCB | MCCB | 0 | 250 A ( adj. magnetic) | EA | 0 | 이전RSI 화인후 수정
68 | 68 |  |  | PLG-001 | power plug | Industrial Socket | 0 | 3P - 16A | EA |  | 이전RSI 화인후 수정
69 | 69 |  |  | PLG-002 | power plug | Industrial Socket | 0 | 3P - 32A | EA | 0 | 이전RSI 화인후 수정
70 | 70 |  |  | PLG-003 | power plug | Industrial Socket | 0 | 5P - 32A | EA | 0 | 이전RSI 화인후 수정
71 | 71 |  |  | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA | 0 | 이전RSI 화인후 수정
72 | 72 |  |  | LMP-001 | Other | Indication Lamp | 0 | Red | EA | 0 | 이전RSI 화인후 수정
73 | 73 |  |  | LMP-002 | Other | Indication Lamp | 0 | Yellow | EA | 0 | 이전RSI 화인후 수정
74 | 74 |  |  | LMP-003 | Other | Indication Lamp | 0 | Blue | EA | 0 | 이전RSI 화인후 수정
75 | 75 |  |  | LOK-001 | Other | Metal Panel Lock with Key | 0 | Universal type | EA |  | 이전RSI 화인후 수정
76 | 76 |  |  | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA | 50
77 | 77 |  |  | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 20
78 | 78 |  | 2024-07-18 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1000 | CAL-013
79 | 79 |  | 2024-07-18 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1000
80 | 80 |  | 2024-07-18 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1000
81 | 81 |  | 2024-07-18 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2000
82 | 82 |  | 2024-06-22 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 300
83 | 83 |  | 2024-06-22 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 3000
84 | 84 |  | 2024-06-22 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M | 300
85 | 85 |  | 2024-06-22 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 3000
86 | 86 |  | 2024-09-03 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3000
87 | 87 |  | 2024-09-03 | CAL-021 | Cable | CV Cable | 0 | 2C x 16mm2 | M | 2000
88 | 88 |  | 2024-09-03 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1000
89 | 89 |  | 2024-09-03 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 500
90 | 90 |  | 2024-09-03 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 36
91 | 91 |  | 2024-09-03 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 36
92 | 92 |  | 2024-10-08 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 1000
93 | 93 |  | 2024-10-08 | CAL-005 | Cable | AL Cable | 0 | 3C x 70+35mm2 [ALU] | M | 1000
94 | 94 |  | 2024-10-08 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 500
95 | 95 |  | 2024-10-08 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 10
96 | 96 |  | 2024-10-08 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1
97 | 97 |  | 2024-10-15 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 1
98 | 98 |  | 2024-10-15 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1
99 | 99 |  | 2024-10-15 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 1
100 | 100 |  | 2024-10-15 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1
101 | 101 |  | 2024-10-15 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1
102 | 102 |  | 2024-10-15 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 10
103 | 103 |  | 2024-10-17 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 33
104 | 104 |  | 2024-10-22 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 50
105 | 105 |  | 2024-10-23 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 61
106 | 106 |  | 2024-10-23 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 6
107 | 107 |  | 2024-10-28 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 8
108 | 108 |  | 2024-11-05 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 7
109 | 109 |  | 2024-11-10 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 3
110 | 110 |  | 2024-11-27 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M | 500
111 | 111 |  | 2024-11-27 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 500
112 | 112 |  | 2024-11-27 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 300
113 | 113 |  | 2024-11-27 | CAL-012 | Cable | CV Cable | 0 | 4C x 25mm2 | M | 300
114 | 114 |  | 2024-11-27 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 500 | CAL-013
115 | 115 |  | 2024-11-27 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 500
116 | 116 |  | 2024-11-27 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 500 |  |  |  | 61
117 | 117 |  | 2024-11-27 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1000 |  |  | 123.5 | 62.5
118 | 118 |  | 2024-11-27 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3000 |  |  | 197.6
119 | 119 |  | 2024-11-27 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 100
120 | 120 |  | 2024-12-10 | PNL-011 | Panel | Electrical Panel | 0 | 32A | EA | 3
121 | 121 |  | 2025-03-19 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA | 10
122 | 122 |  | 2025-03-19 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA | 8 |  | PNL-008→PNL-007
123 | 123 |  | 2025-04-10 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1
124 | 124 |  | 2025-04-22 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA | 4
125 | 125 |  | 2025-04-22 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 300
126 | 126 |  | 2025-04-27 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 | 2
127 | 127 |  | 2025-04-27 | GEN-003 | D/G | Generator | 0 | 150KVA | 대 | 2
128 | 128 | Daesun | 2025-05-23 | PNL-012 | Panel | MTS Panel | 0 | 200A | EA | 2 | Daesun Income
129 | 129 | Daesun | 2025-05-23 | PNL-013 | Panel | MTS Panel | 0 | 100A | EA | 1 | Daesun Income
130 | 130 |  | 2025-06-03 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M | 1003
131 | 131 |  | 2025-06-03 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 2005
132 | 132 |  | 2025-06-04 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3002
133 | 133 |  | 2025-06-04 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3961
134 | 134 |  | 2025-06-04 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3022
135 | 135 |  | 2025-09-25 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 200
136 | 136 |  | 2025-10-14 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 | 4
137 | 137 |  | 2025-10-15 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 100
138 | 138 |  | 2025-10-15 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | 50
139 | 139 |  | 2025-10-15 | MCB-002 | MCB | MCB | 0 | 1P - 25A | EA | 50
140 | 140 |  | 2025-10-15 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | 50
141 | 141 |  | 2025-10-15 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | 45
142 | 142 |  | 2025-10-15 | MCB-007 | MCB | RCBO | 0 | 1P + N -25A - 30 mA | EA | 17
143 | 143 |  | 2025-10-15 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 20
144 | 144 |  | 2025-10-15 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 20
145 | 145 |  | 2025-10-23 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 50
146 | 146 |  | 2025-10-23 | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA | 50
147 | 147 |  | 2025-10-23 | MCB-011 | MCB | MCCB | 0 | 100 A ( adj. magnetic) | EA | 5
148 | 148 |  | 2025-10-23 | MCB-012 | MCB | MCCB | 0 | 160 A ( adj. magnetic) | EA | 5
149 | 149 |  | 2025-10-23 | MCB-013 | MCB | MCCB | 0 | 250 A ( adj. magnetic) | EA | 5
150 | 150 |  | 2025-10-23 | PLG-002 | power plug | Industrial Socket | 0 | 3P - 32A | EA | 30
151 | 151 |  | 2025-10-23 | PLG-003 | power plug | Industrial Socket | 0 | 5P - 32A | EA | 50
152 | 152 |  | 2025-10-23 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA | 20
153 | 153 |  | 2025-10-23 | LMP-001 | Other | Indication Lamp | 0 | Red | EA | 50
154 | 154 |  | 2025-10-23 | LMP-002 | Other | Indication Lamp | 0 | Yellow | EA | 50
155 | 155 |  | 2025-10-23 | LMP-003 | Other | Indication Lamp | 0 | Blue | EA | 50
156 | 156 |  | 2025-10-23 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | 5
157 | 157 |  | 2025-10-23 | MCB-007 | MCB | RCBO | 0 | 1P + N -25A - 30 mA | EA | 33
158 | 158 |  | 2025-10-23 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 30
159 | 159 |  | 2025-10-23 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1
160 | 160 |  | 2025-10-23 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 5
161 | 161 |  | 2025-11-04 | CAL-001 | Cable | AL Cable | 0 | 3C x 240+120mm2 [ALU] | M | 1000
162 | 162 |  | 2025-11-04 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M | 500
163 | 163 |  | 2025-11-04 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M | 1000
164 | 164 |  | 2025-11-04 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 1000
165 | 165 |  | 2025-11-04 | CAL-005 | Cable | AL Cable | 0 | 3C x 70+35mm2 [ALU] | M | 1000
166 | 166 |  | 2025-11-04 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1000
167 | 167 |  | 2025-11-04 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 1000
168 | 168 |  | 2025-11-04 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 955
169 | 169 |  | 2025-11-04 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 2
170 | 170 |  | 2025-11-04 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 10
171 | 171 |  | 2025-11-09 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1
172 | 172 |  | 2025-11-09 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 2
173 | 173 |  | 2025-11-09 | CAL-028 | Cable | AL Cable | 0 | 3C x 185+95mm2 [ALU] | M | 995
174 | 174 |  | 2025-11-09 | CAL-029 | Cable | CV Cable | 0 | 3C X 95+50mm2 | M | 100
175 | 175 |  | 2025-11-09 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1000
176 | 176 |  | 2025-11-09 | CAL-026 | Cable | Grounding Cable | 0 | 1C x 10mm2 | M | 500
177 | 177 |  | 2025-11-09 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3000
178 | 178 |  | 2025-11-09 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1500
179 | 179 | RSI2025005869 | 2025-11-13 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 6
180 | 180 | RSI2025005869 | 2025-11-13 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 10
181 | 181 | RSI2025005869 | 2025-11-13 | PLG-001 | power plug | Industrial Socket | 0 | 3P - 16A | EA | 50
182 | 182 | RSI2025005869 | 2025-11-13 | LOK-001 | Other | Metal Panel Lock with Key | 0 | Universal type | EA | 50
183 | 183 | RSI2025006051 | 2025-11-26 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA | 1
184 | 184 | RSI2025006051 | 2025-11-26 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1
185 | 185 | RSI2025006007 | 2025-11-26 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 10
186 | 186 | RSI2025006007 | 2025-11-26 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3
187 | 187 | Daesun | 2025-12-09 | PNL-015 | Panel | MTS Panel | 0 | 250A | EA | 2 | Daesun Income
188 | 188 | RSI2025006281 | 2025-12-14 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA | 3
189 | 189 | RSI2025006360 | 2025-12-18 | MCB-009 | MCB | RCCB | 0 | 4P - 32A - 30 mA | EA | 50
190 | 190 | RSI2025006360 | 2025-12-18 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 4
191 | 191 | RSI2026000169 | 2026-01-13 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 80
192 | 192 | RSI2026000169 | 2026-01-13 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 100
193 | 193 | RSI2026000169 | 2026-01-13 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 100
194 | 194 | RSI2026000169 | 2026-01-13 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 99
195 | 195 | RSI2026000458 | 2026-01-28 | CAL-028 | Cable | AL Cable | 0 | 3C x 185+95mm2 [ALU] | M | 1000
196 | 196 | RSI2026000458 | 2026-01-28 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 1000
197 | 197 | RSI2026000458 | 2026-01-28 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 1000
198 | 198 | RSI2026000458 | 2026-01-28 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 2000
199 | 199 | RSI2026000458 | 2026-01-28 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 2000
200 | 200 | RSI2026000458 | 2026-01-28 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1000
201 | 201 | RSI2026000458 | 2026-01-28 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 2000
202 | 202 | RSI2026000458 | 2026-01-28 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 2000
203 | 203 | RSI2026000458 | 2026-01-28 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4000
204 | 204 | RSI2026000458 | 2026-01-28 | CAL-016 | Cable | CV Cable | 0 | 3C x 10mm2 | M | 1000
205 | 205 | RSI2026000458 | 2026-01-28 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1500
206 | 206 | RSI2026000458 | 2026-02-01 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M | 1000
207 | 207 | RSI2026000458 | 2026-02-01 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 1000
208 | 208 | RSI2026000458 | 2026-02-01 | CAL-012 | Cable | CV Cable | 0 | 4C x 25mm2 | M | 2000
209 | 209 | RSI2026000455 | 2026-02-02 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 220
210 | 210 | RSI2026000455 | 2026-02-02 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 200
211 | 211 | RSI2026000455 | 2026-02-02 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 100
212 | 212 | RSI2026000455 | 2026-02-02 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 201
213 | 213 | RSI2026001370 | 2026-04-08 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 10
214 | 214 | RSI2026001523 | 2026-04-13 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 20
215 | 215 | RSI2026001518 | 2026-04-13 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 20
216 | 216 | RSI2026001648 | 2026-04-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 10
217 | 217 |  |  |  | 0 | 0 | 0 | 0
218 | 218 |  |  |  | 0 | 0 | 0 | 0
219 | 219 |  |  |  | 0 | 0 | 0 | 0
220 | 220 |  |  |  | 0 | 0 | 0 | 0
221 | 221 |  |  |  | 0 | 0 | 0 | 0
222 | 222 |  |  |  | 0 | 0 | 0 | 0
223 | 223 |  |  |  | 0 | 0 | 0 | 0
224 | 224 |  |  |  | 0 | 0 | 0 | 0
225 | 225 |  |  |  | 0 | 0 | 0 | 0
226 | 226 |  |  |  | 0 | 0 | 0 | 0
227 | 227 |  |  |  | 0 | 0 | 0 | 0
228 | 228 |  |  |  | 0 | 0 | 0 | 0
229 | 229 |  |  |  | 0 | 0 | 0 | 0
230 | 230 |  |  |  | 0 | 0 | 0 | 0
231 | 231 |  |  |  | 0 | 0 | 0 | 0
232 | 232 |  |  |  | 0 | 0 | 0 | 0
233 | 233 |  |  |  | 0 | 0 | 0 | 0
234 | 234 |  |  |  | 0 | 0 | 0 | 0
235 | 235 |  |  |  | 0 | 0 | 0 | 0
236 | 236 |  |  |  | 0 | 0 | 0 | 0
237 | 237 |  |  |  | 0 | 0 | 0 | 0
238 | 238 |  |  |  | 0 | 0 | 0 | 0
239 | 239 |  |  |  | 0 | 0 | 0 | 0
240 | 240 |  |  |  | 0 | 0 | 0 | 0
241 | 241 |  |  |  | 0 | 0 | 0 | 0
242 | 242 |  |  |  | 0 | 0 | 0 | 0

## T-Power-out
POR CONTROL LOG - Issue
| 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [5 empty] | from Warehouse & Workshop to Site
| No | Date | Material No. | Sortation | Items / Services | Applicable Code & Standards | Size | Unit | Unit # | BLDG | Q'TY | User | Remarks
|  |  |  | 3 | 4 | 5 | 6 | 7
1 | 1 | 2024년이전불출 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 13
2 | 2 | 2024년이전불출 | GEN-003 | D/G | Generator | 0 | 150KVA | 대 |  |  | 13
3 | 3 | 2024년이전불출 | GEN-004 | D/G | Generator | 0 | 100KVA | 대 |  |  | 1
4 | 4 | 2024년이전불출 | GEN-005 | D/G | Generator | 0 | 80KVA | 대 |  |  | 3
5 | 5 | 2024년이전불출 | GEN-006 | D/G | Generator | 0 | 50KVA | 대 |  |  | -3
6 | 6 | 2024년이전불출 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA |  |  | 4
7 | 7 | 2024년이전불출 | PNL-004 | Panel | Electrical Panel | 0 | 300A | EA |  |  | 1
8 | 8 | 2024년이전불출 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA |  |  | 5
9 | 9 | 2024년이전불출 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 15
10 | 10 | 2024년이전불출 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 11
11 | 11 | 2024년이전불출 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA |  |  | 6
12 | 12 | 2024년이전불출 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA |  |  | 5
13 | 13 | 2024년이전불출 | PNL-011 | Panel | Electrical Panel | 0 | 32A | EA |  |  | 3
14 | 14 | 2024년이전불출 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M |  |  | 142
15 | 15 | 2024년이전불출 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M |  |  | 219
16 | 16 | 2024년이전불출 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M |  |  | 46
17 | 17 | 2024년이전불출 | CAL-005 | Cable | AL Cable | 0 | 3C x 70+35mm2 [ALU] | M |  |  | 279
18 | 18 | 2024년이전불출 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M |  |  | 2173
19 | 19 | 2024년이전불출 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M |  |  | 18
20 | 20 | 2024년이전불출 | CAL-008 | Cable | CV Cable | 0 | 3C X 185+95mm2 | M |  |  | 43
21 | 21 | 2024년이전불출 | CAL-009 | Cable | CV Cable | 0 | 3C X 70+35mm2 | M |  |  | -55
22 | 22 | 2024년이전불출 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M |  |  | -149
23 | 23 | 2024년이전불출 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M |  |  | 464
24 | 24 | 2024년이전불출 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 868
25 | 25 | 2024년이전불출 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 218
26 | 26 | 2024년이전불출 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 492
27 | 27 | 2024년이전불출 | CAL-016 | Cable | CV Cable | 0 | 3C x 10mm2 | M |  |  | 1301
28 | 28 | 2024년이전불출 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M |  |  | 1757
29 | 29 | 2024년이전불출 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  |  | 2435
30 | 30 | 2024년이전불출 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M |  |  | 2135
31 | 31 | 2024년이전불출 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 5640 |  |  | 368 | 5272
32 | 32 | 2024년이전불출 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 2912
33 | 33 | 2024년이전불출 | CAL-021 | Cable | CV Cable | 0 | 2C x 16mm2 | M |  |  | 45
34 | 34 | 2024년이전불출 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M |  |  | 294
35 | 35 | 2024년이전불출 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | -120
36 | 36 | 2024년이전불출 | CAL-026 | Cable | Grounding Cable | 0 | 1C x 10mm2 | M |  |  | 495
37 | 37 | 2024년이전불출 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 316
38 | 38 | 2024년이전불출 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 139
39 | 39 | 2024년이전불출 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA |  |  | 0
40 | 40 | 2024년이전불출 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  |  | 25
41 | 41 | 2024년이전불출 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA |  |  | -1
42 | 42 | 2024년이전불출 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA |  |  | -1
43 | 43 | 2024년이전불출 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA |  |  | -1
44 | 44 | 2024년이전불출 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA |  |  | 1
45 | 45 | 2024년이전불출 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA |  |  | 4
46 | 46 | 2024년이전불출 | MCB-002 | MCB | MCB | 0 | 1P - 25A | EA |  |  | 7
47 | 47 | 2024년이전불출 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA |  |  | 1
48 | 48 | 2024년이전불출 | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA |  |  | 1
49 | 49 | 2024년이전불출 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA |  |  | 4
50 | 50 | 2024년이전불출 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA |  |  | 11
51 | 51 | 2024년이전불출 | MCB-007 | MCB | RCBO | 0 | 1P + N -25A - 30 mA | EA |  |  | 1
52 | 52 | 2024년이전불출 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA |  |  | -2
53 | 53 | 2024년이전불출 | MCB-009 | MCB | RCCB | 0 | 4P - 32A - 30 mA | EA |  |  | 50
54 | 54 | 2025-01-01 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 1 | Mohamed Askry
55 | 55 | 2025-01-01 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 10 | 10 UMA | 190 | Mohamed Askry
56 | 56 | 2025-01-01 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 10 | 10 UMA | 225 | Mohamed Askry
57 | 57 | 2025-01-02 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30 UMA | 1 | Mohamed Askry
58 | 58 | 2025-01-04 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40 UMA | 6 | Hassan Mohamed
59 | 59 | 2025-01-04 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 4 | 40 UMA | 3 | Hassan Mohamed
60 | 60 | 2025-01-04 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4 | 40 UMA | 80 | Hassan Mohamed
61 | 61 | 2025-01-04 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 4 | 40 UMA | 30 | Hassan Mohamed
62 | 62 | 2025-01-06 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 2 | 20 UMA | 1 | Hassan Mohamed
63 | 63 | 2025-01-06 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 2 | 20 UMA | 1 | Hassan Mohamed
64 | 64 | 2025-01-06 | CAL-008 | Cable | CV Cable | 0 | 3C X 185+95mm2 | M | 2 | 20 UMA | 17 | Hassan Mohamed
65 | 65 | 2025-01-06 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 2 | 20 UMA | 10 | Hassan Mohamed
66 | 66 | 2025-01-06 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 2 | 20 UMA | 10 | Hassan Mohamed
67 | 67 | 2025-01-06 | CAL-026 | Cable | Grounding Cable | 0 | 1C x 10mm2 | M | 2 | 20 UGB | 15 | Mohamed Mousa
68 | 68 | 2025-01-07 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M | 3 | 30 UMA | 55 | Hassan Mohamed
69 | 69 | 2025-01-07 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M | 3 | 30 UMA | 65 | Hassan Mohamed
70 | 70 | 2025-01-07 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 3 | 30 UMA | 1 | Hassan Mohamed
71 | 71 | 2025-01-07 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 3 | 30 UMA | 1 | Hassan Mohamed
72 | 72 | 2025-01-07 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 3 | 30 UMA | 1 | Hassan Mohamed
73 | 73 | 2025-01-07 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | KHNP | KHNP | 1 | Hassan Mohamed
74 | 74 | 2025-01-08 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 1 | 10 UMA | 100 | Mohamed Mousa
75 | 75 | 2025-01-09 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M | 3 | 30 UGB | 30 | Mohamed Mousa
76 | 76 | 2025-01-09 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 3 | 30 UGB | 100 | Mohamed Mousa
77 | 77 | 2025-01-09 | CAL-016 | Cable | CV Cable | 0 | 3C x 10mm2 | M | 3 | 30 UMA | 5 | Hassan Mohamed
78 | 78 | 2025-01-12 | CAL-008 | Cable | CV Cable | 0 | 3C X 185+95mm2 | M | 3 | 30 UGB | 18 | Hassan Mohamed
79 | 79 | 2025-01-12 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  | MAIN WH | 2 | Hassan Mohamed
80 | 80 | 2025-01-07 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 3 | 30 UMA | 1 | Hassan Mohamed
81 | 81 | 2025-01-12 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  | MAIN WH | 30 | Hassan Mohamed
82 | 82 | 2025-01-13 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  | lighting Service | 4 | Hassan Mohamed
83 | 83 | 2025-01-13 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  | lighting Service | 100 | Hassan Mohamed
84 | 84 | 2025-01-13 | CAL-026 | Cable | Grounding Cable | 0 | 1C x 10mm2 | M |  | lighting Service | 150 | Hassan Mohamed
85 | 85 | 2025-01-14 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M | 3 | 30UMA | 50
86 | 86 | 2025-01-14 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 15
87 | 87 | 2025-03-11 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 250
88 | 88 | 2025-03-11 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 19
89 | 89 | 2025-03-11 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 7
90 | 90 | 2025-03-13 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 200
91 | 91 | 2025-03-13 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6
92 | 92 | 2025-03-13 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 11
93 | 93 | 2025-03-14 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M |  |  | 70
94 | 94 | 2025-03-14 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 70
95 | 95 | 2025-03-14 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 7
96 | 96 | 2025-03-14 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 156
97 | 97 | 2025-03-14 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1
98 | 98 | 2025-03-14 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M |  |  | 18
99 | 99 | 2025-03-15 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 20
100 | 100 | 2025-03-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4
101 | 101 | 2025-03-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  | 30 UMA | 4
102 | 102 | 2025-03-16 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  | 40 UMA | 10
103 | 103 | 2025-03-18 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100
104 | 104 | 2025-03-18 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  |  | 100
105 | 105 | 2025-03-19 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M |  |  | 33
106 | 106 | 2025-03-20 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6
107 | 107 | 2025-03-22 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  | 10 UGB | 100
108 | 108 | 2025-03-22 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  | 10 UGB | 45
109 | 109 | 2025-03-23 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  | 10 UMA | 50
110 | 110 | 2025-03-23 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  | 10 UMA | 50
111 | 111 | 2025-03-23 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M |  | 90 UGB | 145
112 | 112 | 2025-03-23 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  | 10 UMA | 4
113 | 113 | 2025-04-06 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  | 40 UMA | 5
114 | 114 | 2025-04-08 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  | 30 UMA | 5
115 | 115 | 2025-04-08 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  | 30UMA | 125
116 | 116 | 2025-04-08 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  | 30UMA | 100
117 | 117 | 2025-04-10 | CAL-009 | Cable | CV Cable | 0 | 3C X 70+35mm2 | M |  |  | 75
118 | 118 | 2025-04-10 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA |  |  | 1
119 | 119 | 2025-04-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 2 | Hassan Mohamed
120 | 120 | 2025-04-14 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | Hassan Mohamed
121 | 121 | 2025-04-15 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 1 | Hassan Mohamed |  | PNL-008→PNL-007
122 | 122 | 2025-04-16 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 2 | Hassan Mohamed |  | PNL-008→PNL-007
123 | 123 | 2025-04-16 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  |  | 60 | Hassan Mohamed
124 | 124 | 2025-04-21 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 10UGB | 10UGB | 50 | Hassan Mohamed
125 | 125 | 2025-04-21 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 10UGB | 10UGB | 50 | Hassan Mohamed
126 | 126 | 2025-04-21 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 10UGB | 10UGB | 1 | Hassan Mohamed
127 | 127 | 2025-04-21 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 40UMA | 40UMA | 1 | Hassan Mohamed
128 | 128 | 2025-04-22 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 40UMA | 40UMA | 120 | Hassan Mohamed
129 | 129 | 2025-04-22 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 40UMA | 40UMA | 100 | Hassan Mohamed
130 | 130 | 2025-04-22 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | Hassan Mohamed
131 | 131 | 2025-04-22 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 1 | Hassan Mohamed
132 | 132 | 2025-04-23 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | Hassan Mohamed
133 | 133 | 2025-04-27 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 40 | Hassan Mohamed
134 | 134 | 2025-04-28 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M |  |  | 95 | Hassan Mohamed
135 | 135 | 2025-04-28 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA |  |  | 1 | Hassan Mohamed
136 | 136 | 2025-04-27 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | Hassan Mohamed
137 | 137 | 2025-04-29 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M |  |  | 95 | Hassan Mohamed
138 | 138 | 2025-04-29 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 200 | Hassan Mohamed
139 | 139 | 2025-04-30 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M |  |  | 80 | Hassan Mohamed
140 | 140 | 2025-05-03 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 2 | Hassan Mohamed
141 | 141 | 2025-05-03 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 1 | Hassan Mohamed
142 | 142 | 2025-05-04 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 10 | Hassan Mohamed
143 | 143 | 2025-05-04 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M |  |  | 10 | Hassan Mohamed
144 | 144 | 2025-05-05 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 75 | Hassan Mohamed
145 | 145 | 2025-05-05 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 3 | Hassan Mohamed
146 | 146 | 2025-05-05 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UMA | 2 | Hassan Mohamed
147 | 147 | 2025-05-09 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 15 | Hassan Mohamed
148 | 148 | 2025-05-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 5 | Hassan Mohamed
149 | 149 | 2025-05-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | Hassan Mohamed
150 | 150 | 2025-05-12 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 1 | Hassan Mohamed
151 | 151 | 2025-05-13 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 222 | Hassan Mohamed
152 | 152 | 2025-05-14 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | Hassan Mohamed
153 | 153 | 2025-05-14 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA |  |  | 1 | Hassan Mohamed
154 | 154 | 2025-05-15 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 280 | Hassan Mohamed
155 | 155 | 2025-05-16 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 1 | Ashour
156 | 156 | 2025-05-17 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 75 | Hassan Mohamed
157 | 157 | 2025-05-18 | GEN-006 | D/G | Generator | 0 | 50KVA | 대 |  |  | 1 | Ashour
158 | 158 | 2025-05-18 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA |  |  | 1 | Hassan Mohamed
159 | 159 | 2025-05-18 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 4 | 40UMA | 50 | Hassan Mohamed
160 | 160 | 2025-05-19 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 2 | 20USJ | 50 | Hassan Mohamed
161 | 161 | 2025-05-19 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20USJ | 6 | Hassan Mohamed
162 | 162 | 2025-05-19 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 25 | Hassan Mohamed
163 | 163 | 2025-05-21 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 2 | 20UMA | 1 | Hassan Mohamed
164 | 164 | 2025-05-21 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M | 2 | 20UMA | 20 | Hassan Mohamed
165 | 165 | 2025-05-21 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 2 | 20UMA | 4 | Hassan Mohamed
166 | 166 | 2025-05-21 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 2 | Hassan Mohamed
167 | 167 | 2025-05-21 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 21 | Hassan Mohamed
168 | 168 | 2025-05-23 | CAL-010 | Cable | CV Cable | 0 | 3C X 50+25mm2 | M |  |  | 5 | Hassan Mohamed
169 | 169 | 2025-05-23 | PNL-012 | Panel | MTS Panel | 0 | 200A | EA |  |  | 1 | Askary
170 | 170 | 2025-05-24 | PNL-012 | Panel | MTS Panel | 0 | 200A | EA |  |  | 1 | Askary
171 | 171 | 2025-05-24 | PNL-013 | Panel | MTS Panel | 0 | 100A | EA |  |  | 1 | Askary
172 | 172 | 2025-05-25 | GEN-003 | D/G | Generator | 0 | 150KVA | 대 |  |  | 1 | Ashour
173 | 173 | 2025-05-26 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1 | Hassan Mohamed
174 | 174 | 2025-05-26 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 10 | Hassan Mohamed
175 | 175 | 2025-05-26 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 10 | Hassan Mohamed
176 | 176 | 2025-05-27 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 8 | Hassan Mohamed
177 | 177 | 2025-05-27 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 8 | Hassan Mohamed
178 | 178 | 2025-05-27 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 2 | Hassan Mohamed
179 | 179 | 2025-05-26 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 25 | Hassan Mohamed
180 | 180 | 2025-05-29 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 100 | Hassan Mohamed
181 | 181 | 2025-05-31 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 500 | Hassan Mohamed
182 | 182 | 2025-06-01 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 5 | Hassan Mohamed
183 | 183 | 2025-06-03 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 51 | Hassan Mohamed
184 | 184 | 2025-06-03 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA |  |  | 1 | Hassan Mohamed
185 | 185 | 2025-06-03 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 1 | Ashour
186 | 186 | 2025-06-11 | CAL-016 | Cable | CV Cable | 0 | 3C x 10mm2 | M |  |  | 35 | Hassan Mohamed
187 | 187 | 2025-06-11 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 10 | Hassan Mohamed
188 | 188 | 2025-06-12 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 75 | Hassan Mohamed
189 | 189 | 2025-06-12 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  |  | 60 | Hassan Mohamed
190 | 190 | 2025-06-12 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M |  |  | 60 | Hassan Mohamed
191 | 191 | 2025-06-13 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  |  | 75 | Hassan Mohamed
192 | 192 | 2025-06-13 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 50 | Hassan Mohamed
193 | 193 | 2025-06-13 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 30 | Hassan Mohamed
194 | 194 | 2025-06-13 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA |  |  | 1 | Hassan Mohamed
195 | 195 | 2025-06-16 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 200 | Hassan Mohamed
196 | 196 | 2025-06-16 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 20 | Hassan Mohamed
197 | 197 | 2025-06-17 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M |  |  | 4 | Hassan Mohamed
198 | 198 | 2025-06-18 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 90 | Hassan Mohamed
199 | 199 | 2025-06-19 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M |  |  | 145 | Hassan Mohamed
200 | 200 | 2025-06-19 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 60 | Hassan Mohamed
201 | 201 | 2025-06-20 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA |  |  | 1 | Askary
202 | 202 | 2025-06-20 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 1 | Askary
203 | 203 | 2025-06-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA |  |  | 1 | Askary
204 | 204 | 2025-06-22 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA |  |  | 1 | Hassan Mohamed
205 | 205 | 2025-06-22 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1 | Hassan Mohamed
206 | 206 | 2025-06-22 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 1 | Hassan Mohamed |  | PNL-008→PNL-007
207 | 207 | 2025-06-22 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M |  |  | 60 | Hassan Mohamed
208 | 208 | 2025-06-22 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 55 | Hassan Mohamed
209 | 209 | 2025-06-24 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M |  |  | 30 | Hassan Mohamed
210 | 210 | 2025-06-30 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA |  |  | 1 | Hassan Mohamed
211 | 211 | 2025-06-30 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 17 | Hassan Mohamed
212 | 212 | 2025-06-30 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 200 | Hassan Mohamed
213 | 213 | 2025-06-30 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M |  |  | 15 | Hassan Mohamed
214 | 214 | 2025-07-01 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M |  |  | 120 | Hassan Mohamed
215 | 215 | 2025-07-01 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA |  |  | 1 | Hassan Mohamed
216 | 216 | 2025-07-02 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M |  |  | 25 | Hassan Mohamed
217 | 217 | 2025-07-02 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 60 | Hassan Mohamed
218 | 218 | 2025-07-06 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 60 | Hassan Mohamed
219 | 219 | 2025-07-06 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1 | Hassan Mohamed
220 | 220 | 2025-07-07 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 125 | Hassan Mohamed
221 | 221 | 2025-07-07 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 125 | Hassan Mohamed
222 | 222 | 2025-07-08 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1 | Hassan Mohamed
223 | 223 | 2025-07-08 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 70 | Hassan Mohamed
224 | 224 | 2025-07-09 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | hassan
225 | 225 | 2025-07-13 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | hassan
226 | 226 | 2025-07-13 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 2 | hassan
227 | 227 | 2025-07-13 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M |  |  | 35 | hassan
228 | 228 | 2025-07-16 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 3 | hassan
229 | 229 | 2025-07-16 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA |  |  | 1 | hassan
230 | 230 | 2025-07-16 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 100 | hassan
231 | 231 | 2025-07-16 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 95 | hassan
232 | 232 | 2025-07-16 | CAL-005 | Cable | AL Cable | 0 | 3C x 70+35mm2 [ALU] | M |  |  | 75 | hassan
233 | 233 | 2025-07-17 | GEN-003 | D/G | Generator | 0 | 150KVA | 대 |  |  | 1 | RAMY
234 | 234 | 2025-07-20 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1 | hassan
235 | 235 | 2025-07-20 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 79 | hassan
236 | 236 | 2025-07-21 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 100 | hassan
237 | 237 | 2025-07-21 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA |  |  | 1 | hassan
238 | 238 | 2025-07-21 | GEN-003 | D/G | Generator | 0 | 150KVA | 대 |  |  | 1 | Ashour
239 | 239 | 2025-07-22 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 12 | hassan
240 | 240 | 2025-07-22 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 10 | hassan
241 | 241 | 2025-07-24 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | hassan
242 | 242 | 2025-07-24 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 2 | hassan
243 | 243 | 2025-07-24 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | hassan
244 | 244 | 2025-07-28 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 5 | hassan
245 | 245 | 2025-07-29 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 165 | hassan
246 | 246 | 2025-07-29 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 20 | hassan
247 | 247 | 2025-07-30 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 1 | Ashour
248 | 248 | 2025-08-03 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 2 | hassan
249 | 249 | 2025-08-03 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 140 | hassan
250 | 250 | 2025-08-04 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 45 | hassan
251 | 251 | 2025-08-04 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 150 | hassan
252 | 252 | 2025-08-04 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 1 | hassan
253 | 253 | 2025-08-04 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 10 | hassan
254 | 254 | 2025-08-04 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6 | hassan
255 | 255 | 2025-08-04 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 6 | hassan
256 | 256 | 2025-08-05 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M |  |  | 85 | hassan
257 | 257 | 2025-08-05 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | hassan
258 | 258 | 2025-08-05 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | hassan
259 | 259 | 2025-08-05 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 15 | hassan
260 | 260 | 2025-08-05 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | hassan
261 | 261
262 | 262 | 2025-08-07 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 125 | hassan
263 | 263 | 2025-08-07 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | hassan
264 | 264 | 2025-08-07 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 5 | hassan
265 | 265 | 2025-08-07 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 10 | hassan
266 | 266 | 2025-08-07 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 200 | hassan
267 | 267 | 2025-08-09 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 2 | hassan
268 | 268 | 2025-08-10 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6 | hassan
269 | 269 | 2025-08-10 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 6 | hassan
270 | 270 | 2025-08-10 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | hassan
271 | 271 | 2025-08-13 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 3 | hassan
272 | 272 | 2025-08-17 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M |  |  | 260 | hassan
273 | 273 | 2025-08-18 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 10 | hassan
274 | 274 | 2025-08-19 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 45 | hassan
275 | 275 | 2025-08-20 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 1 | ASHOUR | Maintenance At Cairo
276 | 276 | 2025-08-24 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M |  |  | 130 | Hassan
277 | 277 | 2025-08-25 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  |  | 10 | Hassan
278 | 278 | 2025-08-25 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 128 | Hassan
279 | 279 | 2025-08-25 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 100 | Hassan
280 | 280 | 2025-08-26 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 |  |  | 1 | ASHOUR | Maintenance At Cairo
281 | 281 | 2025-08-26 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M |  |  | 37 | Hassan
282 | 282 | 2025-08-27 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 50 | Hassan
283 | 283 | 2025-08-27 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M |  |  | 50 | Hassan
284 | 284 | 2025-09-02 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 2 | Hassan
285 | 285 | 2025-09-02 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | Hassan
286 | 286 | 2025-09-02 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
287 | 287 | 2025-09-07 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
288 | 288 | 2025-09-08 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA |  |  | 1 | Hassan
289 | 289 | 2025-09-08 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 95 | Hassan
290 | 290 | 2025-09-09 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M |  |  | 40 | Hassan
291 | 291 | 2025-09-09 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 120 | Hassan
292 | 292 | 2025-09-10 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
293 | 293 | 2025-09-10 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6 | Hassan
294 | 294 | 2025-09-12 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 18 | Alaskary
295 | 295 | 2025-09-12 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Alaskary
296 | 296 | 2025-09-13 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 130 | Alaskary
297 | 297 | 2025-09-14 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 8 | Hassan
298 | 298 | 2025-09-14 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | Hassan
299 | 299 | 2025-09-14 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 75 | Hassan
300 | 300 | 2025-09-14 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  |  | 10 | Hassan
301 | 301 | 2025-09-15 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  |  | 11 | Hassan
302 | 302 | 2025-09-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 3 | Hassan
303 | 303 | 2025-09-17 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 5 | Hassan
304 | 304 | 2025-09-17 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 2 | Hassan
305 | 305 | 2025-09-17 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
306 | 306 | 2025-09-17 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 16 | Hassan
307 | 307 | 2025-09-18 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | Hassan
308 | 308 | 2025-09-18 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 1 | Hassan
309 | 309 | 2025-09-18 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 10 | Hassan
310 | 310 | 2025-09-19 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 5 | Hassan
311 | 311 | 2025-09-19 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 2 | Hassan
312 | 312 | 2025-09-19 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA |  |  | 2 | Hassan
313 | 313 | 2025-09-20 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | Hassan
314 | 314 | 2025-09-21 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | Hassan
315 | 315 | 2025-09-22 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | Hassan
316 | 316 | 2025-09-22 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6 | Hassan
317 | 317 | 2025-09-22 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 100 | Hassan
318 | 318 | 2025-09-22 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 100 | Hassan
319 | 319 | 2025-09-22 | GEN-006 | D/G | Generator | 0 | 50KVA | 대 |  |  | 1 | Hassan
320 | 320 | 2025-09-23 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 100 | Hassan
321 | 321 | 2025-09-23 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 1 | Hassan
322 | 322 | 2025-09-23 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M |  |  | 45 | Hassan
323 | 323 | 2025-09-23 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 1 | Hassan
324 | 324 | 2025-09-23 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 1 | Hassan
325 | 325 | 2025-09-24 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 150 | Hassan
326 | 326 | 2025-09-24 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6 | Hassan
327 | 327 | 2025-09-25 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 6 | Hassan
328 | 328 | 2025-09-25 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | Hassan
329 | 329 | 2025-09-25 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
330 | 330 | 2025-09-25 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
331 | 331 | 2025-09-26 | PNL-007 | Panel | Electrical Panel | 0 | 125A | EA |  |  | 1 | Askary
332 | 332 | 2025-09-27 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | Askary
333 | 333 | 2025-09-27 | GEN-006 | D/G | Generator | 0 | 50KVA | 대 |  |  | 1 | Ashour
334 | 334 | 2025-09-28 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 20 | Hassan
335 | 335 | 2025-09-28 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 100 | Hassan
336 | 336 | 2025-09-28 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 10 | Hassan
337 | 337 | 2025-09-28 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 4 | Hassan
338 | 338 | 2025-09-29 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA |  |  | 2 | Hassan
339 | 339 | 2025-09-29 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M |  |  | 10 | Hassan
340 | 340 | 2025-09-29 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA |  |  | 4 | Hassan
341 | 341 | 2025-09-30 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40UMA | 2 | Hassan
342 | 342 | 2025-09-30 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 2 | Hassan
343 | 343 | 2025-09-30 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 3 | 30UMA | 75 | Hassan
344 | 344 | 2025-09-30 | CAL-016 | Cable | CV Cable | 0 | 3C x 10mm2 | M | 3 | 30UMA | 95 | Hassan
345 | 345 | 2025-10-01 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 3 | 30UMA | 126 | Hassan
346 | 346 | 2025-10-02 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 200 | Hassan
347 | 347 | 2025-10-03 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 3 | 30UMA | 40 | Hassan
348 | 348 | 2025-10-03 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 4 | 30UMA | 70 | Hassan
349 | 349 | 2025-10-03 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 1 | 10UGB | 1 | Hassan
350 | 350 | 2025-10-06 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USJ | 15 | Hassan
351 | 351 | 2025-10-06 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 3 | 30USG | 2 | Hassan
352 | 352 | 2025-10-06 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 3 | 30UMA | 1 | Hassan
353 | 353 | 2025-10-06 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 600 | Hassan
354 | 354 | 2025-10-07 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 6 | Hassan
355 | 355 | 2025-10-07 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30UMA | 4 | Hassan
356 | 356 | 2025-10-07 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 3 | 30UMA | 5 | Hassan
357 | 357 | 2025-10-07 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30UMA | 200 | Hassan
358 | 358 | 2025-10-07 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 3 | 30USG | 14 | Hassan
359 | 359 | 2025-10-08 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10UMA | 300 | Hassan
360 | 360 | 2025-10-08 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1 | 10UMA | 80 | Hassan
361 | 361 | 2025-10-09 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 20 | Hassan
362 | 362 | 2025-10-09 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 4 | Hassan
363 | 363 | 2025-10-09 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 110 | Hassan
364 | 364 | 2025-10-09 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 100 | Hassan
365 | 365 | 2025-10-10 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 5 | ASKARY
366 | 366 | 2025-10-10 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USG | 2 | ASKARY
367 | 367 | 2025-10-10 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 45 | ASKARY
368 | 368 | 2025-10-10 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 2 | ASKARY
369 | 369 | 2025-10-10 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 4 | ASKARY
370 | 370 | 2025-10-11 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 8 | ASKARY
371 | 371 | 2025-10-11 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 100 | Askary
372 | 372 | 2025-10-11 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30USG | 200 | Askary
373 | 373 | 2025-10-12 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 10 | Hassan
374 | 374 | 2025-10-12 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 10 | Hassan
375 | 375 | 2025-10-12 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40UMA | 4 | Hassan
376 | 376 | 2025-10-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10USJ | 5 | Hassan
377 | 377 | 2025-10-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 5 | Hassan
378 | 378 | 2025-10-12 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30USG | 1 | Hassan
379 | 379 | 2025-10-12 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30UMA | 300 | Hassan
380 | 380 | 2025-10-13 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 100 | Hassan
381 | 381 | 2025-10-13 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 8 | Hassan
382 | 382 | 2025-10-13 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 2 | Hassan
383 | 383 | 2025-10-13 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30UMA | 290 | Hassan
384 | 384 | 2025-10-13 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 200 | Hassan
385 | 385 | 2025-10-14 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USG | 2 | Hassan
386 | 386 | 2025-10-15 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 200 | Hassan
387 | 387 | 2025-10-15 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 6 | Hassan
388 | 388 | 2025-10-15 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 6 | Hassan
389 | 389 | 2025-10-15 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 4 | 40UMA | 1 | Hassan
390 | 390 | 2025-10-15 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UGB | 13 | Hassan
391 | 391 | 2025-10-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 4 | Hassan
392 | 392 | 2025-10-16 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1 | 10UGB | 2 | Hassan
393 | 393 | 2025-10-16 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1 | 10UMA | 1 | Hassan
394 | 394 | 2025-10-16 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 2 | 20UMA | 100 | Hassan
395 | 395 | 2025-10-16 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30USG | 10 | Hassan
396 | 396 | 2025-10-16 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 3 | 30UMA | 40 | Hassan
397 | 397 | 2025-10-17 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 3 | 30UMA | 107 | Hassan
398 | 398 | 2025-10-17 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 2 | Hassan
399 | 399 | 2025-10-18 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 3 | 30UMA | 25 | Hassan
400 | 400 | 2025-10-18 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 12 | Hassan
401 | 401 | 2025-10-19 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 3 | 30UMA | 1 | Hassan
402 | 402 | 2025-10-19 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | 1 | 10UMA | 2 | Hassan
403 | 403 | 2025-10-19 | MCB-002 | MCB | MCB | 0 | 1P - 25A | EA | 4 | 40UMA | 1 | Hassan
404 | 404 | 2025-10-19 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | 3 | 30UMA | 1 | Hassan
405 | 405 | 2025-10-19 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 2 | 20UMA | 6 | Hassan
406 | 406 | 2025-10-20 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 1 | 10UMA | 1 | Hassan
407 | 407 | 2025-10-20 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UGB | 20 | Hassan
408 | 408 | 2025-10-20 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1 | 10USJ | 85 | Hassan
409 | 409 | 2025-10-20 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 100 | Hassan
410 | 410 | 2025-10-20 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30USG | 150 | Hassan
411 | 411 | 2025-10-21 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 274 | Hassan
412 | 412 | 2025-10-21 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 1 | 10UMA | 30 | Hassan
413 | 413 | 2025-10-21 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10UMA | 200 | Hassan
414 | 414 | 2025-10-21 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10UMA | 100 | Hassan
415 | 415 | 2025-10-21 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1 | 10UMA | 75 | Hassan
416 | 416 | 2025-10-22 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30UMA | 100 | Hassan
417 | 417 | 2025-10-22 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 2 | 20UMA | 100 | Hassan
418 | 418 | 2025-10-22 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 100 | Hassan
419 | 419 | 2025-10-22 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 1 | 10UGB | 1 | Hassan
420 | 420 | 2025-10-23 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 5 | Hassan
421 | 421 | 2025-10-23 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4 | 40UMA | 100 | Hassan
422 | 422 | 2025-10-23 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10UGB | 150 | Hassan
423 | 423 | 2025-10-24 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 100 | ASKRY
424 | 424 | 2025-10-24 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10UGB | 150 | ASKRY
425 | 425 | 2025-10-25 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 11 | ASKRY
426 | 426 | 2025-10-25 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30UMA | 130 | ASKRY
427 | 427 | 2025-10-25 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 50 | ASKRY
428 | 428 | 2025-10-26 | PNL-010 | Panel | Electrical Panel | 0 | 50A | EA | 3 | 30UMA | 1 | ASKRY
429 | 429 | 2025-10-26 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 22 | ASKRY
430 | 430 | 2025-10-26 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10UMA | 200 | ASKRY
431 | 431 | 2025-10-26 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30UMA | 26 | ASKRY
432 | 432 | 2025-10-27 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 30UMA | 14 | ASKRY
433 | 433 | 2025-10-27 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10UGB | 10 | ASKRY
434 | 434 | 2025-10-28 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30USJ | 5 | Hassan
435 | 435 | 2025-10-28 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30USG | 100 | Hassan
436 | 436 | 2025-10-28 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 3 | 30UMA | 185 | Hassan
437 | 437 | 2025-10-29 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30USG | 54 | Hassan
438 | 438 | 2025-10-29 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 50 | Hassan
439 | 439 | 2025-10-29 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 1 | 10UMA | 100 | Hassan
440 | 440 | 2025-10-29 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 4 | 40UMA | 1 | Hassan
441 | 441 | 2025-10-29 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | 4 | 40UGB | 1 | Hassan
442 | 442 | 2025-10-30 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UGB | 12 | Hassan
443 | 443 | 2025-10-30 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 8 | Hassan
444 | 444 | 2025-10-30 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 35 | Hassan
445 | 445 | 2025-10-30 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 1 | 10UMA | 30 | Hassan
446 | 446 | 2025-11-02 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 7 | Hassan
447 | 447 | 2025-11-02 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 1 | 10UMA | 18 | Hassan
448 | 448 | 2025-11-03 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 14 | Hassan
449 | 449 | 2025-11-03 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 2 | 20UMA | 30 | Hassan
450 | 450 | 2025-11-06 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10UMA | 100 | Hassan
451 | 451 | 2025-11-06 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 1 | 10UGB | 100 | Hassan
452 | 452 | 2025-11-06 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30UMA | 1 | Hassan
453 | 453 | 2025-11-07 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 3 | 30USG | 100 | ASKRY
454 | 454 | 2025-11-07 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30UMA | 300 | ASKRY
455 | 455 | 2025-11-07 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 3 | 30USG | 200 | ASKRY
456 | 456 | 2025-11-07 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30UMA | 2 | ASKRY
457 | 457 | 2025-11-08 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10UMA | 300 | ASKRY
458 | 458 | 2025-11-08 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 4 | 40UGB | 500 | ASKRY
459 | 459 | 2025-11-08 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 4 | 40UMA | 300 | ASKRY
460 | 460 | 2025-11-09 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UGB | 200 | ASKRY
461 | 461 | 2025-11-10 | CAL-003 | Cable | AL Cable | 0 | 3C x 120+70mm2 [ALU] | M | 2 | 20UGB | 210 | Hassan
462 | 462 | 2025-11-10 | CAL-005 | Cable | AL Cable | 0 | 3C x 70+35mm2 [ALU] | M | 3 | 30UMA | 202 | Hassan
463 | 463 | 2025-11-10 | CAL-024 | Cable | Grounding Cable | 0 | 1C x 25mm2 | M | 1 | 10UGB | 210 | Hassan
464 | 464 | 2025-11-11 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4 | 40UMA | 500 | Hassan
465 | 465 | 2025-11-12 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 500 | Hassan
466 | 466 | 2025-11-13 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 496 | Hassan
467 | 467 | 2025-11-17 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1 | 10UGB | 90 | Hassan
468 | 468 | 2025-11-17 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10UMA | 1 | Hassan
469 | 469 | 2025-11-18 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 1 | 10UMA | 130 | Hassan
470 | 470 | 2025-11-23 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 1 | 10UGB | 125 | ASKRY
471 | 471 | 2025-11-23 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 1 | 10UMA | 90 | ASKRY
472 | 472 | 2025-11-23 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 4 | 40UGB | 5 | ASKRY
473 | 473 | 2025-11-23 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UMA | 40 | ASKRY
474 | 474 | 2025-11-23 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UGB | 2 | ASKRY
475 | 475 | 2025-11-25 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 10 | Hassan
476 | 476 | 2025-11-26 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UGB | 50 | Hassan
477 | 477 | 2025-11-26 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UGB | 10 | Hassan
478 | 478 | 2025-11-26 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | C | CEB | 63 | Hassan
479 | 479 | 2025-11-30 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10UMA | 1 | Hassan
480 | 480 | 2025-11-30 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UMA | 20 | Hassan
481 | 481 | 2025-11-30 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UGB | 2 | Hassan
482 | 482 | 2025-11-30 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1 | 10UMA | 1 | Hassan
483 | 483 | 2025-11-30 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 4 | 40UGB | 1 | Hassan
484 | 484 | 2025-12-01 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 4 | 40UMA | 70 | Hassan
485 | 485 | 2025-12-02 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UGB | 13 | Hassan
486 | 486 | 2025-12-02 | CAL-002 | Cable | AL Cable | 0 | 3C x 150+70mm2 [ALU] | M | 2 | 20UGB | 60 | Hassan
487 | 487 | 2025-12-02 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 3 | Hassan
488 | 488 | 2025-12-02 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 4 | 40UGB | 3 | Hassan
489 | 489 | 2025-12-02 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 1 | 10UGB | 1 | Hassan
490 | 490 | 2025-12-03 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 4 | 40UMA | 4 | Hassan
491 | 491 | 2025-12-03 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 20 | Hassan
492 | 492 | 2025-12-03 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 2 | 20UMA | 12 | Hassan
493 | 493 | 2025-12-03 | CAL-020 | Cable | CV Cable | 0 | 3C x 1.5mm2 | M | 1 | 10UGB | 20 | Hassan
494 | 494 | 2025-12-04 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 4 | 40UGB | 25 | Hassan
495 | 495 | 2025-12-04 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 4 | 40UMA | 10 | Hassan
496 | 496 | 2025-12-05 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 2 | ASKRY
497 | 497 | 2025-12-08 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | C |  | 10 | Hassan
498 | 498 | 2025-12-09 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UMA | 1 | Hassan
499 | 499 | 2025-12-10 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UMA | 4 | Hassan
500 | 500 | 2025-12-10 | PNL-015 | Panel | MTS Panel | 0 | 250A | EA | 1 | 10UMA | 1 | Hassan
501 | 501 | 2025-12-11 | PNL-015 | Panel | MTS Panel | 0 | 250A | EA | 3 | 30UMA | 1 | Hassan
502 | 502 | 2025-12-12 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10UGB | 2 | Hassan
503 | 503 | 2025-12-14 | CAL-026 | Cable | Grounding Cable | 0 | 1C x 10mm2 | M | 4 | 40UMA | 10 | Hassan
504 | 504 | 2025-12-15 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 50 | Hassan
505 | 505 | 2025-12-16 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 2 | 20UMA | 8 | Hassan
506 | 506 | 2025-12-16 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UGB | 12 | Hassan
507 | 507 | 2025-12-17 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 1 | 10UMA | 1 | Hassan
508 | 508 | 2025-12-17 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 4 | 40UGB | 6 | Hassan
509 | 509 | 2025-12-17 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40UMA | 3 | Hassan
510 | 510 | 2025-12-17 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 1 | 10UGB | 10 | Hassan
511 | 511 | 2025-12-08 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UGB | 20 | Hassan
512 | 512 | 2025-12-20 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 10 | Hassan
513 | 513 | 2025-12-20 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 20 | Hassan
514 | 514 | 2025-12-21 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UGB | 9 | Hassan
515 | 515 | 2025-12-22 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 4 | 40UMA | 14 | Hassan
516 | 516 | 2025-12-22 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 50 | Hassan
517 | 517 | 2025-12-22 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | 2 | 20UMA | 1 | Hassan
518 | 518 | 2025-12-23 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 1 | 10UGB | 1 | Hassan
519 | 519 | 2025-12-23 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UGB | 200 | Hassan
520 | 520 | 2025-12-24 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30UMA | 1 | Hassan
521 | 521 | 2025-12-24 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 4 | 40UMA | 15 | Hassan
522 | 522 | 2025-12-24 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | 1 | 10UMA | 1 | Hassan
523 | 523 | 2025-12-25 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 3 | 30UMA | 2 | Hassan
524 | 524 | 2025-12-25 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UMA | 3 | Hassan
525 | 525 | 2025-12-25 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA | 1 | 10UGB | 4 | Hassan
526 | 526 | 2025-12-25 | PLG-003 | power plug | Industrial Socket | 0 | 5P - 32A | EA | 2 | 20UGB | 2 | Hassan
527 | 527 | 2025-12-26 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA | 3 | 30UMA | 1 | Hassan
528 | 528 | 2025-12-27 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | C | 90UFT | 2 | Hassan
529 | 529 | 2025-12-27 | CAL-007 | Cable | AL Cable | 0 | 4C x 35mm2 [ALU] | M | 2 | 20UMA | 145 | Hassan
530 | 530 | 2025-12-27 | GEN-006 | D/G | Generator | 0 | 50KVA | 대 | C | 90UFT | 1 | Hassan | 수리후 불출
531 | 531 | 2025-12-28 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | C | 90UFT | 1 | Hassan
532 | 532 | 2025-12-28 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 2 | 20UMA | 200 | Hassan
533 | 533 | 2025-12-29 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UGB | 300 | Hassan
534 | 534 | 2025-12-30 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 2 | 20UGB | 100 | Hassan
535 | 535 | 2025-12-30 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA | 3 | 30UMA | 8 | Hassan
536 | 536 | 2025-12-30 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 4 | 40UMA | 100 | Hassan
537 | 537 | 2025-12-30 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 1 | Hassan
538 | 538 | 2026-01-01 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | C |  | 3 | Hassan | RETURN 7EA
539 | 539 | 2026-01-01 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 100 | Hassan
540 | 540 | 2026-01-02 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 200 | Hassan
541 | 541 | 2026-01-03 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UGB | 4 | Hassan
542 | 542 | 2026-01-05 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | C |  | 5 | Hassan | RETURN 30EA
543 | 543 | 2026-01-06 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UGB | 300 | Hassan
544 | 544 | 2026-01-06 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 2 | 20UGB | 100 | Hassan
545 | 545 | 2026-01-07 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30USJ | 1 | Hassan
546 | 546 | 2026-01-07 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30UMA | 14 | Hassan
547 | 547 | 2026-01-08 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 2 | 20UMA | 1 | Hassan
548 | 548 | 2026-01-09 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UGB | 7 | Hassan
549 | 549 | 2026-01-10 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 3 | 30USJ | 1 | Hassan
550 | 550 | 2026-01-10 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UMA | 100 | Hassan
551 | 551 | 2026-01-10 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 104 | Hassan
552 | 552 | 2026-01-11 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 100 | Hassan
553 | 553 | 2026-01-11 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UMA | 13 | Hassan
554 | 554 | 2026-01-12 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | C |  | 400 | Hassan
555 | 555 | 2026-01-12 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UGB | 50 | Hassan
556 | 556 | 2026-01-13 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 1 | 10UGB | 90 | Hassan
557 | 557 | 2026-01-15 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 2 | Hassan
558 | 558 | 2026-01-16 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UGB | 9 | Hassan
559 | 559 | 2026-01-18 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10USJ | 14 | Hassan
560 | 560 | 2026-01-18 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 12 | Hassan
561 | 561 | 2026-01-19 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10USJ | 6 | Hassan
562 | 562 | 2026-01-19 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 10 | Hassan | Doosan civil
563 | 563 | 2026-01-20 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UGB | 20 | Hassan
564 | 564 | 2026-01-20 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 6 | Hassan
565 | 565 | 2026-01-20 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 10 | Hassan
566 | 566 | 2026-01-20 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 10 | Hassan | Doosan civil
567 | 567 | 2026-01-20 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | c |  | 200 | Hassan
568 | 568 | 2026-01-21 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 4 | Hassan
569 | 569 | 2026-01-21 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 70 | Hassan
570 | 570 | 2026-01-21 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10UMA | 7 | Hassan
571 | 571 | 2026-01-22 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10UGB | 12 | Hassan
572 | 572 | 2026-01-22 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10UGB | 100 | Hassan
573 | 573 | 2026-01-22 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10UGB | 200 | Hassan
574 | 574 | 2026-01-22 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10UGB | 1 | Hassan
575 | 575 | 2026-01-23 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 6 | Hassan
576 | 576 | 2026-01-23 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UMA | 100 | Hassan
577 | 577 | 2026-01-23 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 |  | 200 | Hassan
578 | 578 | 2026-01-24 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 14 | Hassan
579 | 579 | 2026-01-25 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UGB | 4 | Hassan
580 | 580 | 2026-01-26 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10UGB | 1 | Hassan
581 | 581 | 2026-01-26 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 3 | 30UGB | 2 | Hassan
582 | 582 | 2026-01-26 | MCB-007 | MCB | RCBO | 0 | 1P + N -25A - 30 mA | EA | 3 | 30UGB | 1 | Hassan
583 | 583 | 2026-01-27 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 15 | Hassan
584 | 584 | 2026-01-28 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30UMA | 100 | Hassan
585 | 585 | 2026-01-28 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 6 | Hassan
586 | 586 | 2026-01-28 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10UGB | 1 | Hassan
587 | 587 | 2026-01-28 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 1 | Hassan
588 | 588 | 2026-01-31 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 3 | 30UMA | 50 | Hassan
589 | 589 | 2026-02-01 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1 | 10UMA | 1 | Hassan
590 | 590 | 2026-02-01 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30UMA | 100 | Hassan
591 | 591 | 2026-02-02 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 13 | Hassan
592 | 592 | 2026-02-03 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UMA | 12 | Hassan
593 | 593 | 2026-02-03 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 10 | Hassan
594 | 594 | 2026-02-03 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40UMA | 4 | Hassan
595 | 595 | 2026-02-03 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 1 | 10UGB | 1 | Hassan
596 | 596 | 2026-02-04 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10UGB | 100 | Hassan
597 | 597 | 2026-02-04 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UGB | 100 | Hassan
598 | 598 | 2026-02-04 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M |  | SHOP | 470 | Hassan
599 | 599 | 2026-02-04 | CAL-028 | Cable | AL Cable | 0 | 3C x 185+95mm2 [ALU] | M |  | SHOP | 262 | Hassan
600 | 600 | 2026-02-05 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40UMA | 8 | Hassan
601 | 601 | 2026-02-05 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UGB | 200 | Hassan
602 | 602 | 2026-02-05 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UGB | 2 | Hassan
603 | 603 | 2026-02-07 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 3 | 30UGB | 50 | Hassan
604 | 604 | 2026-02-07 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 3 | 30UGB | 1 | Hassan
605 | 605 | 2026-02-08 | GEN-001 | D/G | Generator | 0 | 400KVA | 대 |  | KHNP | 1 | Hassan
606 | 606 | 2026-02-08 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 2 | 20UMA | 50 | Hassan
607 | 607 | 2026-02-08 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 2 | 20UMA | 10 | ASKRY
608 | 608 | 2026-02-08 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 4 | 40UMA | 1 | ASKRY
609 | 609 | 2026-02-09 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30UMA | 7 | ASKRY
610 | 610 | 2026-02-09 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 2 | 20UMA | 2 | ASKRY
611 | 611 | 2026-02-10 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 3 | ASKRY
612 | 612 | 2026-02-10 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 2 | 20UMA | 15 | ASKRY
613 | 613 | 2026-02-10 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 8 | ASKRY
614 | 614 | 2026-02-11 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USJ | 12 | ASKRY
615 | 615 | 2026-02-11 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA | 3 | 30UMA | 1 | ASKRY
616 | 616 | 2026-02-11 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 1 | 10UMA | 1 | Hassan
617 | 617 | 2026-02-11 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 1 | 10UGB | 140 | Hassan
618 | 618 | 2026-02-11 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 1 | 10UGB | 12 | Hassan
619 | 619 | 2026-02-11 | CAL-001 | Cable | AL Cable | 0 | 3C x 240+120mm2 [ALU] | M | 2 | 20UMA | 12 | Hassan
620 | 620 | 2026-02-11 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USJ | 7 | Hassan
621 | 621 | 2026-02-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20USG | 10 | Hassan
622 | 622 | 2026-02-12 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 100 | Hassan
623 | 623 | 2026-02-12 | MCB-012 | MCB | MCCB | 0 | 160 A ( adj. magnetic) | EA | s | Store | 2 | ASKRY
624 | 624 | 2026-02-12 | MCB-013 | MCB | MCCB | 0 | 250 A ( adj. magnetic) | EA | S | Store | 2 | ASKRY
625 | 625 | 2026-02-12 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 5 | ASKRY
626 | 626 | 2026-02-13 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 4 | 40UMA | 1 | ASKRY
627 | 627 | 2026-02-15 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UGB | 7 | Rady
628 | 628 | 2026-02-15 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UGB | 8 | Rady
629 | 629 | 2026-02-15 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10USG | 26 | Rady
630 | 630 | 2026-02-15 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10USG | 9 | Rady
631 | 631 | 2026-02-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USJ | 10 | Rady
632 | 632 | 2026-02-16 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 200 | Rady
633 | 633 | 2026-02-16 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 200 | Rady
634 | 634 | 2026-02-16 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UMA | 50 | Rady
635 | 635 | 2026-02-16 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 2 | 20UMA | 15 | Rady
636 | 636 | 2026-02-16 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 100 | Rady
637 | 637 | 2026-02-16 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 100 | Rady
638 | 638 | 2026-02-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 4 | Rady
639 | 639 | 2026-02-16 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30USJ | 9 | Rady
640 | 640 | 2026-02-16 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30UMA | 200 | Rady
641 | 641 | 2026-02-17 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 4 | Rady
642 | 642 | 2026-02-17 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | C | 90UGG | 5 | Rady
643 | 643 | 2026-02-17 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 2 | 20UMA | 1 | Rady
644 | 644 | 2026-02-17 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10USG | 1 | Rady
645 | 645 | 2026-02-17 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | C | 90UGG | 200 | Rady
646 | 646 | 2026-02-17 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UMA | 10 | Rady
647 | 647 | 2026-02-17 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | C | 90UGG | 10 | Rady
648 | 648 | 2026-02-17 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | C | 90UGG | 5 | Rady
649 | 649 | 2026-02-17 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40UMA | 7 | Rady
650 | 650 | 2026-02-18 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 20 | Rady
651 | 651 | 2026-02-18 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 300 | Rady
652 | 652 | 2026-02-18 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30USJ | 4
653 | 653 | 2026-02-18 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 5
654 | 654 | 2026-02-19 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 2 | 20UMA | 3
655 | 655 | 2026-02-19 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10USG | 4
656 | 656 | 2026-02-19 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10USG | 2
657 | 657 | 2026-02-19 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30USJ | 100
658 | 658 | 2026-02-20 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30UMA | 5
659 | 659 | 2026-02-21 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10USJ | 1
660 | 660 | 2026-02-21 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 2 | 20UMA | 100
661 | 661 | 2026-02-21 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30USJ | 100
662 | 662 | 2026-02-22 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20USG | 6
663 | 663 | 2026-02-22 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UMA | 8
664 | 664 | 2026-02-22 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 4 | 40USG | 100
665 | 665 | 2026-02-22 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4 | 40USG | 50
666 | 666 | 2026-02-22 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 4 | 40USG | 6
667 | 667 | 2026-02-23 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40USG | 2
668 | 668 | 2026-02-23 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30USG | 200
669 | 669 | 2026-02-23 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30USG | 100
670 | 670 | 2026-02-23 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | CEB | KHNP | 2
671 | 671 | 2026-02-23 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UMA | 16
672 | 672 | 2026-02-23 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UMA | 130
673 | 673 | 2026-02-23 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 2 | 20UMA | 1
674 | 674 | 2026-02-24 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 4 | 40UMA | 100
675 | 675 | 2026-02-24 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30USJ | 100
676 | 676 | 2026-02-24 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 3 | 30UMA | 70
677 | 677 | 2026-02-24 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10USG | 5
678 | 678 | 2026-02-25 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10USG | 8
679 | 679 | 2026-02-25 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | 3 | 30USJ | 1
680 | 680 | 2026-02-25 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30USG | 1
681 | 681 | 2026-02-25 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4 | 40USG | 100
682 | 682 | 2026-02-25 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40USG | 1
683 | 683 | 2026-02-26 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 4 | 40UMA | 20
684 | 684 | 2026-02-26 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 3 | 30USJ | 184
685 | 685 | 2026-02-26 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 3 | 30UMA | 2
686 | 686 | 2026-02-26 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10USG | 18
687 | 687 | 2026-02-26 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10USG | 500
688 | 688 | 2026-02-26 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30USJ | 420
689 | 689 | 2026-02-27 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | CEB | KHNP | 1
690 | 690 | 2026-02-28 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 3 | 30USJ | 9
691 | 691 | 2026-02-28 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 3 | 30UMA | 4
692 | 692 | 2026-02-28 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 1 | 10USJ | 68
693 | 693 | 2026-03-01 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 2 | 20UMA | 3
694 | 694 | 2026-03-01 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30USJ | 5
695 | 695 | 2026-03-02 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 2 | 20USG | 1
696 | 696 | 2026-03-03 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 4 | 40UMA | 1
697 | 697 | 2026-03-03 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 4 | 40UMA | 171
698 | 698 | 2026-03-03 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 2 | 20UMA | 167
699 | 699 | 2026-03-03 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30USJ | 289
700 | 700 | 2026-03-04 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20USG | 273
701 | 701 | 2026-03-07 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M |  |  | 200
702 | 702 | 2026-03-08 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 1 | 10UGB | 1
703 | 703 | 2026-03-08 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA | 1 | 10UMA | 1
704 | 704 | 2026-03-09 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 2 | 20UMA | 1
705 | 705 | 2026-03-09 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 2 | 20UMA | 70
706 | 706 | 2026-03-09 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 57
707 | 707 | 2026-03-09 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | C |  | 4
708 | 708 | 2026-03-09 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | C | KHNP | 100
709 | 709 | 2026-03-10 | PNL-002 | Panel | Electrical Panel | 0 | 630A | EA | 2 | 20UMA | 1
710 | 710 | 2026-03-10 | CAL-001 | Cable | AL Cable | 0 | 3C x 240+120mm2 [ALU] | M | 2 | 20UMA | 12
711 | 711 | 2026-03-10 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 2 | 20UMA | 10
712 | 712 | 2026-03-11 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30USJ | 2
713 | 713 | 2026-03-11 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 3 | 30UMA | 3
714 | 714 | 2026-03-12 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10USJ | 3
715 | 715 | 2026-03-12 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 2 | 20UMA | 12
716 | 716 | 2026-03-13 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 3 | 30USJ | 11
717 | 717 | 2026-03-15 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20USG | 5
718 | 718 | 2026-03-15 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 4 | 40UMA | 100
719 | 719 | 2026-03-15 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 4 | 40UMA | 100
720 | 720 | 2026-03-15 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 2 | 20UMA | 100
721 | 721 | 2026-03-15 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 3 | 30USJ | 100
722 | 722 | 2026-03-15 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 100
723 | 723 | 2026-03-16 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UMA | 5
724 | 724 | 2026-03-16 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 200
725 | 725 | 2026-03-16 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 2 | 20UMA | 0 |  | return
726 | 726 | 2026-03-18 | PNL-004 | Panel | Electrical Panel | 0 | 300A | EA | 2 | 20UMA | 1
727 | 727 | 2026-03-18 | CAL-028 | Cable | AL Cable | 0 | 3C x 185+95mm2 [ALU] | M | 2 | 20UMA | 70
728 | 728 | 2026-03-18 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | C |  | 50
729 | 729 | 2026-03-19 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | C |  | 3 | HASSAN MAHDY
730 | 730 | 2026-03-24 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | C |  | 5 | MOHAMED KHALIL
731 | 731 | 2026-03-24 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 1 | 10UMA | 50 | RADI
732 | 732 | 2026-03-24 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | C |  | 3 | RADI
733 | 733 | 2026-03-24 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 1 | RADI
734 | 734 | 2026-03-26 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | CEB | KHNP | 4 | RADI
735 | 735 | 2026-03-26 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 1 | 10UMA | 10 | RADI
736 | 736 | 2026-03-26 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 10 | RADI
737 | 737 | 2026-03-27 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 1 | 10UGB | 10 | RADI
738 | 738 | 2026-03-27 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UGB | 3 | RADI
739 | 739 | 2026-03-27 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UGB | 1 | RADI
740 | 740 | 2026-03-27 | CAL-028 | Cable | AL Cable | 0 | 3C x 185+95mm2 [ALU] | M | 3 | 30UMA | 45 | HASSAN MAHDY
741 | 741 | 2026-03-27 | PNL-003 | Panel | Electrical Panel | 0 | 400A | EA | 3 | 30UMA | 1 | HASSAN MAHDY
742 | 742 | 2026-03-27 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UGB | 130 | HASSAN MAHDY
743 | 743 | 2026-03-28 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10UGB | 9 | RADI
744 | 744 | 2026-03-28 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10USJ | 3 | RADI
745 | 745 | 2026-03-28 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | 1 | 10USJ | 3 | RADI
746 | 746 | 2026-03-28 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 2 | 20UGB | 50 | HASSAN MAHDY
747 | 747 | 2026-03-28 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 50 | HASSAN MAHDY
748 | 748 | 2026-03-28 | MCB-007 | MCB | RCBO | 0 | 1P + N -25A - 30 mA | EA | CEB |  | 3 | SAYED
749 | 749 | 2026-03-28 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | CEB |  | 10 | SAYED
750 | 750 | 2026-03-28 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10USG | 75 | HASSAN MAHDY
751 | 751 | 2026-03-29 | MCB-002 | MCB | MCB | 0 | 1P - 25A | EA | CEB |  | 3 | SAYED
752 | 752 | 2026-03-30 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 4 | 40UGB | 110 | RADI
753 | 753 | 2026-03-30 | CAL-004 | Cable | AL Cable | 0 | 3C x 95+50mm2 [ALU] | M | 4 | 40UGB | 50 | RADI
754 | 754 | 2026-03-30 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 4 | 40UGB | 1 | RADI
755 | 755 | 2026-03-30 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 2 | 20UGB | 1 | RADI
756 | 756 | 2026-03-30 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 2 | 20UGB | 50 | RADI
757 | 757 | 2026-03-30 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UGB | 2 | HASSAN MAHDY
758 | 758 | 2026-03-30 | MCB-013 | MCB | MCCB | 0 | 250 A ( adj. magnetic) | EA |  | PANEL | 1 | RADI
759 | 759 | 2026-03-31 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | S | STORE | 50 | RADI
760 | 760 | 2026-04-02 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 4 | 40UMA | 1 | HASSAN MAHDY
761 | 761 | 2026-04-02 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 4 | 40UMA | 2 | HASSAN MAHDY
762 | 762 | 2026-04-02 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 4 | 40UMA | 120 | HASSAN MAHDY
763 | 763 | 2026-04-03 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 1 | 10UGB | 1 | HASSAN MAHDY
764 | 764 | 2026-04-03 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | 4 | 40UMA | 1 | HASSAN MAHDY
765 | 765 | 2026-04-03 | MCB-012 | MCB | MCCB | 0 | 160 A ( adj. magnetic) | EA |  |  | 1 | HASSAN MAHDY
766 | 766 | 2026-04-03 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | S | STORE | 60 | HASSAN MAHDY
767 | 767 | 2026-04-03 | GEN-002 | D/G | Generator | 0 | 300KVA | 대 | CEB |  | 1 | ashour
768 | 768 | 2026-04-04 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | S | STORE | 50 | HASSAN MAHDY
769 | 769 | 2026-04-05 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 2 | 20UMA | 1 | HASSAN MAHDY
770 | 770 | 2026-04-05 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA | 2 | 20UMA | 1 | HASSAN MAHDY
771 | 771 | 2026-04-05 | MCB-012 | MCB | MCCB | 0 | 160 A ( adj. magnetic) | EA | 4 | 40uma | 1 | HASSAN MAHDY
772 | 772 | 2026-04-05 | LMP-001 | Other | Indication Lamp | 0 | Red | EA | C | PANELS | 2 | HASSAN MAHDY
773 | 773 | 2026-04-05 | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA | CEB |  | 4 | HASSAN MAHDY
774 | 774 | 2026-04-05 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | CEB |  | 12 | HASSAN MAHDY
775 | 775 | 2026-04-05 | PLG-001 | power plug | Industrial Socket | 0 | 3P - 16A | EA | C | PANELS | 50 | HASSAN MAHDY
776 | 776 | 2026-04-05 | PLG-002 | power plug | Industrial Socket | 0 | 3P - 32A | EA | C | PANELS | 9 | HASSAN MAHDY
777 | 777 | 2026-04-05 | PLG-003 | power plug | Industrial Socket | 0 | 5P - 32A | EA | C | PANELS | 27 | HASSAN MAHDY
778 | 778 | 2026-04-06 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | C | FIXTURES | 8 | HASSAN MAHDY
779 | 779 | 2026-04-06 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M | C | FIXTURES | 3 | HASSAN MAHDY
780 | 780 | 2026-04-06 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 4 | 40UMA | 50 | HASSAN MAHDY
781 | 781 | 2026-04-06 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 4 | 40UMA | 50 | HASSAN MAHDY
782 | 782 | 2026-04-06 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UMA | 6 | HASSAN MAHDY
783 | 783 | 2026-04-06 | MCB-013 | MCB | MCCB | 0 | 250 A ( adj. magnetic) | EA | 4 | 40UMA | 1 | HASSAN MAHDY
784 | 784 | 2026-04-07 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 15 | HASSAN MAHDY
785 | 785 | 2026-04-07 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 10 | HASSAN MAHDY
786 | 786 | 2026-04-07 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA |  | 10UMA | 1 | HASSAN MAHDY
787 | 787 | 2026-04-07 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA |  | 20UMA | 1 | HASSAN MAHDY
788 | 788 | 2026-04-07 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA |  | 10UMA | 1 | HASSAN MAHDY
789 | 789 | 2026-04-07 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA |  | 20UMA | 1 | HASSAN MAHDY
790 | 790 | 2026-04-07 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M |  |  | 8 | HASSAN MAHDY
791 | 791 | 2026-04-07 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 3 | 30UMA | 1 | HASSAN MAHDY
792 | 792 | 2026-04-07 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | 3 | 30UMA | 1 | HASSAN MAHDY
793 | 793 | 2026-04-07 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30USG | 1 | HASSAN MAHDY
794 | 794 | 2026-04-07 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 4 | 40UMA | 1 | HASSAN MAHDY
795 | 795 | 2026-04-07 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | C |  | 85 | HASSAN MAHDY
796 | 796 | 2026-04-07 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | C |  | 5 | HASSAN MAHDY
797 | 797 | 2026-04-07 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M | 1 | 10USG | 100 | HASSAN MAHDY
798 | 798 | 2026-04-07 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 50 | HASSAN MAHDY
799 | 799 | 2026-04-07 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10UMA | 1 | HASSAN MAHDY
800 | 800 | 2026-04-07 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UMA | 12 | HASSAN MAHDY
801 | 801 | 2026-04-08 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M |  |  | 50 | RADI
802 | 802 | 2026-04-08 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 12 | RADI
803 | 803 | 2026-04-08 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  |  | 10 | RADI
804 | 804 | 2026-04-08 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA |  |  | 1 | RADI
805 | 805 | 2026-04-08 | PLG-002 | power plug | Industrial Socket | 0 | 3P - 32A | EA | 1 | 10UMA | 1 | RADI
806 | 806 | 2026-04-08 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA |  |  | 1 | RADI
807 | 807 | 2026-04-09 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 2 | 20UMA | 30 | HASSAN MAHDY
808 | 808 | 2026-04-09 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | 2 | 20UMA | 30 | RADI
809 | 809 | 2026-04-09 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | 2 | 20UMA | 1 | RADI
810 | 810 | 2026-04-10 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | CEB | DOOSAN | 125 | RADI
811 | 811 | 2026-04-10 | CAL-017 | Cable | CV Cable | 0 | 3C x 6mm2 | M | CEB | DOOSAN | 30 | RADI
812 | 812 | 2026-04-10 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | CEB | DOOSAN | 3 | RADI
813 | 813 | 2026-04-10 | LMP-001 | Other | Indication Lamp | 0 | Red | EA | CEB | DOOSAN | 1 | RADI
814 | 814 | 2026-04-11 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  |  | 200 | RADI
815 | 815 | 2026-04-11 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA |  |  | 5 | RADI
816 | 816 | 2026-04-11 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA |  |  | 7 | RADI
817 | 817 | 2026-04-11 | LMP-001 | Other | Indication Lamp | 0 | Red | EA | 2 | 20UGB | 1 | RADI
818 | 818 | 2026-04-12 | CAL-027 | Cable | CV Cable | 0 | 3C x 3mm2 | M |  |  | 10 | RADI
819 | 819 | 2026-04-12 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M |  |  | 100 | RADI
820 | 820 | 2026-04-12 | CAL-023 | Cable | Grounding Cable | 0 | 1C x 35mm2 | M |  |  | 35 | RADI
821 | 821 | 2026-04-13 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA |  | PANEL | 1 | RADI
822 | 822 | 2026-04-13 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | C | 90UGG | 50 | RADI
823 | 823 | 2026-04-13 | CAL-030 | Cable | CV Cable | 0 | 4C x 4mm2 | M |  |  | 12 | RADI
824 | 824 | 2026-04-14 | CAL-023 | Cable | Grounding Cable | 0 | 1C x 35mm2 | M | CEB |  | 58 | RADI
825 | 825 | 2026-04-14 | LMP-001 | Other | Indication Lamp | 0 | Red | EA |  |  | 3 | RADI
826 | 826 | 2026-04-15 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M |  | FIXTURES | 10 | RADI
827 | 827 | 2026-04-16 | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA |  | panel | 1 | HASSAN MAHDY
828 | 828 | 2026-04-17 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M |  |  | 160 | HASSAN MAHDY
829 | 829 | 2026-04-17 | MCB-004 | MCB | MCB | 0 | 3P - 32A | EA |  | panel | 1 | HASSAN MAHDY
830 | 830 | 2026-04-18 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA |  |  | 1 | HASSAN MAHDY
831 | 831 | 2026-04-18 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 1 | 10UGB | 125 | HASSAN MAHDY
832 | 832 | 2026-04-19 | MCB-008 | MCB | RCBO | 0 | 1P + N -32A - 30 mA | EA |  | panel | 1 | HASSAN MAHDY
833 | 833 | 2026-04-19 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA |  | panel | 2 | HASSAN MAHDY
834 | 834 | 2026-04-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 2 | 20UMA | 1 | HASSAN MAHDY
835 | 835 | 2026-04-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 2 | 20UGB | 1 | HASSAN MAHDY
836 | 836 | 2026-04-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 1 | 10UMA | 1 | HASSAN MAHDY
837 | 837 | 2026-04-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 1 | 10UGB | 1 | HASSAN MAHDY
838 | 838 | 2026-04-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 3 | 30UMA | 1 | HASSAN MAHDY
839 | 839 | 2026-04-21 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 3 | 30UMA | 20 | HASSAN MAHDY
840 | 840 | 2026-04-22 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 4 | 40UMA | 2 | HASSAN MAHDY
841 | 841 | 2026-04-24 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 1 | 10UMA | 100 | RADI
842 | 842 | 2026-04-26 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA |  | panel | 2 | RADI
843 | 843 | 2026-04-27 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 1 | 10UMA | 1 | RADI
844 | 844 | 2026-04-27 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 1 | 10UGB | 15 | RADI
845 | 845 | 2026-04-28 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 3 | 30UMA | 26 | HASSAN MAHDY
846 | 846 | 2026-04-28 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UGB | 2 | HASSAN MAHDY
847 | 847 | 2026-04-28 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | c |  | 16 | HASSAN MAHDY
848 | 848 | 2026-04-29 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | C |  | 1 | HASSAN MAHDY
849 | 849 | 2026-04-29 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | C |  | 10 | HASSAN MAHDY
850 | 850 | 2026-04-29 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | C | FIXTURES | 20 | HASSAN MAHDY
851 | 851 | 2026-04-30 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | C |  | 5 | HASSAN MAHDY
852 | 852 | 2026-05-01 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 3 | 30UMA | 1 | HASSAN MAHDY
853 | 853 | 2026-05-01 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 3 | 30UMA | 10 | HASSAN MAHDY
854 | 854 | 2026-05-01 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 3 | 30UMA | 150 | HASSAN MAHDY
855 | 855 | 2026-05-02 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 3 | 30UMA | 60 | HASSAN MAHDY
856 | 856 | 2026-05-02 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 2 | 20UMA | 2 | HASSAN MAHDY
857 | 857 | 2026-05-02 | CAL-011 | Cable | CV Cable | 0 | 4C x 35mm2 | M | 2 | 20UMA | 70 | HASSAN MAHDY
858 | 858 | 2026-05-02 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | C |  | 100 | HASSAN MAHDY
859 | 859 | 2026-05-03 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1 | 10USG | 70 | HASSAN MAHDY
860 | 860 | 2026-05-03 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10USG | 100 | HASSAN MAHDY
861 | 861 | 2026-05-03 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 1 | 10USG | 1 | HASSAN MAHDY
862 | 862 | 2026-05-04 | GEN-003 | D/G | Generator | 0 | 150KVA | 대 | 3 | 30UMA | 1 | ASHOUR
863 | 863 | 2026-05-05 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UGB | 30 | HASSAN MAHDY
864 | 864 | 2026-05-05 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 1 | 10UGB | 1 | HASSAN MAHDY
865 | 865 | 2026-05-05 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UGB | 100 | HASSAN MAHDY
866 | 866 | 2026-05-06 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 1 | 10UMA | 100 | HASSAN MAHDY
867 | 867 | 2026-05-06 | MCB-001 | MCB | MCB | 0 | 1P - 16A | EA | 3 | 30UMA | 2 | HASSAN MAHDY
868 | 868 | 2026-05-06 | GEN-005 | D/G | Generator | 0 | 80KVA | 대 | C | 90UTF | 1 | ASHOUR
869 | 869 | 2026-05-07 | PNL-005 | Panel | Electrical Panel | 0 | 250A | EA | 2 | 20USG | 1 | RADY
870 | 870 | 2026-05-07 | CAL-014 | Cable | CV Cable | 0 | 4C x 10mm2 | M | 1 | 10UGB | 10 | RADY
871 | 871 | 2026-05-07 | CAL-025 | Cable | Grounding Cable | 0 | 1C x 16mm2 | M | 2 | 20USG | 12 | RADY
872 | 872 | 2026-05-07 | CAL-023 | Cable | Grounding Cable | 0 | 1C x 35mm2 | M | 2 | 20USG | 35 | RADY
873 | 873 | 2026-05-07 | CAL-029 | Cable | CV Cable | 0 | 3C X 95+50mm2 | M | 2 | 20USG | 45 | RADY
874 | 874 | 2026-05-08 | CAL-022 | Cable | Grounding Cable | 0 | 1C x 70mm2 | M | 2 | 20USG | 8 | RADY
875 | 875 | 2026-05-08 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 2 | 20USG | 2 | RADY
876 | 876 | 2026-05-08 | CAL-015 | Cable | CV Cable | 0 | 4C x 6mm2 | M | 2 | 20USG | 100 | RADY
877 | 877 | 2026-05-09 | PNL-014 | Panel | Electrical Panel | 0 | 63A | EA | 2 | 20USG | 1 | RADY
878 | 878 | 2026-05-10 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20USG | 2 | RADY
879 | 879 | 2026-05-10 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 1 | 10UGB | 20 | HASSAN MAHDY
880 | 880 | 2026-05-11 | LMP-001 | Other | Indication Lamp | 0 | Red | EA |  | PAANEL | 2 | HASSAN MAHDY
881 | 881 | 2026-05-11 | LMP-002 | Other | Indication Lamp | 0 | Yellow | EA |  | PANEL | 2 | HASSAN MAHDY
882 | 882 | 2026-05-11 | LMP-003 | Other | Indication Lamp | 0 | Blue | EA |  | PANEL | 2 | HASSAN MAHDY
883 | 883 | 2026-05-11 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UGB | 10 | HASSAN MAHDY
884 | 884 | 2026-05-11 | PNL-006 | Panel | Electrical Panel | 0 | 160A | EA | C | 90UTF | 1 | HASSAN MAHDY
885 | 885 | 2026-05-11 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | C | 90UTF | 65 | HASSAN MAHDY
886 | 886 | 2026-05-12 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 4 | 40UMA | 1 | HASSAN MAHDY
887 | 887 | 2026-05-12 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 1 | 10UGB | 1 | HASSAN MAHDY
888 | 888 | 2026-05-12 | CAL-006 | Cable | AL Cable | 0 | 3C x 50+25mm2 [ALU] | M | 1 | 10UMA | 100 | HASSAN MAHDY
889 | 889 | 2026-05-13 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | 1 | 10UMA | 1 | ASKARY
890 | 890 | 2026-05-13 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 1 | 10UMA | 1 | ASKARY
891 | 891 | 2026-05-14 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | 1 | 10UMA | 1 | HASSAN MAHDY
892 | 892 | 2026-05-14 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | 1 | 10USJ | 1 | HASSAN MAHDY
893 | 893 | 2026-05-14 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1 | 10UMA | 100 | RADY
894 | 894 | 2026-05-14 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 2 | 20UMA | 50 | RADY
895 | 895 | 2026-05-14 | CAL-019 | Cable | CV Cable | 0 | 3C x 2.5mm2 | M | 2 | 20UMA | 50 | HASSAN MAHDY
896 | 896 | 2026-05-15 | MCB-003 | MCB | MCB | 0 | 1P - 32A | EA | C | PANELS | 1 | HASSAN MAHDY
897 | 897 | 2026-05-15 | MCB-010 | MCB | RCCB | 0 | 4P - 63A - 30 mA | EA | C | PANELS | 1 | HASSAN MAHDY
898 | 898 | 2026-05-16 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 17 | HASSAN MAHDY
899 | 899 | 2026-05-16 | LTG-003 | LTG | Lighting Fixture | 0 | 100W | EA | 2 | 20UMA | 4 | HASSAN MAHDY
900 | 900 | 2026-05-16 | LTG-004 | LTG | Lighting Fixture | 0 | 50W | EA | 2 | 20UMA | 3 | HASSAN MAHDY
901 | 901 | 2026-05-17 | MCB-006 | MCB | RCBO | 0 | 1P + N -16A - 30 mA | EA | C | PANELS | 1 | HASSAN MAHDY
902 | 902 | 2026-05-18 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 10 | DOOSAN CIVIL
903 | 903 | 2026-05-18 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 1 | 10UGB | 13 | HASSAN MAHDY
904 | 904 | 2026-05-19 | MCB-002 | MCB | MCB | 0 | 1P - 25A | EA | C | PANELS | 1 | HASSAN MAHDY
905 | 905 | 2026-05-19 | LTG-002 | LTG | Lighting Fixture | 0 | 200W | EA | 2 | 20UMA | 10 | HASSAN MAHDY
906 | 906 | 2026-05-19 | LTG-001 | LTG | Lighting Fixture | 0 | 400W | EA | 2 | 20UMA | 10 | HASSAN MAHDY
907 | 907 | 2026-05-19 | CAL-013 | Cable | CV Cable | 0 | 4C x 16mm2 | M | 1 | 10UGB | 100 | HASSAN MAHDY
908 | 908 | 2026-05-19 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 1 | 10UGB | 1 | HASSAN MAHDY
909 | 909 | 2026-05-20 | CAL-018 | Cable | CV Cable | 0 | 3C x 4mm2 | M | 4 | 40USG | 100 | HASSAN MAHDY
910 | 910 | 2026-05-20 | PNL-009 | Panel | Electrical Panel | 0 | 100A | EA | 4 | 40USG | 1 | HASSAN MAHDY
911 | 911 | 2026-05-20 | MCB-005 | MCB | MCB | 0 | 3P - 63A | EA | C | PANELS | 1 | HASSAN MAHDY
912 | 912 | 2026-05-20 | PLG-004 | power plug | Industrial Socket | 0 | 5P - 63A | EA | C | PANELS | 1 | HASSAN MAHDY
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0
913 | 913 |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | 3 | 4 | 4 | 5

## Summary Table
Summary Table
| No | 품목 | 규격 | 단위 | 두산 | [5 empty] | 대선 | [5 empty] | Remark
[5 empty] | 발주 | 입고 | 미입고 | 타업체 인계 | 불출 | 재고 | 인수 | 불출 |  |  | 소계 | 재고
[12 empty] | 설치 | 제작 | Scrap
| A | Grounding | [8 empty] | 0
GR001 | 1 | Ground Cable | 78SQ | M | 17500 | 17200 | 300 | 300 | 17200 | 0 | 17200 | 14194.1 | 0 | 872.4 | 15066.5 | 2133.5
GR002 | 2 | Ground Cable | 70SQ | M | 3120 | 3120 | 0 | 0 | 3120 | 0 | 3120 | 258 | 0 | 0 | 258 | 2862
GR004 | 3 | Cadweld Powder | #90 | EA | 100 | 100 | 0 | 0 | 100 | 0 | 100 | 5 | 0 | 2 | 7 | 93
GR005 | 4 | Cadweld Powder | #115 | EA | 540 | 540 | 0 | 0 | 540 | 0 | 540 | 207 | 0 | 16 | 223 | 317
GR006 | 5 | Cadweld Powder | #150 | EA | 100 | 100 | 0 | 0 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 100
GR007 | 6 | Cadweld Powder | #200 | EA | 1332 | 1332 | 0 | 0 | 1332 | 0 | 1332 | 742 | 0 | 223 | 965 | 367
GR008 | 7 | Cadweld Mold | Cross (+) | EA | 30 | 30 | 0 | 0 | 30 | 0 | 30 | 13 | 0 | 0 | 13 | 17
GR009 | 8 | Cadweld Mold | Parallel (=) | EA | 12 | 12 | 0 | 0 | 12 | 0 | 12 | 3 | 0 | 0 | 3 | 9
GR010 | 9 | Cadweld Mold | Cross (T) | EA | 5 | 5 | 0 | 0 | 5 | 0 | 5 | 1 | 0 | 0 | 1 | 4
GR012 | 10 | Nicoband | 10m x 15cm | EA | 770 | 20 | 750 | 0 | 20 | 0 | 20 | 11 | 0 | 0 | 11 | 9
GR013 | 11 | Flexible Conduit | 2", 50mm | M | 2200 | 2200 | 0 | 0 | 2200 | 0 | 2200 | 859 | 0 | 121 | 980 | 1220
GR014 | 12 | PVC Flexible Pipe ф 20 | ф20 | M | 140 | 140 | 0 | 0 | 140 | 0 | 140 | 0 | 0 | 0 | 0 | 140
| B | Conduit | [7 empty] | 0
CO003 | 1 | Conduit (Galvanized) | 6.5" | M | 172 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO005 | 2 | Conduit (Galvanized) | 5.5" | M | 530 | 530 | 0 | 0 | 530 | 0 | 530 | 0 | 189 | 0 | 189 | 341
CO001 | 3 | Conduit (Galvanized) | 4.5" | M | 2551 | 2437 | 114 | 0 | 2437 | 0 | 2437 | 1438 | 597 | 270 | 2305 | 132
CO002 | 4 | Conduit (Galvanized) | 3" | M | 5390 | 5390 | 0 | 0 | 5390 | 0 | 5390 | 1452 | 460 | 238 | 2150 | 3240
CO004 | 5 | Conduit | 6" | M | 1400.32 | 1400.32 | 0 | 0 | 1400.32 | 0 | 1400.32 | 1176 | 0 | 116.32 | 1292.32 | 108
CO007 | 6 | Conduit | 4" | M | 6040 | 5956 | 84 | 66 | 5956 | 0 | 5956 | 5156.488 | 113 | 555.512 | 5825 | 131
CO008.1 | 7 | Conduit (Galvanized) | 2" | M | 18 | 18 | 0 | 0 | 18 | 0 | 18 | 18 | 0 | 0 | 18 | 0
CO011 | 8 | Coupling (Galvanized) | 5.5" | EA | 120 | 60 | 60 | 0 | 60 | 0 | 60 | 0 | 14 | 0 | 14 | 46
CO014 | 9 | Coupling (Galvanized) | 4.5" | EA | 280 | 280 | 0 | 0 | 280 | 0 | 280 | 175 | 0 | 0 | 175 | 105
CO015 | 10 | Coupling (Galvanized) | 3" | EA | 440 | 440 | 0 | 0 | 440 | 0 | 440 | 368 | 0 | 0 | 368 | 72
CO009 | 11 | Coupling | 6" | M | 44 | 44 | 0 | 0 | 44 | 0 | 44 | 1.3 | 0 | 0 | 1.3 | 42.7 | 284.6667
CO010 | 12 | Coupling | 6" | EA | 200 | 200 | 0 | 0 | 200 | 0 | 200 | 188 | 0 | 0 | 188 | 12
CO011 | 13 | Coupling (Galvanized) | 5.5" | EA | 120 | 60 | 60 | 0 | 60 | 0 | 60 | 0 | 14 | 0 | 14 | 46 | 추가
CO012 | 14 | Coupling | 4" | M | 104 | 104 | 0 | 0 | 104 | 0 | 104 | 48 | 1.5 | 0 | 49.5 | 54.5 | 363.3333
CO013 | 15 | Coupling | 4" | EA | 456 | 456 | 0 | 0 | 456 | 0 | 456 | 423 | 33 | 0 | 456 | 0
CO015.1 | 16 | Coupling (Galvanized) | 2" | EA | 9 | 9 | 0 | 0 | 9 | 0 | 9 | 9 | 0 | 0 | 9 | 0
CO016 | 17 | Angle | 50*50*5 | M | 3584 | 3584 | 0 | 0 | 3584 | 0 | 3584 | 2726 | 459.1 | 326.9 | 3512 | 72
CO017 | 18 | Angle | 70*70*7 | M | 732 | 732 | 0 | 0 | 732 | 0 | 732 | 414.4 | 0 | 29.6 | 444 | 288
CO019a | 19 | JOTUN Pipe Primer Paint (A) | 16L | CAN | 23 | 6 | 17 | 1 | 6 | 0 | 6 | 5 | 0 | 0 | 5 | 1
CO019b | 20 | JOTUN Pipe Primer Paint (B) | 4L | CAN | 23 | 6 | 17 | 1 | 6 | 0 | 6 | 5 | 0 | 0 | 5 | 1
CO020 | 21 | JOTUN Pipe Top-coated Paint | 20L | CAN | 21 | 0 | 21 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CO021 | 22 | JOTUN Thinner | 20L | CAN | 21 | 2 | 19 | 1 | 2 | 0 | 2 | 1 | 0 | 0 | 1 | 1
| C | CCGG | [7 empty] | 0
CG001 | 1 | Steel round bar(rebar) | ф10 | M | 156805.25 | 111445.25 | 45360 | 0 | 111445.25 | 0 | 111445.25 | 100172.6 | 800 | 1816.833 | 102789.433 | 8655.817
CG002 | 2 | Angle | 100x100x10 (12m) | M | 3132 | 1200 | 1932 | 0 | 1200 | 0 | 1200 | 927 | 3.5 | 19.5 | 950 | 250
CG003 | 3 | Plate | 1000x6000x8 | PCS | 10 | 1 | 9 | 0 | 1 | 0 | 1 | 0.8 | 0 | 0 | 0.8 | 0.2
CG004 | 4 | Plate | 1500x6000x10 | PCS | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1
|  | 21 | 22 | 23

## Tray
| No | 품 명 | Items / Services | 규 격 | Unit | DOOSAN | [5 empty] | DAESUN |  |  |  |  | Remarks
[6 empty] | 발주 | 입고 | 미입고 | 타업체 인계 | 불출 | 재고 | 인수 | 불출
[13 empty] | 설치 | 제작 | 스크랩 | 재고
TRY027 | 1 | Console KS3-750 | 3-KS3-750-M-TA4 | 754x45x146; T=3.0 | pcs | 1865 | 1865 | 0 | 0 | 423 | 1442 | 423 | 144 | 0 | 0 | 279
TRY035 | 2 | Rack ST | 3-ST-260-4-M-TA4 | 2600x63x37x20; T=4.0 | pcs | 244 | 244 | 0 | 0 | 119 | 125 | 119 | 18 | 0 | 0 | 101
TRY046 | 3 | Simple gusset KP for racks ST | 3-KP-4-M-TA4 | 170x72x110; T=4.0 | pcs | 74 | 74 | 0 | 0 | 56 | 18 | 56 | 0 | 0 | 0 | 56
TRY049 | 4 | Side gusset KB for racks ST | 3-KB-4-M-TA4 | 150x72x70; T=4.0 | pcs | 4700 | 4700 | 0 | 0 | 1046 | 3654 | 1046 | 90 | 0 | 0 | 956
TRY050 | 5 | Double gusset KD for racks STD | 3-KD-4-M-TA4 | 109x72x72x110; T=4.0 | pcs | 153 | 153 | 0 | 0 | 141 | 12 | 141 | 0 | 0 | 0 | 141
TRY053 | 6 | Transition clamp SP 150 for gussets | 3-SP-150-M-TA4 | 150x142x59; T=4.0 | pcs | 4926 | 4926 | 0 | 0 | 1102 | 3824 | 1102 | 90 | 0 | 0 | 1012