## Sheet1
|  | ■ 본공사 자재 입.출고 현황 (Status of main construction materials) | [5 empty] | Current status of Doosan | [5 empty] | ※ Update every Sunday!!
|  | 【Project : El-Dabaa Nuclear Power Plant (ENPP) #1 to 4】 | [16 empty] | 2026-05-19
| Code | No | Sortation | Material No. | Items / Services | Size | Unit | DOOSAN | [5 empty] | DAESUN |  |  |  |  | Remarks | BALANCE IN REALITY | PCS | DATE
[8 empty] | Purchase | Incoming | Not come | Other company | Handover | Balance | Incoming | Install | Fabrication | Scrap/ Faulty | Balance
1 |  | A |  | Grounding
9 | GR001 | 1 | Ground | Ground Cable 78SQ | Ground Cable | 78SQ | M | 17500 | 17200 | 300 | 300 | 17200 | 0 | 17200 | 14128.1 |  | 872.4 | 2199.5 |  | UNCOUNTABLE | UNCOUNTABLE | 16/5/2026
3 | GR002 | 2 | Ground | Ground Cable 70SQ | Ground Cable | 70SQ | M | 3120 | 3120 | 0 |  | 3120 | 0 | 3120 | 258 |  | 0 | 2862 |  | UNCOUNTABLE | UNCOUNTABLE | 16/5/2026
4 | GR003 | 3 | Ground Fitting | Ground TERMINAL LUG 70mm2 | Terminal Lug | 70mm2 | EA | 200 | 200 | 0 |  | 200 | 0 | 200 |  |  |  | 200 |  | 200 | 200 | 16/5/2026
5 | GR004 | 4 | Ground | Cadweld Powder #90 | Cadweld Powder | #90 | EA | 100 | 100 | 0 |  | 100 | 0 | 100 | 5 |  | 2 | 93 |  | 100 | 100 | 16/5/2026
6 | GR005 | 5 | Ground | Cadweld Powder #115 | Cadweld Powder | #115 | EA | 540 | 540 | 0 |  | 540 | 0 | 540 | 201 |  | 16 | 323 |  | 350 | 350 | 16/5/2026
7 | GR006 | 6 | Ground | Cadweld Powder #150 | Cadweld Powder | #150 | EA | 100 | 100 | 0 |  | 100 | 0 | 100 |  |  |  | 100 |  | 100 | 100 | 16/5/2026
8 | GR007 | 7 | Ground | Cadweld Powder #200 | Cadweld Powder | #200 | EA | 1332 | 1332 | 0 |  | 1332 | 0 | 1332 | 742 |  | 223 | 367 |  | 380 | 380 | 16/5/2026
9 | GR008 | 8 | Ground | Cadweld XBQ-Y4Y4 | Welding Mold | Cross (+) | EA | 30 | 30 | 0 |  | 30 | 0 | 30 | 13 |  |  | 17 |  | 17 | 17 | 16/5/2026
10 | GR009 | 9 | Ground | Cadweld PGC-Y4Y4 | Welding Mold | Parallel (=) | EA | 12 | 12 | 0 |  | 12 | 0 | 12 | 3 |  | 0 | 9 |  | 6 | 6 | 16/5/2026
11 | GR010 | 10 | Ground | Cadweld TAC-Y4Y4 | Welding Mold | Cross (T) | EA | 5 | 5 | 0 |  | 5 | 0 | 5 | 1 |  | 0 | 4 |  | 4 | 4 | 16/5/2026
12 | GR011 | 11 | Ground | Zinc Spray | Zinc Spray |  | EA | 196 | 196 | 0 |  | 196 | 0 | 196 | 99 |  |  | 97 |  | 84 | 84 | 16/5/2026
13 | GR012 | 12 | Miscellious | Nicoband | Nicoband | 10m x 15cm | EA | 770 | 20 | 750 |  | 20 | 0 | 20 | 6 |  | 0 | 14 |  |  |  | 16/5/2026
14 | GR013 | 13 | Ground Conduit | Flexible Conduit 2" | Ground Conduit | 2" | M | 2200 | 2200 | 0 |  | 2200 | 0 | 2200 | 859 |  | 121 | 1220 |  |  | _ | 16/5/2026
15 | GR014 | 14 | PVC PIPE | PVC Flexible Pipe ф 20 | PVC PIPE | ф20 | M | 140 | 140 | 0 |  | 140 | 0 | 140 | 0 |  | 0 | 140 |  | 100 + SMALL PCS | _ | 16/5/2026
16 | GR015 | 15 | Ground | nVent Exothemic Welding Control Unit | CAD WELD GUN |  | EA | 3 | 3 | 0 |  | 3 | 0 | 3 | 2 |  | 0 | 1 |  | 1 | 1 | 16/5/2026
17 |  | B |  | Conduit |  |  |  |  | 0 |  |  | 0 | 0 |  |  |  |  | _ |  |  |  | 16/5/2026
18 | CO001 | 1 | Conduit | Conduit (Galvanized) Ts-100x4.5 | Conduit (Galvanized) | 114x4.5 | M | 2437 | 2437 | 0 |  | 2437 | 0 | 2437 | 1438 | 408 | 255 | 336 |  | 130 | 13×12M | 16/5/2026
19 | CO002 | 2 | Conduit | Conduit (Galvanized) Ts-80x4 | Conduit (Galvanized) | 88x4 | M | 5390 | 5390 | 0 |  | 5390 | 0 | 5390 | 1452 | 376 | 238 | 3324 | ULD 및 UGD 필요수량 포함 | 2964+ SMALL PCS | 60+60+34+67+26×12M | 16/5/2026
20 | XX-CO003 | 3 | Conduit | Conduit 159x4.5 | Conduit | 159x6.0 | M | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | _ | 설계 변경 → 6.5"(168mm) |  |  | 16/5/2026
25 | CO003 | 4 | Conduit | Conduit (Galvanized) 168x6 | Conduit (Galvanized) | 168x6 | M | 172 | 172 | 0 |  | 172 | 0 | 172 | 0 |  | 0 | 172 | 설계 추가 | 156+ SMALL PCS | 13 PCS×12M | 16/5/2026
21 | CO004 | 5 | Conduit | Conduit 159x4.5 | Conduit | 159x4.5 | M | 1400.32 | 1400.32 | 0 |  | 1400.32 | 0 | 1400.32 | 1176 |  | 116.32 | 108 |  |  |  | 16/5/2026
22 | CO005 | 6 | Conduit | Conduit (Galvanized) 140x5 | Conduit (Galvanized) | 140x5 | M | 530 | 530 | 0 |  | 530 | 0 | 530 | 0 | 189 | 0 | 341 |  | 430 | 43×10M | 16/5/2026
23 | XX-CO006 | 7 | Conduit | Conduit 108x5 | Conduit | 108x5 | M | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | _ | 설계 삭제(토건 역무) |  |  | 16/5/2026
24 | CO007 | 8 | Conduit | Conduit 108x4.0 | Conduit | 108x4 | M | 6040 | 5956 | 84 | 66 | 5956 | 0 | 5956 | 5156.488 | 113 | 555.512 | 131 | (Scrap 555.5)-(발전기 굴뚝 : 86M) | 150 + SMALL PCS | 15×10M | 16/5/2026
25 | CO008.1 | 9 | Conduit | Conduit (Galvanized) 60.3x3.91 | Conduit (Galvanized) | 60.3x3.91 | M | 18 | 18 | 0 |  | 18 | 0 | 18 | 0 | 0 | 0 | 18 | 추가 |  |  | 16/5/2026
26 | CO009 | 10 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | M | 44 | 44 | 0 |  | 44 | 0 | 44 | 1.3 |  | 0 | 42.7 | 284.6667 | 336(160 RETURNED TO DOOSAN) | 241 IN WARHOUSE+95 INSTALLED | 16/5/2026
27 | CO010 | 11 | Conduit Fitting | Conduit Coupling 168x4 | Conduit Coupling | 168x4 | EA | 200 | 200 | 0 |  | 200 | 0 | 200 | 188 | 0 | 0 | 12 |  |  |  | 16/5/2026
28 | CO011 | 12 | Conduit Fitting | Conduit Coupling 125-Ts | Conduit Coupling | Ts-152x5 | EA | 120 | 60 | 60 |  | 60 | 0 | 60 | 0 |  | 0 | 60 |  |  |  | 16/5/2026
29 | CO012 | 13 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | M | 104 | 104 | 0 |  | 104 | 0 | 104 | 48 | 1.5 | 0 | 54.5 | 363.3333 |  |  | 16/5/2026
30 | CO013 | 14 | Conduit Fitting | Conduit Coupling 121x5 | Conduit Coupling | 121x5 | EA | 456 | 456 | 0 |  | 456 | 0 | 456 | 423 | 33 | 0 | _ |  |  |  | 16/5/2026
31 | CO014 | 15 | Conduit Fitting | Conduit Coupling 100-Ts | Conduit Coupling | 100-Ts | EA | 280 | 280 | 0 |  | 280 | 0 | 280 | 120 | 35 | 0 | 125 |  |  |  | 16/5/2026
32 | CO015 | 16 | Conduit Fitting | Conduit Coupling 80-Ts | Conduit Coupling | 80-Ts | EA | 440 | 440 | 0 |  | 440 | 0 | 440 | 97 | 44 | 0 | 299 |  |  |  | 16/5/2026
| CO015.1 | 17 | Conduit Fitting | Conduit Coupling | Conduit Coupling | 50-11 NPT | EA | 9 | 9 | 0 |  | 9 | 0 | 9 | 9 | 0 |  | _ | 추가 |  |  | 16/5/2026
33 | CO016 | 18 | Sup't | Angle 50x50x5 | Angle | 50*50*5 | M | 3968 | 3968 | 0 |  | 3968 | 0 | 3968 | 2726 | 43.1 | 326.9 | 872 | ULD 및 UGD 필요수량 포함 | 466 | 8×12M | 16/5/2026
34 | CO017 | 19 | Sup't | Angle 70x70x7 | Angle | 70*70*7 | M | 732 | 732 | 0 |  | 732 | 0 | 732 | 414.4 |  | 29.6 | 288 |  | 288 | 24×12M | 16/5/2026
35 | CO018 | 20 | Sup't | Angle 75x75x5 | Angle | 75x75x5 | M | 40 | 40 | 0 |  | 40 | 0 | 40 | 35 |  | 5 | _ |  |  | _ | 16/5/2026
36 | CO019a | 21 | Paint | JOTUN Pipe Primer Paint (A) | Paint | 16L | CAN | 23 | 6 | 17 | 1 | 6 | 0 | 6 | 5 |  |  | 1 |  | 1 | 1 | 16/5/2026
36 | CO019b | 22 | Paint | JOTUN Pipe Primer Paint (B) | Paint | 4L | CAN | 23 | 6 | 17 | 1 | 6 | 0 | 6 | 5 |  |  | 1 |  | 1 | 1 | 16/5/2026
37 | CO020 | 23 | Paint | JOTUN Pipe Top-coated Paint | Paint | 20L | CAN | 21 | 0 | 21 | 1 | 0 | 0 | 0 | 0 |  |  | _ |  |  | _ | 16/5/2026
38 | CO021 | 24 | Paint | JOTUN Thinner | Paint | 20L | CAN | 21 | 2 | 19 | 1 | 2 | 0 | 2 | 1 |  |  | 1 |  | 1 | 1 | 16/5/2026
39 |  | C |  | CCGG |  |  |  |  | 0 |  |  | 0 | 0 | [8 empty] | 16/5/2026
40 | CG001 | 1 | Steel round bar | Steel round bar(rebar) | CCGG | ф10, 1ton=1,620.7m | M | 156805.25 | 111445.25 | 45360 |  | 111445.25 | 0 | 111445.25 | 98727.6 | 800 | 1796.833 | 10120.817 | 1 ton=1620.7 | 9720+SMALL PCS(TOOK FROM 1) | 3 BOXES(2 ton)=6 ton | 16/5/2026
41 | CG002 | 2 | Angle | Angle 100x100x10 | CCGG | 100x100x10 (12m) | M | 3132 | 1200 | 1932 |  | 1200 | 0 | 1200 | 927 | 3.5 | 19.5 | 250 |  | 264 | 22 PCS + SMALL PCS | 16/5/2026
42 | CG003 | 3 | Plate | Carbon Plate 1000x6000x8 | CCGG | 1000x6000x8 | PCS | 10 | 1 | 9 |  | 1 | 0 | 1 | 0.8 | 0 | 0 | 0.2 |  |  |  | 16/5/2026
42 | CG004 | 4 | Plate | Carbon Plate 1500x6000x10 | CCGG | 1500x6000x10 | PCS | 1 | 1 | 0 |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 |  |  |  | 14/V48+W13+W6:W50
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
[15 empty] | 92837.6 | -5890
Note on M37: 128ea return